## Sheet1
Annex-7
Itemwise FA Budget & Reimbursement Position under CDSP-III as on 31st December 2010
Sl. No. | Item | 2nd Revised Budget Allocation (BDT in lakh) | Expenditure incurred & claimed by IAs (BDT in lakh) | Recommended by TA Team (BDT in lakh)
Name of Agency: BWDB
A. | Baggardona Upstream area
(Civil Work)
1 | Re-excavation of Baggardona
| (Bhulua river) River (10 km.) | 648 | 626.04 | 626.04
2 | Re-excavation of Jarirdona khal(3.535 km) | 400 | 377.78 | 377.78
3 | Short cut Drainage cannel (Jarirdona 3.50 km) | 629 | 606.65 | 606.65
| Sub-Total of A. | 1677 | 1610.47 | 1610.47
B. | Boyer Char & Char Moradona area
1 | Drainage Sluice (DS-2, 7V-2.20x2.20m) | 570 | 505.42 | 505.42
2 | Closure-1 (D/S of steamer ghat) | 246.87 | 193.6 | 193.6
3 | Closure-2 (at CBD-I) | 113 | 85.2 | 85.2
4 | Embankment in Boyer Char (18.87 km) | 950 | 853.61 | 853.61
5 | Guide dyke cum rural road (2.96 km) | 81 | 80.77 | 80.77
6 | Short cut Drainage channel at Gabtoli (6.00 km) | 267 | 258.75 | 258.75
7 | Re-excavation of Banskhali Khal at D/S of sluice (2.10 km) | 110 | 109.17 | 109.17
8 | Improvement of Secondary drainage channel (38 km) | 68 | 36.52 | 36.52
9 | Drainage cum flushing sluices (Tanki & Chatla) | 230 | 135.58 | 135.58
| Sub-Total of B. | 2635.87 | 2258.62 | 2258.62
C. | Other cost
1 | Additional drainage study | 99.2 | 86.55 | 86.55
| Sub-Total of C. | 99.2 | 86.55 | 86.55
Total of BWDB |  | 4412.07 | 3955.64 | 3955.64
Name of Agency : LGED
Boyer Char & Char Moradona area
i) | Rural Infrastructure
| a) Road (Paved 18.75 km.) | 714 | 659.92 | 659.92
| b) Rural Road (Earthen 62 km.) | 230 | 209.37 | 209.37
| c) Bridge (3 nos.) | 200 | 198.87 | 198.87
| d) Foot bridge (1 no.) | 11 | 9.4 | 9.4
| e) Box culvert (29 nos.) | 320 | 287 | 287
| f) Pipe Culvert (40 nos.) | 55 | 53.45 | 53.45
ii) | Settlement Infrastructure
| a) Cyclone shelter (20 nos.) | 1240 | 1212.74 | 1212.58
| b) Community Pond (50 nos.) | 80 | 70.4 | 70.4
| c) Bus stand (1 no.) | 60 | 59.23 | 59.23
Total of LGED |  | 2910 | 2760.43 | 2760.28
Name of Agency : DPHE
A. | Boyer Char area
| a) Single pit latrine (8500 nos.) | 187 | 153.96 | 141.841
| b) Public Toilet in Market (20 nos.) | 150 | 134.1 | 132.2
| c) Deep Tubewell (600 nos.) | 300 | 241.5 | 234.63
d) Development of community pond with
| arrangement of PSF (47 nos.) | 105.75 | 59.9 | 53.89
| e) Rain Water Harvesting (60 nos.) | 13.5 | 11.64 | 11.64
| Sub-Total of A. | 756.25 | 601.1 | 574.201
B. | Other cost
| a) Training software activities (LS) | 31.15 | 10.07 | 10.07
| b) Test Tubewell (18 nos.) | 12.6 | 9.59 | 9.59
| Sub-Total of B. | 43.75 | 19.66 | 19.66
Total of DPHE |  | 800 | 620.74 | 593.861
Name of Agency : FD
A. | Plantation Programme
1 | Establishment of Mangrove plantation (500 ha) | 30.5 | 30.5 | 30.5
2 | Establishment of Foreshore Plantation (200 ha) | 236.4 | 62.83 | 53.7
3 | Establishment of strip Plantation
| a) Embankment Plantation (28.5 km.) | 14.4 | 14.39 | 13.32
| b) Feeder Road Plantation (120 km.) | 15.78 | 15.778 | 12.24
4 | Village afforestation (52 nos.) | 63.844 | 63.842 | 59.509
| Sub-Total of A. | 360.924 | 187.34 | 169.269
B. | Plantation Maintenance
| a) Mangrove plantation (500 ha) | 13 | 13 | 13
| b) Foreshore Plantation (200 ha) | 11.65 | 0 | 0
| c) Embankment Plantation (28.5 km) | 13.48 | 11.9 | 8.86
| d) Feeder Road Plantation (60 ha) | 3.564 | 2.34 | 2.34
| Sub-Total of B. | 41.694 | 27.24 | 24.2
C. | Other cost
| a) Contingencies (LS) | 6.37 | 6.14 | 6.12
| b) Local Training & Logistic (1800 person) | 51.052 | 51.31 | 42.53
| c) Manpower (MR Basis) | 75.39 | 70.06 | 70.06
| Sub-Total of C. | 132.812 | 127.51 | 118.71
Total of FD |  | 535.43 | 342.09 | 312.179
Name of Agency : DAE
A. | Boyerchar area
1 | Demonstration (7 items) | 20.4 | 20.3 | 20.3
2 | Farmers Training (Local 288 nos.) | 17.28 | 17.28 | 17.28
3 | Farmer Motivation Tour (32 nos.) | 11.2 | 11.2 | 11.2
4 | Workshop/ seminar (Local 6 nos.) | 3.12 | 3.08 | 3.08
5 | On-farm testing of new technology (LS) | 3.4 | 1.3 | 1.3
6 | Procurement of support materials (LS) | 7 | 4.1 | 4.1
7 | Training of Trainers (9 nos.) | 2.4 | 2.08 | 2.08
8 | Printing Extension Materials (LS) | 1 | 1 | 1
9 | Contingency (LS) | 0.7 | 0.7 | 0.7
Total of DAE |  | 66.5 | 61.04 | 61.04
Name of Agency : MoL
A. | Settlement Progamme
| a) Construction of twin houses | 33.26 | 11.53 | 11.53
| b) Other Expenditure (Khs land dis. & LRMS Program) | 60 | 3 | 0
| c) Excavation of Ponds | 200 | 123.18 | 123.18
| d) Rehabilitation of 3000 families | 202.74 | 58.73 | 58.73
Total of MoL |  | 496 | 196.44 | 193.44
Grand Total (BWDB+LGED+DPHE+FD+DAE+MoL) |  | 9220 | 7936.39 | 7876.45

## Sheet2
| E/R |  | C/S |  | Pond | BC
| 517890 |  | 989887 |  | 51673
| 295480 |  | 458178 |  | 65672
| 350363 |  | 834794 |  | 57529
| 325738 |  | 472787 |  | 57632
| 362460 |  | 1113663 |  | 41171
| 357714 |  | 1009784 |  | 37958
| 321021 |  | 435973 |  | 51159
| 297593 |  | 898742 |  | 65229
| 208055 | 208055 | 893204 |  | 63291
| 376711 |  | 898484 |  | 59742
| 3413025 | 208055 | 8005496 |  | 57647
71253
| 204362 |  | 1363279 | 254250 | 679956 | 538066
| 150195 |  | 951430 |  |  | 648257
| 51090 |  | 278416 |  |  | 1186323
| 37549 |  | 897226
| 443196 |  | 108993
1055103
1348184
1361099
1094377
559655
569923
713070
|  |  | 10300755 | 254250
Total | 3856221 | 208055 | 18306251 | 254250 | 679956 | 1186323