## Overview BWDB
Table 1 - BWDB | Design available (y/n) % | Design concurred (y/n) % | Estimate concurred (y/n) % | Floating tender (y/n) % | Work order given (y/n) % | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Invested amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks | Estimated amount Tk. In Lakh
Item of work | [6 empty] | 2010-12-31 |  |  | 93.5342
Total BWDB | 100 | 100 | 100 | 100 | 100 | 98.9327 | 100 | -1.0673 | 4268.091 | 3992.1263 | 3955.644 | 3955.644
1) Embankments | [8 empty] | 933.2842 |  | 853.607 | 853.607
Total sea dyke (10.87 km) | 100 | 100 | 100 | 100 | 100 | 99.0493 | 100 | -0.95069 | 542.6342 | 539.6225 | 500.456 | 500.456
Total interior dyke (8 km) | 100 | 100 | 100 | 100 | 100 | 99.3998 | 100 | -0.60023 | 390.65 | 388.3052 | 353.151 | 353.151
1.1) Sea dyke, 0.63km-3.365km (2.5 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 132.44 | 132.44 | 138.29 | 138.29 | package 1- 5 all completed
1.2) Sea dyke, 3.365km-5.085km (1.72 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 76.12 | 76.12 | 72.956 | 72.956 | package 4 completed
1.3) Sea dyke, 5.085km-8.585km (3.5 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 154.8742 | 154.8742 | 153.35 | 153.35 | package 1- 5 all completed
1.4) Sea dyke, 8.585km-11.5km (2.915 km), Noakhali | y | y | y | y | y | 98.3194 | 100 | -1.6806 | 179.2 | 176.1883 | 135.86 | 135.86 | package 6 achieved 96.5% progress up to 31-12-10 & package 7 completed
1.5) Interior dyke, 11.5km-19.5km (8 km), Noakhali | y | y | y | y | y | 99.3998 | 100 | -0.60023 | 390.65 | 388.3052 | 353.151 | 353.151 | 5 packages, package 8 achieved 96.9% progress up to 31-12-10 and package-9 to 12 all completed
2) Individual guide dyke
Total guide dyke (2.965 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 82.09 | 82.09 | 80.77 | 80.77
2.1) Guide dyke cum rural road, 7.035km-10.00km (2.965 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 82.09 | 82.09 | 80.77 | 80.77 | 2 packages, all completed.
3) Re-excavations
Total Jarirdona (3.535 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 387.12 | 387.12 | 377.777 | 377.777
Total Bagardona (10 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 644.942 | 644.942 | 626.034 | 626.034
3.1) Re-excavation Jarirdona, 0km-2.625km (2.625 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 281.54 | 281.54 | 277.33 | 277.33 | 4 packages, all completed
3.2) Re-excavation Jarirdona, 2.625km-3.535km (0.91 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 105.58 | 105.58 | 100.447 | 100.447 | 1 package, completed
3.3) Re-excavation Baggardona, 7.035km-13.935km (6.9 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 419.74 | 419.74 | 404.969 | 404.969 | 5 packages, all completed.
3.4) Re-excavation Baggardona, 13.935km-17.035km (3.1 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 225.202 | 225.202 | 221.065 | 221.065 | 3 packages, all completed.
4) Excavations
4) Short cuts
Total Jarirdona shortcut (3.5 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 613.81 | 592.79 | 606.652 | 606.652
Total Gabtali khal (6.155 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 266.36 | 266.36 | 258.754 | 258.754
Total Secondary drainage channel (21 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 36.68 | 30.15 | 36.523 | 36.523
4.1) Jarirdona shortcut, 3.535km-3.925km (0.39 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 62.67 | 62.67 | 58.766 | 58.766 | 1 package, completed
4.2) Jarirdona shortcut, 3.925km-6.035km (2.11 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 371.15 | 371.15 | 368.048 | 368.048 | 5 packages, all completed
4.3) Jarirdona shortcut, 6.035km-7.035km (1 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 158.97 | 158.97 | 158.95 | 158.95 | 2 packages, completed.
4.4) drainage channel Gabtali khal (6.155 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 266.36 | 266.36 | 258.754 | 258.754 | 4 packages, all completed
4.5) improvement of secondary drainage (6 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 6.53 | 6.53 | 6.39 | 6.39 | 1 package, completed
4.6) improvement secondary drainage (15 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 30.15 | 30.15 | 30.133 | 30.133 | 1 package, completed
110
4.7) improvement of Banshkhali khal (2.100 km) | y | y | y | y | y | 100 | 100 | 0 | 109.21 |  | 109.168 | 109.168 | 1 package, completed
5) Sluices (3 nos)
Total sluices | 100 | 100 | 100 | 100 | 100 | 99.514 | 100 | -0.48602 | 715.7251 | 712.2466 | 641.001 | 641.001
5.1) Gabtali Khal sluice, Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 508.8468 | 508.8468 | 505.423 | 505.423 | completed
5.2) Tankir Khal sluice, Noakhali | y | y | y | y | y | 98.14 | 100 | -1.86 | 104.2694 | 102.33 | 83.656 | 83.656 | 98% progress achieved up to 31-12-10,
5.3) Chatla Khal sluice, Noakhali | y | y | y | y | y | 98.5 | 100 | -1.5 | 102.609 | 101.0699 | 51.922 | 51.922 | 98.5% progress achieved up to 31-12-10
6) Closures (2 nos)
Total closures | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 348.5 | 348.5 | 278.8 | 278.8
6.1) closure 1 (Downstream Banshkhali), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 242 | 242 | 193.6 | 193.6 | completed
6.2) closure 2 (CBD-1), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 106.5 | 106.5 | 85.2 | 85.2 | completed
Maintenance khals
Maintenance khals (17 nos) | y | y | y | y | y | 100 | #REF! | #REF! | 133.5505 | 133.5505 | 0 | 0
7.1) Additional drainage study at upper Baggardona | - | - | - | - | - | 100 | 100 | 0 | 81.18 | 81.18 | 81.178 | 81.178 | completed
7.2) Emergency Protective work for Jaridona, Lakshmipur | - | - | - | - | - | 100 | 100 | 0 | 21.02 | 21.02 | 20.888 | 20.888 | work done
7.3) Upper Baggardona Monitoring work | y | y | y | y | y | 100 | 100 | 0 | 17.9 | 17.9 | 5.37 | 5.37 | Field Monitoring completed by IWM & draft final report submitted.
7.4) Additional improvement of secondary drainage channel (13.5 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 24.6027 | 24.6027 | - | - | 2 packages, work completed
7.4) Additional improvement of secondary drainage channel (3.5 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 6.687 | 6.687 | - | - | work completed by LCS

## Overview LGED
Table 2 - LGED | Design available (y/n) % | Design concurred (y/n) % | Estimate concurred (y/n) % | Floating tender (y/n) % | Work order given (y/n) % | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2010-12-31
Total LGED | 100 | 100 | 100 | 100 | 100 | 99.727 | 100 | -0.27301 | 2803.5371 | 2760.425 | 2760.282
7) Bridges | 100 | 100 | 100 | 100 | 100
7.1) bridges (3 no's), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 199.355 | 198.867 | 198.867 | 3 bridges (H20 loading), all completed
7.2) foot bridge (1 no), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 9.3977 | 9.402 | 9.402 | 1 foot bridge completed
8) Busstand | 100 | 100 | 100 | 100 | 100
8.1) Busstand, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 56.7459 | 56.227 | 56.227 | 1 bus stand, completed
9) Community ponds
Total community ponds (49 nos.) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 74.9549 | 70.403 | 70.403
9.1) 19 ponds, Lakshmipur (4 LCS) | y | y | y | y | y | 100 | 100 | 0 | 25.36 | 25.22 | 25.22 | all 19 completed
9.2) 15 ponds (Cont.), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 19.6449 | 15.297 | 15.297 | all 15 completed
9.3) 15 ponds (LCS), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 29.95 | 29.886 | 29.886 | all 15 completed
10) Culverts
Total box culverts (28 nos.) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 290.58 | 287 | 287
Total pipe culverts (38 nos.) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 53.6503 | 50.753 | 50.753
10.1) box culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 61.85 | 58.155 | 58.155 | all 7 completed
10.2) box culverts (21 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 228.73 | 228.845 | 228.845 | all 21 completed
10.3) pipe culverts (31 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 44.9703 | 42.133 | 42.133 | all 31 completed
10.4) pipe culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 8.68 | 8.62 | 8.62 | all 7 completed
11) Cyclone shelters
Total cyclone shelters (20 nos.) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 1223.4661 | 1212.737 | 1212.584
11.1) 7 cyclone shelters, Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 439.178 | 423.804 | 423.804 | all 7 completed
11.2) 13 cyclone shelters, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 733.037 | 732.132 | 732.132 | all 13 completed
11.3) Field raising near cyclone shelters (7 nos), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 22.3101 | 20.607 | 20.454 | all 5 completed
11.4) Field raising near cyclone shelters (13 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 23.571 | 23.544 | 23.544 | all 13 completed
11.5) Additional furniture supply to 15 cyclone shelters, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 5.37 | 5.37 | 5.37 | all furniture supplied
12) Roads
Total rural roads (55.00 km) | 100 | 100 | 100 | 100 | 100 | 99.8818 | 100 | -0.11817 | 189.4921 | 185.83 | 185.83
Total paved roads (18.70 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 662.824 | 655.134 | 655.134
12.1) paved (7 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 259.803 | 280.544 | 280.544 | 3 groups, all completed
12.2) paved (11.56 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 399.421 | 371 | 371 | All 5 groups completed.
12.3) paved (0.14 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 3.6 | 3.59 | 3.59 | spent for the revision purpose of ongoing works
12.4) 13 rural roads (22.6 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 78.16 | 76.362 | 76.362 | All 13 completed
12.5) 13 rural roads (32 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 111.3321 | 109.468 | 109.468 | all 13 completed
12.6) 8 earthen roads for cyclone shelter approach (2.7 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 7.43 | 7.28 | 7.28 | all 8 completed
13) Additional works: | 100 | 100 | 100 | 100 | 100 | 100 |  |  | 35.6411 | 34.022 | 34.022
Maintenance
Maintenance (12 items) | y | y | y | y | y | 0 | 0 | 0 | 99.2192 | 0 | 0 | for 6 items contracts have been awarded, the other 6 have to be retendered
13.1) Box culvert 1 no, Lakshmipur | y | y | y | y | y | - | 100 | - | 9.1461 | - | - | Work dropped due to time constrain.
13.2) Pipe culvert 1 no, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 2.7011 | 2.7 | 2.7 | work completed
13.3) 16 Rural roads (earthen, 6.18km, additional & CV house connecting road ), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 24.7531 | 23.535 | 23.535 | all 16 roads completed.
13.4) Additional work for bus stand on Tankir Bazar (Water supply, drain etc.) | y | y | y | y | y | 100 | 100 | 0 | 3.1959 | 2.996 | 2.996 | additional work for bus stand completed
13.5) Emergency work of Steamerghat to Chairmanghat road (HBB road construction) | y | y | y | y | y | 100 | 100 | 0 | 4.991 | 4.791 | 4.791 | emergency construction of HBB road completed. Work started in 3rd June 2010 & completed in 30th June 2010.

## Overview DPHE
Table 3 - DPHE | Design available (y/n) % | Design concurred (y/n) % | Estimate concurred (y/n) % | Floating tender (y/n) % | Work order given (y/n) % | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2010-12-31
Total DPHE | 100 | 100 | 100 | 100 | 100 | 97.0955 | 100 | -2.9045 | 743.0153 | 620.739 | 593.863
13) Deep tube wells
Total deep tube wells (600) | 100 | 100 | 100 | 100 | 100 | 99.3333 | 100 | -0.66667 | 301.8595 | 241.498 | 234.634
13.1) deep tube wells (400 nos), Lakshmipur & Noakhali | y | y | y | y | y | 99 | 100 | -1 | 200.75 | 182.398 | 176.634 | All 400 sunk. Some platform yet not done. Field progress achieved as on 30-12-10 is 99.86% . Work is going on.
13.3) deep tube wells (200 nos), Noakhali, Lakshmipur & new chars | y | y | y | y | y | 100 | 100 | 0 | 101.1095 | 59.1 | 58 | 199 sunk out of 200, one dropped due to site problem.
13.4) test deep tube wells (8 nos), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 4.96 | 4.2 | 4.2 | all sunk
14) Pond with sand filter
14.1) 10 ponds with sf, Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 4.9275 | 5.325 | 4.821 | all 10 completed.
15) Public toilets
15.1) public toilets (20 nos), Lakshmipur & Noakhali (With water facilities) | y | y | y | y | y | 100 | 100 | 0 | 137.12 | 132.197 | 130.298 | all 20 structures completed including water facilities.
16) Rainwater harvesting
16.1) rainwater harvesting (18 nos), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 3.53 | 3.07 | 3.07 | all 18 completed
17) Single pit latrines
Total single pit latrines (8500 nos) | 100 | 100 | 100 | 100 | 100 | 99.7 | 100 | -0.3 | 159.64 | 153.96 | 141.841
17.1) single pit latrines (8500 nos), Noakhali & Lakshmipur | y | y | y | y | y | 99.7 | 100 | -0.3 | 159.64 | 153.96 | 141.841 | cast:8500, installed: 8300. Field progress achieved as on 31-12-10 is 99.7% .
18) Software Training | NA | NA | NA | NA | Na | 40 | 100 | -60 | 31.15 | 10.072 | 10.072 | in training program 23 events completed out of 181 including purchase of training equipments
19) Additional works | [5 empty] | 99.5997 |  |  | 99.8283 | 70.427 | 64.927 |  |  | Tendered/Est amount (Additional) | RDPP-1 | Total |  |  | Average Progress
19.1) ponds with sf for 37 nos | y | y | y | y | y | 99.5 | 100 | -0.5 | 79.92 | 54.567 | 49.067 | out of 37 PSF 19 PSF constructed including pond re-excavation. 3 PSFproposed in MoL's ponds dropped as MoL could not excavate their all scheduled ponds. Field progress achieved is 99.5% as on 31-12-10. | PSF | 81.41 | 4.93 | 86.34 |  | 86 | 99.6064 | %
19.2) rain water harvesting 42 nos | y | y | y | y | y | 100 | 100 | 0 | 10.6676 | 8.57 | 8.57 | all 42 completed | RWHS | 10.98 | 3.53 | 14.51 | say | 13.5 | 100 | %
19.3) test tube wells 10 nos in new chars | y | y | y | y | y | 100 | 100 | 0 | 7.15 | 5.39 | 5.39 | all 10 completed | TTW | 7.15 | 4.96 | 12.11 |  | 12 | 100 | %
19.4) approach roads for public toilets (10 sites and 345m in total length) | y | y | y | y | y | 100 | 100 | 0 | 2.0907 | 1.9 | 1.9 | work for all 10 sites completed
[13 empty] | Deep Tub wells | 108.259 | 200.75 | 309.009 | say | 300 | 99.3333

## Overview MoL
Table 4 - MoL | Design available (y/n) % | Design concurred (y/n) % | Estimate concurred (y/n) % | Floating tender (y/n) % | Work order given (y/n) % | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2010-12-31
Total MoL | 100 | 100 | 100 | 100 | 100 | 89.236 | 100 | -10.764 | 516.9879 | 196.44 | 193.44
18) Construction work in cluster villages
Total construction work (128 twin houses & 8 ponds GoB) | 100 | 100 | NA | 100 | 100 | 82.1564 | 100 | -17.8436 | 251.5874 | 11.53 | 11.53
18.1Construction of Twin Houses (GoB-107 & RPA - 21, GoB budget Tk.167.76 & RPA Budget: Tk.33.26 Lakh.) | y | y | NA | y | y | 79 | 100 | -21 | 200.6944 | 11.53 | 11.53 | For GoB out of 107, 22 completed & others on going. For RPA part out of 21, 10 completed & 11 on going, achieved 97% progress as on 31-12-10.
18.2) construction of 6 ponds, Lakshmipur & Noakhali | y | y | NA | y | y | 100 | 100 | 0 | 35.503 | - | - | all completed
18.3) construction of 2 ponds, Lakshmipur & Noakhali | y | y | NA | y | y | - | 100 | - | 15.39 | - | - | work dropped due to time constrain
19) Settlement programme (RPA) | [5 empty] | 96.3162 |  |  | 236.1705
19.1)Total : excavation of CV ponds (29 cv ponds) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 178.4005 | 123.18 | 123.18
19.1.1) Excavation of 25 cv ponds, Noakhali and Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 149.1705 | 123.18 | 123.18 | all 25 ponds completed
19.1.2) Excavation of 4 cv ponds, Noakhali and Lakshmipur | y | y | y | y | y | - | 100 | - | 29.23 | - | - | work dropped due to time constrain
19.2)Total house shifting, 616 families from out side the alignment of embankment and 256 directly affected to be shifted to twin houses. | - | - | - | - | - | 90 | 100 | -10 | 87 | 58.73 | 58.73 | 528 families shifted inside from out side of embankment & 241 temporary shifted from the alignment of infrastructures.
20) Other Expenditure (Khas land distribution & LRMS Program) | - | - | - | - | - | - | - | - | 60 | 3 | 0 | Some accessories bought from the contingency fund for the land dist. & LRMS program

## Maintnance
Table 5 - MAINTENANCE | Design available (y/n) | Design concurred (y/n) | Estimate concurred (y/n) | Floating tender (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2010-12-31 |  |  | 86.4579 | 76.7168
Total LGED | 99.1071 | 99.1071 | 99.1071 | 99.1071 | 99.1071 | 99.9852 | 100 | -0.014771 | 2634.4024 | 2277.65 | 2021.03
7) Bridges | 100 | 100 | 100 | 100 | 100
7.1) bridges (3 no's), Noakhali | 0 | y | y | y | y | 100 | 100 | 0 | 100 | 196.09 | 119.32 | Work going on in all three
7.2) foot bridge (1 no), Noakhali | 0 | y | y | y | y | 100 | 0 | 100 | 100 | 9.3977 | - | w.o. issued
8) Busstand | 100 | 100 | 100 | 100 | 100
8.1) Busstand, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 56.7459 | 17.43 | 17.43 | earth filling 75% complete
9) Community ponds
Total community ponds (49 nos.) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 74.9549 | 67.07 | 67.07
9.1) 19 ponds, Lakshmipur (4 LCS) | y | y | y | y | y | 100 | 100 | 0 | 25.36 | 24.82 | 24.82 | work started for 18
9.2) 15 ponds, LGED, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 19.6449 | 15.27 | 15.27 | Work started for all 15
9.3) 15 ponds, LCS, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 29.95 | 26.98 | 26.98 | Work started for all 15
10) Culverts
Total box culverts (28 nos.) | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 100 | 100 | 0 | 335.5503 | 308.68 | 308.68
Total pipe culverts (64 nos.) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 8.68 | 8.52 | 8.52
0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -100 | 0 | 0 | 0 | work started for both
10.1) box culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 61.85 | 44.2 | 44.2 | W.O. issued
10.2) box culverts (21 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 228.73 | 227.97 | 227.97 | 5 yet to start work
10.3) pipe culverts (31 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 44.9703 | 36.51 | 36.51 | work started for 28 (21 completed), 2 yet to start, 1 tender held up.
10.4) pipe culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 8.68 | 8.52 | 8.52 | work started for all 7
10.5) pipe culverts (2 nos), Noakhali | y | y | y | y | y | 0 | 100 | -100 | - | - | - | number and locations yet to be decided
11) Cyclone shelters
Total cyclone shelters (20 nos.) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 1198.7251 | 978.06 | 970.06
11.1) 7 cyclone shelters, Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 425.7659 | 227.74 | 219.74 | work started for 5, W.O. canceled for 2. One w.o. and one estimate under process
11.2) 13 cyclone shelters, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 732 | 731.7 | 731.7 | work started for all 13
11.3) Field raising near cyclone shelters (7 nos), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 22.3101 | - | - | After major construction of cyclone shelter
11.4) Field raising near cyclone shelters (13 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 18.6492 | 18.62 | 18.62 | work started for 13 & final for 12
12) Roads
Total rural roads (54.6 km) | 100 | 100 | 100 | 100 | 100 | 99.8818 | 100 | -0.11817 | 111.3321 | 109.31 | 109.31
Total paved roads (18.7 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 740.984 | 585.21 | 413.36
12.1) paved (7 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 259.803 | 207.31 | 71.92 | work started in both groups
12.4) 13 rural roads (22.6 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 78.16 | 75.03 | 38.57 | W.O. issued
12.2) paved (11.56 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 399.421 | 299.28 | 299.28 | work started on all 5 groups
12.3) paved (0.14 km), Noakhali | n | n | n | n | n | 0 | 100 | -100 | 3.6 | 3.59 | 3.59 | will be divided over the other roads
0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -100 | 0 | 0 | 0 | work started on 12 roads
12.5) 13 rural roads (32 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 111.3321 | 109.31 | 109.31 | 13 started, 12 made final
12.6) 8 earthen roads for cyclone shelter approach (2.7 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 7.43 | 7.28 | 7.28 | 7 made final out of 8

## data status
|  | Design available | Design concurred | Estimate concurred | Floating tender | Work order given | physical progress | current planning
bwdb | sea dyke | 100 | 100 | 100 | 100 | 100 | 99.5493 | 100
| interior dyke | 100 | 100 | 100 | 100 | 100 | 99.3998 | 100
| guide dykes | 100 | 100 | 100 | 100 | 100 | 100 | 100
| re-excavations jarirdona | 100 | 100 | 100 | 100 | 100 | 100 | 100
| re-excavation bagardona | 100 | 100 | 100 | 100 | 100 | 100 | 100
| Jarirdona shortcut | 100 | 100 | 100 | 100 | 100 | 100 | 100
| Secondary drainage | 100 | 100 | 100 | 100 | 100 | 100 | 100
| Gabtali sluice | 100 | 100 | 100 | 100 | 100 | 100 | 100
| 2 sluices | 100 | 100 | 100 | 100 | 100 | 98.32 | 100
| closures | 100 | 100 | 100 | 100 | 100 | 100 | 100
lged | bridges | 100 | 100 | 100 | 100 | 100 | 100 | 100
| busstand | 100 | 100 | 100 | 100 | 100 | 100 | 100
| community ponds | 100 | 100 | 100 | 100 | 100 | 100 | 100
| box culverts | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 100 | 100
| pipe culverts | 100 | 100 | 100 | 100 | 100 | 100 | 100
| cyclone shelters | 100 | 100 | 100 | 100 | 100 | 100 | 100
| rural roads | 100 | 100 | 100 | 100 | 100 | 99.8818 | 100
| paved roads | 100 | 100 | 100 | 100 | 100 | 100 | 100
dphe | deep tube wells | 100 | 100 | 100 | 100 | 100 | 99.3333 | 100
| ponds with sand filter | 100 | 100 | 100 | 100 | 100 | 100 | 100
| public toilets | 100 | 100 | 100 | 100 | 100 | 100 | 100
| rainwater harvesting | 100 | 100 | 100 | 100 | 100 | 100 | 100
| single pit latrines | 100 | 100 | 100 | 100 | 100 | 99.7 | 100
mol | twin houses | 100 | 100 | NA | 100 | 100 | 79 | 100
| community ponds | 100 | 100 | NA | 100 | 100 | 100 | 100
| settlement programme | 100 | 100 | 100 | 100 | 100 | 100 | 100
|  |  |  | Planned Progress in percent for the month of |  |  | 2010-03-15 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01
LGED | Additional. Box culvert 1 no | [5 empty] | 2010-03-15: -; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
NOA/LAK | Add. pipe culvert 1 no | [5 empty] | 2010-03-15: 100; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
| Add. Earthen road | [5 empty] | 2010-03-15: 100; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
DPHE | Additional test tube wells10 nos | [5 empty] | 2010-03-15: 0; 2010-04-01: 100; 2010-05-01: 100; 2010-06-01: 100
| Add. PSF 37 nos | [5 empty] | 2010-03-15: 0; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
| Add RWHS | [5 empty] | 2010-03-15: 0; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
| Software Training | [5 empty] | 2010-03-15: 20; 2010-04-01: 55; 2010-05-01: 85; 2010-06-01: 100
BWDB | Re-excavation of Banshkhali khal | [5 empty] | 2010-03-15: 45; 2010-04-01: 65; 2010-05-01: 85; 2010-06-01: 100
NOA/LAK | Secondary drainage khal | [5 empty] | 2010-03-15: 0; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
NOA | Baggardona Monitoring | [5 empty] | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100
LAK | Protective work | [5 empty] | 0 10: 100
NOA | Closure-01 | [5 empty] | 0 10: 55; 30 20: 70; 80 30: 90; 100 40: 100
NOA | Closure-02 | [5 empty] | 0 10: 55; 30 20: 70; 80 30: 90; 100 40: 100

## hulp sheet
Nos
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.1) box culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 5 | 5 | 5 | 5 | 5
10.2) box culverts (21 nos), Noakhali | y | y | y | y | y | 100 | 21 | 21 | 21 | 21 | 21
10.3) pipe culverts (31 nos), Noakhali | y | y | y | y | y | 100 | 31 | 31 | 31 | 31 | 31
10.4) pipe culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 7 | 7 | 7 | 7 | 7
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.4) 13 rural roads (22.6 km), Lakshmipur | y | y | y | y | y | 100 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5
12.5) 13 rural roads (32 km), Noakhali | y | y | y | y | y | 100 | 32 | 32 | 32 | 32 | 32
12.6) 8 earthen roads for cyclone shelter approach (2.7 km), Noakhali | y | y | y | y | y | 100 | 2.7 | 2.7 | 2.7 | 2.7 | 2.7
12.1) paved (7 km), Lakshmipur | y | y | y | y | y | 100 | 7 | 7 | 7 | 7 | 7
12.2) paved (11.56 km), Noakhali | y | y | y | y | y | 100 | 11.56 | 11.56 | 11.56 | 11.56 | 11.56
12.3) paved (0.14 km), Noakhali | y | y | y | y | y | 100 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14
9.1) 19 ponds, Lakshmipur (4 LCS) | y | y | y | y | y | 100 | 19 | 19 | 19 | 19 | 19
9.2) 15 ponds (Cont.), Noakhali | y | y | y | y | y | 100 | 15 | 15 | 15 | 15 | 15
9.3) 15 ponds (LCS), Noakhali | y | y | y | y | y | 100 | 15 | 15 | 15 | 15 | 15
11.1) 7 cyclone shelters, Lakshmipur | y | y | y | y | y | 100 | 7 | 7 | 7 | 7 | 7
11.2) 13 cyclone shelters, Noakhali | y | y | y | y | y | 100 | 13 | 13 | 13 | 13 | 13
13.1) deep tube wells (400 nos), Lakshmipur & Noakhali | y | y | y | y | y | 99 | 400 | 400 | 400 | 400 | 400
13.3) deep tube wells (200 nos), Noakhali, Lakshmipur & new chars | y | y | y | y | y | 100 | 200 | 200 | 200 | 200 | 200
14.1) 10 ponds with sf, Lakshmipur | y | y | y | y | y | 100 | 10 | 10 | 10 | 10 | 10
16.1) rainwater harvesting (18 nos), Lakshmipur | y | y | y | y | y | 100 | 20 | 20 | 20 | 20 | 20
17.1) single pit latrines (8500 nos), Noakhali & Lakshmipur | y | y | y | y | y | 99.7 | 6 | 6 | 6 | 6 | 6
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1) Re-excavation Jarirdona, 0km-2.625km (2.625 km), Lakshmipur | y | y | y | y | y | 100 | 2.625 | 2.625 | 2.625 | 2.625 | 2.625
3.2) Re-excavation Jarirdona, 2.625km-3.535km (0.91 km), Lakshmipur | y | y | y | y | y | 100 | 0.91 | 0.91 | 0.91 | 0.91 | 0.91
3.3) Re-excavation Baggardona, 7.035km-13.935km (6.9 km), Noakhali | y | y | y | y | y | 100 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9
3.4) Re-excavation Baggardona, 13.935km-17.035km (3.1 km), Lakshmipur | y | y | y | y | y | 100 | 3.1 | 3.1 | 3.1 | 3.1 | 3.1
1.1) Sea dyke, 0.63km-3.365km (2.5 km), Lakshmipur | y | y | y | y | y | 100 | 2.735 | 2.735 | 2.735 | 2.735 | 2.735
1.2) Sea dyke, 3.365km-5.085km (1.72 km), Lakshmipur | y | y | y | y | y | 100 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72
1.3) Sea dyke, 5.085km-8.585km (3.5 km), Noakhali | y | y | y | y | y | 100 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
1.4) Sea dyke, 8.585km-11.5km (2.915 km), Noakhali | y | y | y | y | y | 98.3194 | 2.915 | 2.915 | 2.915 | 2.915 | 2.915
1.5) Interior dyke, 11.5km-19.5km (8 km), Noakhali | y | y | y | y | y | 99.3998 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
4.1) Jarirdona shortcut, 3.535km-3.925km (0.39 km), Lakshmipur | y | y | y | y | y | 100 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39
4.2) Jarirdona shortcut, 3.925km-6.035km (2.11 km), Lakshmipur | y | y | y | y | y | 100 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11
4.3) Jarirdona shortcut, 6.035km-7.035km (1 km), Noakhali | y | y | y | y | y | 100 | 1 | 1 | 1 | 1 | 1
4.4) drainage channel Gabtali khal (6.155 km), Lakshmipur | y | y | y | y | y | 100
4.5) improvement of secondary drainage (6 km), Lakshmipur | y | y | y | y | y | 100 | 6 | 6 | 6 | 6 | 6
4.6) improvement secondary drainage (15 km), Noakhali | y | y | y | y | y | 100 | 15 | 15 | 15 | 15 | 15
15.1) public toilets (20 nos), Lakshmipur & Noakhali (With water facilities) | y | y | y | y | y | 100 | 20 | 20 | 20 | 20 | 20
2.1) Guide dyke cum rural road, 7.035km-10.00km (2.965 km), Noakhali | y | y | y | y | y | 100 | 2.965 | 2.965 | 2.965 | 2.965 | 2.965
19.1.1) Excavation of 25 cv ponds, Noakhali and Lakshmipur | y | y | y | y | y | 100 | 25 | 25 | 25 | 25 | 25
Excavation of 10 cv ponds (actually 4 needed), Noakhali & Lakshmipur | y | y | y | y | y | - | 4 | 4 | 4 | 4 | 4
Additional box culvert, 1 no, Lakshmipur | [6 empty] | 1 | no
Additional pipe culvert, 1 no, Noakhali | [6 empty] | 1 | no
Additional earthen road (6.17km), Noakhali | [6 empty] | 6.18 | km