Annex-2

FINDINGS OF JOINT VERIFICATION TEAM TO ESTABLISH PROGRESS OF INFRASTRUCTURE ACTIVITIES IN CDSP III ON 31st DECEMBER 2010

- Composition of the team

DPHE: Md. Rowshan Alam, Executive Engineer, Noakhali; Md. Rafiqul Islam, Sub-Assistant Engineer, Noakhali.

On behalf of Ministry of Land: Md. Rafiqul Islam, SAE, DPHE.

BWDB: Md. Saifullah, Sub-Divisional Engineer, Noakhali O&M Division; Md. Zahir Uddin, Sectional Officer and Md. Habibur Rahman, Sectional Officer..

Technical Assistance team: Koen de Wilde, Chief Technical Adviser; Zainal Abedin, Team Leader; Mihir Kumar Chakraborty, Quality Control Engineer; Sankar Chandra Saha, Project Engineer; Maksudur Rahman, Project Area Coordinator.

- Date and method of verification

The verification of works under Financial Assistance of the Government of the Netherlands was carried out on Sunday 2nd January 2011, the first working day after 31st December 2010. The joint team visited all concerned Ministry of Land and BWDB works, and a random sample of DPHE works. For the other implementing agencies of CDSP III (LGED, DAE, and Forest Department) there were no more activities going on.

- Findings for Ministry of Land

Work was ongoing on 11 twin-houses in two clustered villages. The incomplete part was as follows:

  - Labour – and fitting costs with a value estimated at 	Tk. 100,000

  - Works will be completed in seven days, on 9th January.

- Findings for Department of Public Health Engineering (DPHE)

Work was ongoing on the filter of 18 Ponds with Sandfilter (PSF), platforms of  eight tube wells and installation of around 200 pit latrines in clustered villages. The incomplete part was as follows:

  - Fitting of 18 covers for PSF filters, estimated at 		Tk.   36,000

  - Completion of 8 tube well platforms, estimated at 		Tk.   28,000

  - Installation of 200 pit latrines, estimated at 			Tk.   50,000

  - Total DPHE 							Tk. 114,000

  - All works will be completed within one week, on 9th January

- Findings for Bangladesh Water Development Board (BWDB)

Work was going on two sections of the embankment and two sluices (Chatla- and Tankir sluice). The incomplete part was as follows:

  - Embankment group 6: dressing/turfing estimated at 	Tk. 300,000

  - Embankment group 8: earthwork, estimated at 		Tk.   50,000

  - Embankment group 8: dressing/turfing estimated at 	Tk. 200,000

  - Tankir sluice: dressing/turfing approach road est. at 	Tk.   40,000

  - Tankir sluice: earthwork approach road, estimated at 	Tk. 150,000

  - Chatla sluice: dressing/turfing approach road est. at 	Tk.   40,000

  - Chatla sluice: earthwork approach road estimated at 	Tk.   50,000

  - Chatla sluice: sand/earth bags estimated at 			Tk.   50,000

  - Total BWDB							Tk. 880,000

  - All works will be completed within 10 days, on 12th January.

- The total estimated value of the incomplete parts of ongoing works is:

- Ministry of Land    	Tk.    100,000

- DPHE 			Tk.    114,000

- BWDB 			Tk.    880,000

- Grand total 		Tk. 1,094,000

For Department of Public Health Engineering:

Sgd.

Md. Rowshan Alam, Executive Engineer

For and on behalf of Ministry of Land:

Sgd.

Md. Rafiqul Islam, Sub-Assistant Engineer, DPHE

For Bangladesh Water Development Board:

Sgd.

Md. Saifullah, Sub-Divisional Engineer, O&M Division Noaskhali

For Technical Assistance team:

Sgd.

Koen de Wilde, Chief Technical Adviser.

Noakhali, 3rd January, 2011.