Table of Contents							          Page No.

TABLE OF CONTENTS	1

List of abbreviation	2

# Chapter 1 INTRODUCTION	4

1.1. 	Background	4

1.2. 	Approaches and strategies	4

1.3. 	Linkages of CDSP III to other development efforts	4

1.4	Project Proformas of implementing agencies	5

# Chapter 2 OBJECTIVES AND SCOPE OF THE PROJECT	6

2.1. 	Development objective and project purpose	6

2.2. 	Components and activities	6

2.3. 	Target groups	6

2.4.	Target areas	6

## Chapter 3  ACTIVITIES PER COMPONENT	7

3.1. 	Introduction	7

3.2. 	Institutional development	7

3.3.	Studies, knowledge management and dissemination	12

3.4.   	Intervention at field level in particular in Boyer Char	14

# Chapter 4  PROJECT ORGANIZATION	27

## 4.1.	Introduction	27

## 4.2.	The parties involved and their responsibilities	27

4.3.	Formal coordination mechanisms	28

4.4.	Monitoring, reporting and review	28

# Chapter 5  BUDGET AND TIME FRAME	29

5.1.	Introduction	29

5.2. 	Contribution of the Government of Bangladesh	29

5.3. 	Contribution of the Government of the Netherlands	29

  - Money flows and financial reporting	30

  - Time frame	30

# Chapter 6  RISKS AND ASSUMPTIONS	31

Appendices :

Annex-1 :	Map of Project areas

Annex-2	:	Report Joint Verification Team

Annex-3	:	Overview progress infrastructural works

Annex-4	:	Training activities in reporting period

Annex-5	:	List of members Technical Assistance Team

Annex-6	:	List of Project Management Committee

Annex-7	:	Item wise FA budget and Re-imbursement

Annex-8	:	Technical Assistance Budget

LIST OF ABBREVIATION

AC (L)	:	Assistant Commissioner (Land)

AEO	:	Assistant Extension Officer

AGM	:	Annual General Meeting

BARD	:	Bangladesh Academy for Rural Development

BRAC	:	Bangladesh Rural Advancement Committee

BRRI	:	Bangladesh Rice Research Institute

BWDB	:	Bangladesh Water Development Board

CBD	:	Char Baggar Dona

CBT	:	Char Bhatir Tek

CDS	:	Coastal Development Strategy

CDSP	:	Char Development and Settlement Project

CEGIS	:	Centre for Environmental and Geographic Information Services

CM	:	Char Majid

DAE	:	Department of Agricultural Extension

DC	:	Deputy Commissioner

DDCC	:	District Development Coordination Committee

DOC	:	Department of Cooperatives

DOF	:	Department of Forest

DPHE	:	Department of Public Health Engineering

DPP	:	Development Project Proforma

DTW	:	Deep Tube Well

ECNEC	:	Executive Committee of National Economic Council

EDP	:	Estuary Development Programme

EIRR	:	Economic Internal Rate of Return

EKN	:	Embassy of the Kingdom of the Netherlands

FF	:	Farmers Forum

FIRR	:	Financial Internal Rate of Return

HH	:	Household

HYV	:	High Yielding Variety

ICRD	:	Integrated Coastal Resource Database

ICZM	:	Integrated Coastal Zone Management

IPSWAM	:	Integrated Planning for Sustainable Water Management

IWM	:	Institute of Water Modeling

LCS	:	Landless Contracting Society

LGED	:	Local Government Engineering Department

LGI	:	Local Government Institution

LRMS		Land Records Management System

MC	:	Management Committee

MIDPCR	:	Market Infrastructure Development Project in Char Land Regions

MoL	:	Ministry of Land

NGO	:	Non Governmental Organization

NSC	:	National Steering Committee

O&M	:	Operation and Maintenance

PDZ	:	Productivity Zone

PMC	:	Project Management Committee

PMU-ESPP	:	Project Management Unit-Estuary Studies and Pilot Project

PP	:	Project Proforma

RDPP	:	Revised Development Project Proforma

SRDI	:	Soil Research Development Institute

SFG	:	Social Forestry Group

UCO	:	Upazila Cooperative Officer

UNO	:	Upazila Nirbahi Officer

UP	:	Union Parishad

XEN	:	Executive Engineer

WARPO	:	Water Resource Planning Organisation

WMA	:	Water Management Association

WMF	:	Water Management Federation

WMG	:	Water Management Group

WMO	:	Water Management Organization

Chapter 1 INTRODUCTION

1.1. Background

This Progress Report covers the last six months (July to December 2010) of the  63 months project period of CDSP III (October 2005 to December 2010). The main reference of this Progress Report is the approved Annual Work Plan 2010.

The current report has the same structure as the AWP (and as all other AWPs and Progress Reports).

1.2. Approaches and strategies

The same approaches and strategies have been applied as throughout the project period. The essential elements are given below:

Poverty alleviation – As was reported in the previous Progress Report, CDSP had a significant impact if it comes to poverty alleviation. Two studies were carried out in the context of the appraisal of CDSP IV. The main findings of these studies are reflected in Technical Report no. 7, published in December. In all CDSP areas (CDSP I, II and III combined), a substantial reduction in poverty has taken place, with the proportion of very poor households and households with chronic food shortages declining from 90% to between 39% and 56%. Despite the overall reduction, there remains a significant proportion (10% to 16%) of households facing a chronic food shortage. Although poverty levels in the CDSP III area have become lower, a high level of poverty remains because the project is not yet completed and the full benefits of development have yet to be realized. In CDSP I and II areas, many of the very poor are those that migrated to these areas since the CDSP I and II projects were completed. They did not benefit from the land settlement programme.

Integration – The involvement of six agencies, covering several sectors in a coordinated manner, continued, as was also shown in the way the DPPs for CDSP IV were prepared.

Participation –  The work with and support of  Water Management Groups and Social Forestry Groups in Boyer Char continued in the reporting period. Staff of the BWDB fully took over the support of WMOs in CDSP I and II areas.

Bridging function - The role CDSP III played in the formulation of CDSP IV (feasibility studies, support for a series of preparatory missions, comments on the mission reports) demonstrates the bridging function the project fulfilled.

1.3. Linkages of CDSP III to other development efforts

Relations with other projects were during these six months limited to

- Regional Fisheries and Livestock Component of the Danida Agricultural Sector Program phase III (RFLDC), on the use of ponds in Boyer Char for aquaculture and the formation of community based organizations for that purpose. In this respect, RFLDC provided block grants to three additional Water Management Groups in Boyer Char. Moreover, the Water Management Association of Bamni (CDSP II) was included as a RFLDC community based organization.

- Market Infrastructure Development Project in Char Land Regions  (MIDPCR) on pavement of a road, connecting markets

- Support to Agricultural Research for Climate Change Adaptation in Bangladesh (SARCCAB) of IRRI, for organizing a workshop in Boyer Char.

1.4. Project Proformas of implementing agencies

In the reporting period no activities were undertaken with regard to DPPs for CDSP III. However, for the preparation of the DPPs for CDSP IV, all agencies and members of the Technical Assistance team were fully involved.

Chapter 2 OBJECTIVES AND SCOPE OF THE PROJECT

2.1. Development objective and project purpose

The project objectives stayed the same. The improvement of the economic situation and the living conditions of the population in the coastal areas of south-eastern Bangladesh, with special reference to the poorest segments of the population, continued to be the long term development objective.

The three project purposes remained:

- promotion of an institutional environment that sustains CDSP type of interventions

- accumulation and dissemination of knowledge on coastal development

- direct improvement of the economic and social situation of people in coastal chars.

2.2. Components and activities

Also in the reporting period, the project had three components:

- institutional development

- studies, knowledge management and dissemination

- concrete interventions at field level, directly contributing to the improvement of livelihoods of households in the chars.

These three components can be found back in the next chapter: paragraph 3.2. is on institutional aspects, 3.3. on knowledge management and 3.4. on field level interventions.

2.3. Target groups

The target groups of the project can be found at different levels in society and the administrative system, from grass roots to the national level. The most important continued to be the settlers in Boyer Char. During the reporting period attention was also given to other groups (among them staff of the implementing agencies) through the internalization - and dissemination activities.

2.4. Target areas

The main target areas for the concrete interventions in the field were Boyer Char and the upstream parts of the  Baggar Dona river catchment area. Some activities were geared towards the CDSP I and II areas. The three completed feasibility studies were on Char Nangulia, Noler Char, Caring Char, Ziar Char and  Urir Char. These areas are included in CDSP IV.

A map of CDSP project areas and a map of Boyer Char can be found in Annex 1.

Chapter 3  ACTIVITIES PER COMPONENT

3.1. Introduction

This chapter follows the three project components: institutional development (3.2); studies, knowledge management and dissemination (3.3.) and activities at field level (3.4). Under each heading progress in the July to December 2010 period is reported on.

3.2. Institutional development

3.2.1. Contribution to ICZM

No specific activities were undertaken in this respect.

3.2.2	Strengthening of implementing agencies, including internalization of CDSP concepts

3.2.2	Strengthening of implementing agencies, including internalisation of CDSP concepts

- Internalisation

As reported before, the ultimate aim of internalisation activities os to improve the capability of participating agencies to prepare and implement future char development programmes. Internalisation in the context of CDSP III has been defined as incorporation of CDSP experiences into the strategies, procedures and organisational culture of those agencies. Internalisation activities have been progressing during the reporting period. Major accomplishments during July-December 2010 period were:

- Internalisation Committee meeting of two agencies, Ministry of Land and Forest Department were held in this period. Since October 2008, the total number of internalisation committee meetings held by the six implementing agencies are: four meetings each in BWDB, DPHE, LGED, DAE, three in MoL and five in Forest Department.

- During this period training modules have been handed over to Forest Department for inserting the lessons of previous CDSP phases in the module of suggested courses and organizing training courses. The MoL internalisation-training module has been published, sufficient copies made and supplied. With this, the internalization training module is available for all agencies.

- During the reporting period, BWDB presented the information on CDSP experience in one course organized in 'Baradi' training centre located at Khustia.

- A one-day workshop on “Internalising CDSP Experiences in DAE” was organized on 30 November 2010 in the conference room of the Director General DAE. The workshop was attended by 30 top- and senior level officials of DAE. The aim of the workshop was to keep top- and senior level officials informed about the accomplishments of DAE in internalising CDSP experiences.

- Preparations to organizing a “National workshop on internalisation of CDSP experience for capacity building of agencies” have been completed. The workshop has been  deferred until early 2011.

-    Strengthening of PMU-ESPP, BWDB

No specific activities were undertaken in the reporting period. The planned course for staff of the PMU-ESPP was not implemente4d due to pre-occupation with other matters of the staff concerned.

    - Participatory water management; monitoring of and support to

WMOs in CDSP-I and II areas, and in Boyer Char; support for the BWDB Water Management Directorate.

- 	WMOs in CDSP-I and II areas

- Overview

Assistant Extension Officer (AEO) and concerned Extension Overseers (XO) have been working to support the established WMOs in CDSP-I and II areas.

Polder 59/3C/Bamni: AEO and XO facilitated the activities of WMOs (11 WMGs, three WMAs and one WMF) in Bamni area. No new members enrolled in the WMOs during this period. A total of 19 meetings were held by three WMAs during July-December 2010, with an average attendance rate of 59%.

Issues discussed in those meetings were as follows:

- New 15 vent regulator and embankment eroded near Charlengta

- Erosion in the old sluice area (15 vent)

- Re-excavation of drainage canals in FY 2010-11

- Refresher training for the WMAs

- Involvement of WMO with RFLDC

- Annual General Meeting (AGM), audit, loan distribution among WMA members.

Mainland Noakhali excluding Bamni: AEO and concerned XOs have been continuing support to 12 WMGs and one WMA with a total of 388 members (60% are male and 40% female)

-	Average attendance in CM, CBD-I and CBD-II (total of 17 meetings) was 61% for male and 39% for female. Numbers of meetings are almost same compared to previous period.

-	Average attendance in Char Bhatir Tek (CBT) and Polder 59/3B (for a total of 37 meetings) was 80%, with 61% for male and 39 % for female. Numbers of meetings were less compared to the previous period

-	Pending AGM of these WMOs were completed during the reporting period

Some of the activities undertaken in the reporting period were:

-WMO Nabagram catchment area suffered a lot from drainage congestion in the  monsoon period. The president and secretary made frequent contact with the XEN, TA Team and other concerned to solve the problem.

-AGM of Nobagram WMG was held on 19th December at CBT site office where staff of BWDB and TA-team were present. The meeting discussed the financial aspects, maintenance priorities, drainage problems and other general matters in their locality.

-A WMG representative attended a workshop held at LGED conference room on 22nd November where they raised the concern of water management problems in the Bamni and CBT area. The workshop was organized by IWM and was presided by the ADG, O & M-1, BWDB, Dhaka

South Hatiya: a total of 20 WMGs, three WMAs and one WMF exist, with a total of 701 members. A total of 17 meetings, including two special meetings, were held by the three WMAs in the reporting period, which is more than the previous period. Average attendance rate in those meetings was 75% (for male 61% and 39% for female). Subjects discussed in those meetings were among others: filling hole in front of Burirdona sluice, filling hole near bridges,  future of O & M, khal re-excavation, operation of sluice and savings collection and fund raising. In addition, RFLDC activities were reviewed with WMO Burirdona in Hatiya.

- 	Training (all CDSP I and II areas)

Eight refresher training events were organized in CDSP-I and II areas in the reporting period (details can be found in annex 4).

-	 Maintenance  (all CDSP I and II areas)

WMOs reviewed the maintenance work implemented by them during the last reporting period with CDSP III funds through BWDB, LGED, and DPHE.

-   	Capacity building (all CDSP I and II areas)

Three weekly progress review meetings were held in the reporting period at the conference room of CDSP III with the Extension Overseer and AEO, BWDB and Project Area Coordinator, Boyer Char. The meeting specially reviewed the WMO related activities, planning for future O & M in CDSP I, II and III areas. Other issues discussed included: training/refreshers, holding regular meetings, poster/leaflet distribution on water management, monitoring WMO fund use. installation of LGED supplied pipes in Boye Char, handing over TA responsibilities to the BWDB concerned was also reviewed in those meeting.

- .

-   Staffing and exit of TA support

- Four BWDB Extension Overseers have been working for Polder 59/3C-Bamni, Polder 59/3B including Bhatir Tek, Char Majid, Char Baggar Dona I and II areas after withdrawal of the TA support from the CDSP I and II areas in July 2009.

- An Extension Overseer is yet to be posted for Hatiya.

- One Assistant Extension Officer (AEO) of BWDB continued supervising the activities of the Extension Overseers.

-  	WMOs in Boyer Char

-     Overview

All ten WMGs and one WMA met regularly in the reporting period in Boyer Char. A total of 20 new members enrolled into five WMGs and 21 members withdrawn or dropped their membership from six WMGs in the reporting period. The reason of withdrawing/drooping membership was long absence from the group activities. Of the total of 368 members, 192 are male and 176 are female. The ten WMGs held a total of 60 meetings in the last six months, one in each month. Average attendance rate in those meetings was about 62% for men and 67% for women.

- Issues and activities

Major subjects discussed in those meetings were among others: drainage congestion due to non-starting of under construction Chatla and Tankir sluice, shifting households from outside to inside the embankment, AGM of 10 WMGs, use and management of the Local Information Center, Joint Management Committee (JMC) for Gabtoli sluice, land settlement, contribution for a deep tube near CDSP-III site office, use of CDSP site office by WMG-Chatla  and audit of all WMGs.  The WMO also reviewed status of remaining infrastructure works and settlement works to be completed within December 2010 or thereafter.

Major activities performed during the reporting period are mentioned below:

- Annual General Meeting of 10 WMGs were held during July-August 2010. AGMs were facilitated by the TA team and concerned BWDB field officials.

- Audit of 10 WMGs were completed by the Department of Cooperative during November-December 2010. The audit was supported by BWDB- and TA-staff.

- A special meeting of WMA was held on 22nd November at Mainuddin bazar site office. The meeting reviewed the findings of the study tour to West Bengal,  where two representatives of the WMA of Boyer Char participated. Among others, draft maintenance plan for Boyer Char, completion the re-excavation work of 19 secondary canals, installation of drainage pipes in different locations supplied by LGED, residual work of land settlement in 2011 under CDSP-IV,  foreshore plantation and O & M of Gabtoli sluice were the major issues of discussion.

- Two LCSs worked during the reporting period and re-excavated 3.5 km secondary canal.

- Sluice operators and WMGs leaders worked hard together with the Mechanical workshop of BWDB for maintenance of seven lift and seven flap gates in Gabtoli sluice during the monsoon.

- WMGs concerned supported and facilitated the resettlement works of households from outside the embankment to inside the polder. In this regard, distribution of shifting costs among affected households, allocation CV plots among the concerned households and motivating them for shifting, were the main supporting services.

- WMO members participated to training/refreshers on water management, gender, social forestry and accounts management, of which all details are shown in annex 4.

- A training was imparted to the operators and WMG leaders of three sluices on operation and maintenance of sluice (see details in annex 4)

- Local people excavated three-link drainage canals by their own initiative with the support of concerned WMG: one in Naidag, one in Yunuspur and another in between Mollagram and Rahmatpur during the monsoon. This local initiative resulted in the increase of aman rice production.

- A small loan operation among the members of 10 WMGs in Boyerchar continued. Outstanding loans total Tk 6 lakh.

- WMG leaders supported the distribution of pending single pit latrines among the re-settled households in the MoL cluster villages.

- WMGs continued fish culture in the community ponds under their respective jurisdictions.

3.2.4	Strengthening links between communities, local government institutions and    implementing agencies in CDSP I and II areas and in Boyer Char

-	CDSP I and II areas

No specific activities are to be reported.

- Boyer Char

The draft Maintenance Plans with regard to works of BWDB, LGED, DPHE and the Ministry of land were all prepared by the Water Management Organisations of Boyer Char. These Maintenance Plans form the kingpin of the relations in future between the communities and the implementing agencies. Although there are no elected Union Parishad officials in the area (see 4.2.9), three out of the six appointed UP members are also WMG-member, which means there is a link to local government. In the extension period (January and February 2011), the draft pan will be discussed with the agencies, priorities will be made and annual plans will be formulated.

Project staff facilitated in the handing over of seven cyclone shelters to the school- or Madrasha management committee. Four more school management committees were formed in the reporting period. Earlier, funds from the TA-budget were provided to assist in the registration of erstwhile community schools with the Government.

    - Greater involvement of District Level in the project

- District Development Coordination Committee (DDCC)

The monthly DDCC meetings were regularly attended by officers of  the implementing agencies and by members of the Technical Assistance team. Bilateral meetings with the Deputy Commissioner of Noakhali were mainly on the land settlement programme and on the preparations for CDSP IV.

# - District Information Centre, Lakshmipur/ Coastal Development        Information Centre (CDIC)

No specific activities were undertaken. The centre, located in the office of the District Administration in Lakshmipur, is run by CODEC.

3.2.6. Upgrading and improving functioning of Project Management Committee

No specific activities were planned, nor undertaken to upgrade and improve the functioning of the PMC.

3.2.7. Preparation of funding arrangements for char development interventions after 2010

Support was provided by members of the Technical Assistance team in preparation of the DPPs for CDSP IV. A range of activities were undertaken of a logistical nature, following an IFAD mission by the CTA, in order to facilitate the transition from CDSP III to CDSP IV.

3.3. Studies, knowledge management and dissemination

3.3.1. Drainage study upstream Baggar Dona

- Drainage study

No further activities wre undertaken. The study has been completed.

-    Monitoring

On the basis of a recommendation of the report of the Additional Drainage Study, BWDB assigned the Institute for Water Modeling to undertake a monitoring programme  in the newly established outfall of the Baggar Dona and the upper Baggar Dona tiver. The outfall started functioning from 25th May 2009. IWM started monitoring salinity intrusion, tidal penetration, sedimentation in the channel, water flow, sediment concentration and drainage condition of the upper Baggardona catchments since 22nd February 2010 for about one year under a contract with BWDB, funded out of Financial Assistance funds. IWM held a workshop on the Inception Report of the monitoring program on 6th Nov 2010 and submitted Draft Final Report in the month of December 2010.

3.3.2	Feasibility Studies for char development project in future

- Overall study

No activity in the reporting period.

-    Feasibility studies.

No activities in the reporting period. The three feasibility studies formed th basis for CDSP IV.

    - Knowledge management: Improving flow of information to communities in Boyer Char; linking project data base with Integrated Coastal Resources Data Base of ICZM; dissemination of CDSP achievement on a wider scale

- Dissemination

Activities in the reporting period related to dissemination of project information were:

- The teacher’s and students' guidebook on climate change was already published and distributed among the staff and students of 18 selected schools in the Noakhali region. In their response to the material, teachers indicated that more information for them is needed to enable them to properly explain the contents of the book to the students. Following this suggestion, CDSP organized a three-day ‘Climate change course for teachers’. Fifty teachers that included climate change in their lessons attended the course in two batches. A module of the course was developed, following the format of the IUCN publications for the students and teachers. Information given in the original publications, was rephrased and structured in an easy-to-present format. The course and the materials were well received by the participants. The course evaluation report revealed that participants learned a lot of information and felt more competent to give the lessons with command.

- The video documentary on CDSP III, titled “Rebuilding Livelihood”, was circulated among the concerned parties.

- A short article “LGED’s CDSP Improves Livelihood of Coastal people” was published in the July - September issue of the Quarterly LGED Newsletter.

- A journalist of the Dutch magazine “Internationale Samenwerking” (meaning International Cooperation), visited the project area in October.

- In December, a photographer on an IFAD assignment made photos of different interventions in Boyer Char and also visited the new chars, to be included in CDSP IV, which will be financially supported by IFAD.

- Talk show on CDSP III was broadcasted on two national TV channels (BTV and Boishaki)

- The dummy copy of the book “Moving Coastlines – emergence and use of land in the Ganges-Brahmaputra Meghna Estuary” as mentioned in the last Progress Report, was produced and checked. Indexing work is now going on. The publisher, University Press Ltd. expects publication within January 2011.

- A half-day Project Ending Workshop of CDSP-III was held on 28th December in Spectra Convention Centre. State-Minister for the Ministry of Water Resources attended as the Chief Guest. First Secretary (Water) of the Embassy of the Kingdom of the Netherlands, high level officials of stakeholder ministries, agencies, top- and senior level officials of implementing agencies were present in workshop. Besides, representative from relevant organizations, institutions, NGO, projects, research institutions and WMOs were among the audience. A total of 80 persons participated to the workshop. The core of the workshop was the presentation of Chief Planning, BWDB, on the achievements during the 63 months of CDSP III.

- Information flow to and from communities in the Boyer Char

Besides the many day to day contacts between project staff of government agencies as well as the TA-team, the activities with regard the Local Information Centre and the information flow to especially women are worth mentioning.

- Local Information Centres

No new activities in the reporting period.

-     Linking up of database

No further activities were undertaken in the reporting period related to linking up of database.

    - Increasing knowledge about impact of past interventions in CDSP-I and CDSP-II area: monitoring land retention in CDSP I and CDSP-II areas; monitoring soil salinity; monitoring HYV adoption

- Land settlement

Technical Report no. 5  on land monitoring in CDSP-I and II areas, based on a survey done in the second half of 2009, was published in December.

-      Soil salinity

As in the previous reporting period, contrary to the plan, no activities were undertaken.

-      Adoption of modern agricultural technologies

No activities were done in the reporting period. Results of monitoring were published as a part of Technical Report no. 6.

3.4. Interventions at field level in particular in Boyer Char

The agreement between the Governments of Bangladesh and the Netherlands stipulate that activities after 31st December 2010 are not eligible for reimbursement under Financial Assistance. In order to establish the exact status on that date, a Joint Verification team was fielded on 2nd January 2011, the first working day after 31st December. The work of that team focused on the incomplete parts of ongoing infrastructural activities.  The report of the team is included as Annex. 2.

3.4.1. Ministry of Land

-  Land Settlement in CDSP-l and II areas.

In total, 6,415 not completed land settlement cases of CDSP-II had to be dealt with under CDSP III. Of these, 5,898 cases were disposed of by making over the khatians to the concerned households during the CDSP-III period. However, despite intensive activities to dispose of all the pending cases, 517 cases (including 155 of Mirsharai Upazila of Chittagong District) were pending as on 31st December 2009. The reasons for this unfortunate situation have been listed in the previous Progress Reports.

In March 2010 the decision was by the District Monitoring Committee that the pending cases will now be dealt with and disposed of by the respective District Administrations through the normal process of Agricultural Khas Land Management & Settlement Policy, so outside CDSP’s procedural framework. Consequently, no activities were undertaken in this respect in the reporting period.

- Land Settlement under CDSP-III (Boyer Char)

Progress of land settlement process in Boyer Char during and at the end of the reporting period was as follows:

| Nature of Work | Progress as on 30/06/2010 | Progress as on 31/12/2010 | Result in rep. period |
| --- | --- | --- | --- |
| Target as per Plot to Plot Survey | 9500 |  |  |
| Approval of sheet Maps of PTPS | 32 | 32 | 0 |
| Consolidation of FTPS Works | 9500 | 9500 | 0 |
| Hearing of Landless Families | 8700 | 8950 | 250 |
| Landless families selected | 7801 | 8945 | 1144 |
| Settlement Case initiated | 7265 | 8142 | 877 |
| Jamabondi cases prepared | 7265 | 8142 | 877 |
| Jamabondi cases approved by Upazila Committee | 7265 | 8142 | 877 |
| Sent to District Committee for approval | 7265 | 7755 | 490 |
| Approval of the list of the landless by District Committee | 7265 | 7755 | 490 |
| Case-to-case approval by the DC & Cases sent back to AC (L) office | 6375 | 7715 | 1340 |
| AC (L)’s order for Salami realization and execution of Kabuliyat at Tahsil. | 6374 | 7706 | 1332 |
| Kabuliyats Executed by Landless | 4489 | 7397 | 2908 |
| Registration of Kabuliyats | 4003 | 7305 | 3302 |
| Khatian Preparation | 4003 | 7305 | 2182 |
| Realization of khatian fees & opening holding for landless | 3882 | 7305 | 2303 |
| Khatian distribution | 3882 | 7305 | 3423 |

From the above statement it will appear that, the progress of the settlement cases in various stages was substantially during the period under review. Twenty hearings were conducted and an additional 1,144 landless families had been selected for settlement of khas land. Thereby, the total number of selected household rose to 8,945. The number of households that received the official title of the allotted land (khatian) increased with 1,118 to 3,423. Total disposal 31st December 2010 stands at 7,305

It may be mentioned here that following an armed confrontation of the possessors of the khas lands with the police at Tankir Bazar areas; the settlement process as well as rehabilitation activities were seriously disrupted. The confusion among the settlers grew up over the requirement of the land for foreshore plantation by the Forest Department, an issue that had been brought up by the Department very late in the project period. Many households abstained from appearing at the hearing sessions, asserting their intention of keeping their long occupied land outside the embankment.

While activities for shifting the households living outside the embankment to inside the embanked areas have been carried out, local residents has been praying for settlement of the crop lands along the Meghna on the basis of the PTPS. The District Administration agreed to the proposal and gave decision of settlement of such land after the land required for the foreshore plantations was provided to the Forest Department. On query of the Deputy Commissioner, the Forest Department in a local meeting declared their requirement up to 50 feet from the embankment site. But later on, they changed the claim and rightly so, to 200 meters. This contradiction created serious complications among the people in the area. The District Administration had to depute police forces to help the Forest Department to implement the foreshore plantation scheme. But the local people raised objection, assaulted and injured the police and other officials (including some TA staff). The injured police lodged criminal cases against the offenders and as a result, many of the households left the shore areas and have been absenting from the hearings and other stages of land settlement apprehending arrests by the police.

A new DC joined on 20th September, which created a gap in the process of since he had to familiarize himself with the of the works of the District including those of CDSP related activities. The post of AC (Land) Hatiya was vacant in November for more than a month as the incumbent officer was sent away for training. However, the UNO discharged the works of the AC (Land) in addition to his own duties...

During the period under review, the Deputy Commissioner held two meetings of the District Monitoring Committee on 3rd August  and 19th October. The meetings reviewed the progress and discussed matters relating to implementation of the settlement activities. The Joint Secretary (Dev) of the MoL held a meeting of the Ministry level Monitoring Committee and the Internalisation Committee on the 12th October 2010.

-    Assessment of actual quantum of land for settlement:

There has been major accretion in the Hatiya river, following the closure of the river by a cross dam just south of Bashkhasli khal. People around the area have been attempting to take these lands under their possession unauthorised. Land was lost by erosion along the Meghna River during the implementing period of CDSP-III. As such, control over the accreted areas and fixation of the changing coast lines in the mouza maps and amendment of the areas of the mouza sheets have been undertaken. This  requires continuous review to enumerate the actual areas and household affected by the erosion during the last few years.

Following the excavation of the ponds, erection of the twin houses and shifting of households from outside the embankments to clustered villages inside the embankment, demarcation of the homestead lands has been undertaken extensively.

In the reporting period, the implementing agencies continued to identify and demarcate the land required for different interventions, in particular related to development of infrastructure. At the close of 31st December 2010, the situation was as reflected in the following table:

| Agencies | Interventions | Quantity of works | Alignments done | Percentage of works done |
| --- | --- | --- | --- | --- |
| BWDB | Embankment-Sea Side | 10.87 Km | 10. 87 Km | 100 % |
| ” | " - Marginal dyke | 8.00 Km | 8.00 Km | 100% |
| ” | " - Jarirdona | 7.35 Km | 7.35 Km | 100% |
| ” | " - Guide dyke | 6. 50 Km | 6.50 Km. | 100% |
| ” | Canals | 27.15 Km | 27.15Km | 100% |
| ” | Sluice structures | 3 nos. | 3 Nos. | 100% |
| ” | Closure | 1 no. | 1 no. | 100% |
| LGED | Cyclone Shelter | 22 nos. | 22 nos. | 100% |
| ” | Rural roads (UP) | 60 Km. | 51 Km. | 90% |
| ” | Ponds | 49 nos. | 49 nos. | 100% |
| ” | RDP-23 | 13 Km | 13 Km. | 100% |
| MoL | Pond (RPA) | 22 nos. | 22 nos. | 100% |
| ” | HH's rehabilitation | 616(22X28) hhs | 616 | 100% |
| ” | Ponds (GoB) | 8 nos. | 8 nos. | 100% |
| ” | Twin Houses | 128 (8X16) hh's | 256 nos. | 100% |
| Forest Dept. | Foreshore plantation | 200 ha. | 150 Ha. | 75% |
| MoL | Fixation of diluvion lines of Boyarchar along the river Meghna | 16 Km |  | 100% |
| MoL | Fixation of the homesteads around the excavated ponds | Ponds 22 nos. | 21nos | 95% |

-    Reallocation of the landless from outside the embankments under RPA

As per revised plan, activities for shifting of 774 families had been carried out. But shifting of all the families could not be completed due to delays in completion of the ponds.UNO, Hatiya took up 29 ponds to be constructed under RPA (in terms of the RDPP-second revision) to accommodate the 774 families on the homesteads over the banks of the pond. Following the modalities of the shifting plans, the families themselves would shift their present house. A reasonable shifting allowance is provided to them from project funds. Of the planned 29 ponds, 25 have been completed in 2009-10 and rectification works have been carried out to repair damages caused by the “Aiyla” cyclone.

The Project Implementation Committee of Hatiya Upazila issued work orders for excavation of the remaining four ponds in June 2010, but the contractors did not take up the excavation works till December 2010. As a result, shifting of the households earmarked for these ponds could not be realised.

As per shifting-modalities of the project, twenty-eight families are accommodated around each RPA pond. For each rehabilitated family 9(nine) decimals of land is allotted as their homestead land for setting their houses, around Tk. 10,000/- has been paid to each family as shifting allowances (fixed up by an Assessment Committee headed by the AC-Land). A water sealed latrine is given to each family through  DPHE, free of cost. Two deep tube wells are sunk at two corners of each pond, which would be maintained by the residents collectively. However, each family has to pay Tk. 320/- as contribution money towards the tube well as per WATSAN rules. Every family will get equal share of the water areas of the pond, enjoy rights for aquaculture and other cooperative activates. The intention to allot these households some additional lands outside the embankment, has been endorsed earlier by the PMC. The process of identifying land to distribute among these households is still ongoing.

Up to December 2010, 616 of the 774 households have been shifted and Tk. 53,84,700 Lac has already been paid to the households as shifting costs.

To date, 253 households have already been shifted from different alignments within the embanked areas with a view to facilitating the progress of different infrastructure interventions. These were involved in the internal alignments and hence were not included in the aforementioned 774 households of outside the embankments. An amount of Tk.22.39 lakh has been paid to these households as compensation towards shifting cost. These families have been rehabilitated in the twin houses, which are being constructed at different sites (see below) by GoB funds, allocated to the Ministry of Land.

## -    Excavation of ponds

Under GoB funds: Out of the total program for excavation of nine ponds, eight ponds had been taken up. Because one pond was no longer necessary to accommodate relocated families. Out of the eight ponds, six have already been excavated out of the GoB fund. As reported in the previous report (PR-9), the PIC of Hatiya Upazila issued Work Orders in June 2010 for excavation of the last two ponds. But the contractors did not take up the work till the approach of the monsoon. Consequently, two GoB ponds were not available for construction of the planned twin houses (128 in total, or all eight ponds). To meet the situation, twin houses have been constructed on the banks of two ponds built under Financial Assistance, as per discussions in the PMC.

Under Financial Assistance (RPA): As per RDPP-2, the physical quantity for excavation of ponds for cluster village for rehabilitation of people outside the embankment was 33 but actual field requirement was 29. So, it was decided that 29 ponds would be excavated and accordingly 25 ponds were excavated earlier and work order was issued for other four. However, due to time constraints, the decision was taken not to start the work and drop the remaining four ponds from the programme.

# -    Construction of twin houses under GoB

As reported in the previous report (PR-9), the PIC headed by the UNO, Hatiya issued work orders in January 2010 for construction of 128 twin houses. The contractors however, delayed taking up the construction works. The PIC pressed hard for completion of the houses with maintaining good quality and good workmanship. The contractors of late, have been completing the construction works in phases. The Upazila Administration has issued allotment letters to affected households showing allotment of the twin houses. The Upazila Administration has also been taking up steps for allotment of the land of the homesteads to the concerned households and transferring title of the land and ponds proportionately as per modalities of the project.

Overall progress for the construction of 128 twin houses at a cost of Tk 200.96 (GoB Tk.167.73 lakh & RPA Tk.33.23 lakh) was 79% till 31st December 2010. Construction started at all 8 CV sites Work completed at Mufti Huzur-16 houses & Dhakiya Samaj-16 houses. Construction ongoing at Nabipur-16 houses, Tanki (East) Samaj-16 houses, Gabtali-16 houses, Mainuddin bazaar-16 houses, Farazigram-16 houses and Tanki West (Dasdag gram) – 16 houses. Out of this, 128 houses, 21 to be constructed from RPA budget (Tk33.26 lakh) and 107 from GoB fund. For the 21 houses under Financial Asistance, progress achieved up to 31st December 2010 is 97% and expected to be completed by 9th January 2011 (see also Annex 2).

-    Maintenance of infrastructure under CDSP-I & II.

In the reporting period, no O&M activities in CDSP I and II areas were undertaken. Proposals were drafted by the AC (L) of Subarnachar, Companigonj and Hatiya, however without a supporting plan and estimates for the schemes. As such, the District Monitoring Committee could not approve these schemes. After revision, the District Administration forwarded a number of schemes to the office of the Project coordinator at the Ministry in Dhaka, but at the end of the reporting period, ni approval was yet given. As per RDPP-2, the budget allocation for the maintenance works in CDSP I and II areas was Tk70.00 lakh. MoL yet spent during CDSP III Tk.14.340 lakh for the construction of 1st floor (extension) of Upazila office at Hatiya, Noakhali

-    Implementation of Land Records Management System (LRMS)

The status of LRMS has been detailed in the previous Progress Report (no.9). The system is now functional at Hatiya where all the land data of CDSP III areas have been fully incorporated. At the initiative of the Ministry of land a “pilot activity” has been conducted in Companyganj upazila of Noakhali District and Ramgati Upazila of Lakhsmipur District, with a view to assess the applicability of the system in other Upazilas of the country. Under the activity, arrangements have been made for entering all the land data of the Upazilas concerning all the landed properties of both private individuals and public agencies. The activity is completed under the supervision of the UNO’s and AC(Land)’s of the two Upazilas. The officers showed positive interests in the outcome of the activity. They have been preparing the report of the pilot activity. It is expected that the reports will be available soon. On the outcome and recommendations of the reports the Ministry of Land may take further actions.

3.4.2.  Bangladesh Water Development Board (BWDB)

For detailed information see Annex 3

Physical progress achieved by BWDB up to 31st December 2010 is 99.8% against a target of 100%. This minor progress deviation is due to the delay in construction work at Chatla- and  Tankir sluice, and flood embankment Groups 6 and 8 under Noakhali O&M Division. It is expected that 100% work will be completed by 12th January 2011 (se also Annex 2).

##### -    Construction of peripheral embankment

- Sea facing embankment (10.87 km): Overall physical progress of the sea-facing embankment is 99.5% against a target of 100%. In Lakshmipur O&M Division all packages of length 4.455 km. (from Km.0.630 to Km.5.085 including Gabtali sluice, DS-2) are completed. In Noakhali O&M Division, 3.500 km length (from Km.5.085 to Km.8.585 with sluice Tankir khal) was  fully completed earlier and for 2.915 km length (from Km. 8.585 to Km.11.500 with sluice Chatla khal) work started in two packages and achieved 98% progress, Group 7 completed and Group 6 achieved 97% progress up to 31st December 2010.

- Interior dyke (8.00 km): Overall progress of 8.0 km length interior dyke from      Km. 11.500 to Km. 19.500 under Noakhali Division is 99% (against a target of 100%). Out of 5 packages, Group 8 work is going on and up to 31st December achieved 97% progress. Groups 9 to 12 are all completed.

iii. Individual guide dyke (2.965 km): Work completed for the 2.965 km length    from Km.7.035 to Km.10.00 under Noakhali  Division.

##### -    Drainage improvement works

- Re-excavation of Baggar Dona (Bhulua) river (10.0km): Re-excavation of 10.0km. length of Baggar Dona (Bhulua) river is 100% completed under Noakhali and Lakshmipur Division.

- Re-excavation of the Jarirdona khal including guide dyke cum rural road (3.535 km): Re-excavation of Jarirdona under Lakshmipur Division for 3.535 km. length from Km.0.000 to Km. 3.535 is completed.

- Excavation of the Jarirdona shortcut including guide dyke cum rural road (3.500 km): Work of Jarirdona shortcut including guide dyke cum rural road from Km. 3.535 to Km. 7.035 is 100% completed under Noakhali and Lakshmipur Division through 8 packages.

- Excavation of the Gabtali khal drainage channel (6.155 km): Excavation of Gabtali khal drainage channel including rural roads is 100% completed under Lakshmipur Division.

- Secondary drainage channel at Boyer Char (38.0 km): Re-excavation of 38.0 km. secondary drainage channel is 100% completed under Noakhali and Lakshmipur O&M Division; 28.5 km length executed by Noakhali Division and 9.5 km. length under Lakshmipur Division, out of which 3.5 km was done by LCSs formed by WMGs.

##### -    Sluices and closures

- Gabtali sluice (7vents-2.20m x 2.20m): Gabtali sluice is completed.

- Tankir khal and Chatla khal sluices (Each-2v x 1.50m x 1.80m): Construction work is in progress for Tankir khal sluice and Chatla khal sluice under Noakhali O&M Division. In Tankir khal sluice achieved progress is 98% pending a minor work for approach embankment up to design section, providing close turfing after proper dressing. In Chatla khal sluice progress achievement is 99% pending same type of work as for Tankir khal sluice in addition of providing sand/earthen bag protection by the side of the CC block protective work at river side slope of lunching apron. See also Annex 2..

- Closures: Closure-01, downstream of Banshkhali outlet and closure 02 on Hatiya river near Char Baggar Dona-I (CBD-I) are completed, but in closure 01 major sliding and rain cut were formed at country side slope. In case of closure 02 protective blocks were partly damaged at river side slope. Both  defects have to be rectified during defect liability period.  Rectification work  started in both closures.

-   Maintenance works

- As per RDPP-2 budget allocation for the maintenance works at CDSP-I & II area under CDSP-III is Tk.350.00 lakh. Till 31st December works completed for Tk.329.28 lakh in total for the re-excavation of drainage khals, re-sectioning of flood embankment, repairing of gates for sluices in CDSP-I & II areas under Noakhali and Feni O&M Division. During the reporting period, works were completed against the balance amount (Tk.20.00lakh) for the re-excavation of Mora Dona drainage khal under Noakhali O&M Division.

- Land Acquisition

No work done during the reporting period.As per original DPP and RDPP-2 the budget allocation for land acquisition was Tk.260lakh for 100ha. Till today Tk.178.52 lakh has been spent in total for the 85.52ha land acquisition, mainly for the construction of embankment and ex/re-excavation of Jarir Dona khal.

#### 3.4.3 Local Government Engineering Department

For detailed information see Annex 3

Local Government Engineering Department (LGED) achieved target progress 100%.

##### -   Roads

- Paved road (18.70 km): Overall progress of paved road is 100%. LGED, Lakshmipur completed 7.00 km and Noakhali 11.56 km length.

- Earthen road (55.00 km): Overall progress of the construction of earthen road is 100%. LGED, Noakhali completed 13 roads with a total length of 32.00 km. and LGED, Lakshmipur completed 13 roads with a total length of 22.60 km.

- Cyclone shelter approach roads (2.70 km): LGED, Noakhali completed in total 2.70 km approach roads to connect all the cyclone shelters with the nearby main roads.

-   Bridges and culverts

- Three bridges: Construction of all the three RCC deck Girder Bridges at Tankir bazar over Tankir branch khal, Mohammadpur bazar and Mirpur bazar over Gabtali khal are completed by LGED, Noakhali.

ii   Foot bridge:  Construction work of foot bridge at Hatiya bazar is completed under LGED, Noakhali.

iii  Box culverts (28 nos.): Overall progress of the box culvert construction is 100%.LGED, Lakshmipur completed 7 and LGED, Noakhali completed 21 box culverts.

- Pipe culverts (38 nos.): In case of construction of 38 pipe culverts overall progress achieved is 100%. LGED, Lakshmipur completed construction of 7pipe culverts and LGED, Noakhali completed 31 pipe culverts.

-    Bus stand

LGED, Noakhali completed construction of bus stand near Tankir bazar.

##### -    Community ponds (50 nos.)

Overall progress for the construction of community pond is 100%; 49 ponds were completed by LGED; one was dropped due to non availability of a site. LGED, Noakhali completed (re-)excavation of 30 ponds, out of which 15 by LCSs and rest by contractors. LGED, Lakshmipur completed 19 ponds out of which four were completed by LCSs.

##### -Cyclone shelters (20 nos.)

i.	Construction of all 20 cyclone shelters is completed. LGED, Lakshmipur completed 7 and LGED, Noakhali completed 13 cyclone shelters.

- Field raising for cyclone shelters (20 nos.): LGED, Noakhali completed field raising of 13 cyclone shelters and LGED Lakshmipur completed 7.

iii. Additional furniture supply for 15 cyclone shelters: LGED, Noakhali supplied additional furniture for 15 cyclone shelters.

##### Additional works as per RDPP-2

i.   .Box culvert (1 nos.): Work order was issued on 23rd November by LGED.

The work was later dropped because of time constraints.

ii.   Pipe culvert (1 no.): Work was completed by LGED Noakhali.

iii.  Sixteen rural roads (6.8 km additional and CV connecting roads): All work

was completed by LGED Noakhali.

iv. Additional work of Bus stand at Tankir bazar (Drain, Water supply to public toilet etc.):  Work completed by LGED, Noakhali.

v.  Emergncy work of Steamerghat to Chairmanghat road (HBB road construction near Chairman bazar 270m):  Work is completed under LGED, Noakhali.

-     Maintenance works

As per RDPP-2,  budget allocation for the maintenance works in CDSP I and II areas from CDSP-III funds is Tk.283.00 lakh. During the reporting period Tk.12.09 lakh was spent for earthen road, pipe culvert and cyclone shelter under LGED, Noakhali. In total fund spent for maintenance is Tk.274.15 lakh

#### 3.4.4 Department of Public Health Engineering

For detailed information see Annex 3

Physical progress achieved by DPHE up to 31st December 2010 stands at 97% against a target of 100%. Progress deviation is due to minor delay in single pit latrine installation, deep tube wells platforms and PSF construction, but mainly for the incomplete software training program.

##### -Water supply: deep tube wells, ponds with sand filter and rainwater harvesting

- Deep tube wells (600 nos.) and test deep tube wells (18nos): Overall progress of deep hand tube well is 99.9% up to 31st December 2010. Out of 600, 599 have been sunk; one was dropped from the programme due to a site problem at Caring Char. Deviation for target achievement is due to delay in construction of 8 tube well platforms at Boyer Char up to 31st December 2010.  Work is going on and it is expected that all platforms will be completed by 9th January 2011 (see Annex 2). As per approved RDPP-2, 460 tube wells were proposed for sinking at Boyer Char and surplus 140 tube wells were proposed for sinking at new chars (66 at Char Nangulia, 42 at Nolerchar and 32 Caring char). Out of which 139 was completed including platform construction. Out of 18 test tube wells, eight were already sunk at Boyer Char and an additional 10 test tube wells, as proposed in RDPP-2, 6 for Char Nangulia, 2 for Noler Char and 2 for Caring Char were installed including platform construction.

- Ponds with sand filter (10 nos.): Construction work for all 10 PSF completed.

In RDPP-2, 37 additional PSFs, including 19 ponds re-excavation, were proposed in the western saline zone of Boyer Char. Re-excavation of 19 ponds was already completed. Out of 37 PSFs, 3 were dropped as the proposed site at MoL’s ponds were not ready.  Achieved progress of the remaining 34 PSFs is 99.5%. This minor progress deviation is due to delay in construction of PSF cover with fibre glass and steel frame. All materials are available at site; there is  only delay in fitting and fixing. It is expected that work to be completed by 9th January 2011 (see also Annex 2).

iii Rainwater harvesting (18 nos.): Work completed for all 18 rainwater harvesting. In RDPP-2, 42 additional rainwater harvesting scheme were proposed for the western saline zone of Boyer Char are also  completed.

##### -    Sanitary  latrines

  - Single pit latrines (8500 nos.): Overall progress of the single pit latrine is 99.7% against a planned progress of 100% up to 31st December 2010. All pit latrines have already been supplied at site. The deviation from the target is due to delay in installation at houses for about 200 pit latrines. Work is in progress and it is expected that this work will be completed by 9th January 2011 (see Annex 2).

  - Public toilets (20 nos.): Construction of all 20 public toilets completed. They have  all been handed over to respective market management committees, including water supply facilities. All the committees received necessary training and support materials for proper cleaning and maintenance. Approach roads had been constructed (10 nos.) where necessary, as additional works for public toilet.

iii. Software training programme: Out of 181 training events, 23 were completed.

Training was on water supply and sanitation, use and maintenance of public

Toilets. Including the purchase of training materials, the progress can be put

at 40%

-    Maintenance works

i    As per RDPP-2,  budget allocation for the maintenance works in CDSP I and II areas under CDSP III is Tk.24.35 lakh. Up to 31st December 2010, total expenditure for maintenance is Tk.24.29 lakh. During the reporting period field work completed for Tk.5.50 lakh for the maintenance (re-sinking) of deep tube wells, maintenance of existing deep tube wells including supply of tube well accessories, and re-construction of platforms.

    - Department of Agriculture Extension (DAE)

DAE has completed all planned activities under CDSP-III within 30th June 2009 but continued follow up activities in Boyer Char. DAE has formed a Farmers Association (FA) on in July, comprising representative from the existing Farmer Forums and Water Management Groups. There are 25 members in the FA, 20  male and five female. Three meetings were held of the FA during the reporting period, which were supported jointly by the TA- team and DAE field officials. A workshop was held at Mainuddin Bazar in CDSP-III site office, which was organized by the SARCCAB-IRRI project. The representatives of FA, FFs and WMGs attended the workshop. Groundnuts and soybean seed were distributed among 30 farmers. MIDPCR-DAE part imparted a 3-days training to the farmers at Boyer Char during the reporting period

Technical Report no.6 on agricultural development and social forestry activities was published.

3. 4. 6     Department of Forest.

### Formation of Social Forestry Groups

Ten more Social Forestry Groups (SFG) were formed for roadside plantation, with 320 members (192 or 60% male, and 128 or 40% female). On 31st December 2010, 128 SFGs existed. Despite the new 10 groups, this is less than the number at the beginning of the reporting period, because existing groups for foreshore plantations were re-organised and 12 SFGs became superfluous.

Social Forestry Group (SFG) formation (Total/ formed in reporting period):

| Name of the Activities | No.of SFG | No.of Male | No of Female | Total |
| --- | --- | --- | --- | --- |
| Roadside plantation | 75/10 | 1214/192 | 761/128 | 1975/320 |
| Foreshore plantation | 11/0 | 155/0 | 100/0 | 255/0 |
| Embankment plantation | 28/0 | 363/0 | 239/0 | 602/0 |
| Mangrove plantation | 14/0 | 210/0 | 130/0 | 340/0 |
| # Total | 128/10 | 1942/192 | 1230/128 | 3172/320 |

### Land lease and benefit sharing agreements

Roadside plantation: For all SFGs agreements have been completed; out of the total of 1975, photocopies for 826 groups have been distributed. The other 1149 members had already received agreements.

Foreshore plantation: Agreements have been signed by  SFGs, Union Parishad, Forest Department for 165 SFG members. They have been submitted to the UNO of Hatiya Upazilla for signing. The 90 remaining ones will be done in the extension period.

Embankment plantation: For 417 SFG members agreements have been signed by SFGs, Union Parishad and Forest Department and have been sent to Executive Engineers of BWDB in Lakshmipur and Noakhali for signing. For 185 members the agreements were already distributed.

Mangrove plantation: All agreements were distributed before the reporting period.

### Establishment of nurseries

No new nurseries were established.

### Roads-  and embankment plantation

In the reporting period, 48 km new roadside plantations were established. Each km. of road length contains 1,000 seedlings, 500 at each side. Pruning and maintenance work has been carried out in already existing road side plantations, creating an income for SFG members. From old roadside plantation, SFG members collected 3,600 kg of fuel wood. The price per kg. was reduced from around Tk. 7.5 to Tk 3 because of the increased supply of fuel  wood in Boyer Char due to the forest activities in the project.

Newly established road plantations (July-December 2010)

| Sl.No | Name of road | Actual road length (km) | No-of seedlings planted | No-of SFG involved |
| --- | --- | --- | --- | --- |
| 01 | Solaiman Bazar to Haris sarder Doken | 2.00 km | 2000 | 01 |
| 02 | Haris sarder to Mir Market | 2.00 km | 2000 | 01 |
| 03 | Islampur to Rasulpur | 2.00 km | 2000 | 01 |
| 04 | Mir market to gabtoli khal | 2.00 km | 2000 | 01 |
| 05 | Mollah gram to south embankment | 2.00 km | 2000 | 01 |
| 06 | Islampur to 12 Dug | 2.00 km | 2000 | 01 |
| 07 | Khalek house to 12 dug | 2.00 km | 2000 | 01 |
| 08 | 12 Dug to Solaiman bazaar | 2.00 km | 2000 | 01 |
| 09 | Mainuddin bazar to Dider bazar | 2.00 km | 2000 | 01 |
| 10 | Dider bazar to Chairmen hat | 2.00 km | 2000 | 01 |
| 11 | Pondath house to Dider bazar | 2.00 km | 2000 | 01 |
| 12 | Jorkhali road to Chatla khal | 2.00 km | 2000 | 01 |
| 13 | Younuspur road | 1.50 km | 1500 | 01 |
| 14 | Jorkhali bazar to Islampur | 1.50 km | 1500 | 01 |
| 15 | Gabtoli sluice to M.pur bazar | 3.00 km | 3000 | 01 |
| 16 | M.pur to Rasulpur culvert | 3.00 km | 3000 | 01 |
| 17 | Rasulpur culvert to Baggar dona | 3.00 km | 3000 | 01 |
| 18 | Gabtoli sluice to M. pur Bazar | 3.00 km | 3000 | 01 |
| 19 | M.pur bazar to Bilkis house | 3.00 km | 3000 | 01 |
| 20 | Bilkis house to Baggar dona | 3.00 km | 3000 | 01 |
| 21 | M.pur to Mir market | 1.50 km | 1500 | 01 |
| 22 | Tiner mosque to Adrasha gram | 1.50 km | 1500 | 01 |
|  | Total : | 48 km | 48000 | 22 |

In the six months, 4.50 km of new embankment plantations were done, while vacancy filling and other maintenance works have been going on in existing embankment plantations. In totals, 4,800 kg of fuel wood was collected, worth Tk. 3 per kg.

Embankment plantation (July-December 2010)

| Sl No. | Name of Area | Planting (km) | No of seedlings planted | No. of SFG |
| --- | --- | --- | --- | --- |
| 01 | Champa ghat to Kalam house | 01 | 2400 | 01 |
| 02 | Kalam house to Chairmen Ghat | 01 | 2400 | 01 |
| 03 | Chairmen Bazar to Chatla sluice | 01 | 2400 | 01 |
| 04 | Chatla sluice to Oder khal | 1.50 | 3600 | 01 |
|  | Total : | 4.50 km | 10800 | 04 |

### Foreshore plantation

Out of the 200 ha (as per design), 85 ha of foreshore plantation were completed as far as the construction of mounds is concerned, of which 45 ha. in the reporting period. Of these 85 ha, 35 ha. were indeed planted with trees, all done in the July to December period. Funds constraints severely hampered further progress.

### Mangrove plantation

Maintenance work continued in the mangrove plantation in Jaliar Char. No new plantations were done, as the programme was already completed.

Village afforestation programme

Afforestation activities took place in 17 new cluster villages, benefiting 492 households. In total, 52 villages have now benefited from this component. In this programme, 22 different species were used.

### Capacity  building

1.	For people that have been settled outside the embankment (foreshore areas), two orientation workshops were held. Subjects were the concept of foreshore plantations and the consequences for their households of such plantations. Staff of the Forest Department and of the TA-team were the facilitators.

2. 	One benefit agreement distribution workshop was organized for SFG members. The Divisional Forest Officer sand the Acting Team Leader facilitated the workshop.

- As in the previous reporting periods, SFG meetings were held, on group approach in social forestry, disseminating information, SFG responsibilities, motivation and awareness building among group members.

A Technical Report (no. 6) on agriculture and social forestry was published.

3.4.7 BRAC/CDSP

The NGO programme, carried out by five local NGOs and coordinated by BRAC, was completed as per 1st July 2010.

3.4.8	Training

Annex 4 provides an overview of the progress of the training imparted during the reporting period..

Chapter 4  PROJECT ORGANIZATION

  - Introduction

The project organization stayed the same in the reporting period. Some changes in personnel occurred, which are reported on below. Information is also provided on the inputs of the Technical Assistance team and on the coordination mechanisms.

  - The parties involved and their responsibilities

    - The Ministry of Water Resources

No changes took place.

    - Embassy of the Kingdom of The Netherlands

There were no visits to the project of staff of EKN in the reporting period. The Chief Technical Advisers had discussions on several occasions with embassy staff at the embassy in Dhaka.

    - Bangladesh Water Development Board

A new Executive Engineer, O&M Lakshmipur Division joined in December.

    - Local Government Engineering Department

No changes of officials at District and head office level

    - Department of Public Health Engineering

No changes in project personnel.

    - Department of Agricultural Extension

A new Deputy Director, Department of Agriculture Extension, Noakhali joined in November.

    - Forestry Department

A new Divisional Forest Officer (and Project Director CDSP III) took up office in November.

    - Ministry of Land

No changes in project personnel.

    - Government at local levels

Still, there are no elected Union Council members in Boyer Char. The District Administration has appointed an Administrator and six members (five male, one female) for Horni Union.

    - Community based field level institutions

See 3.2.3. for Water Management Organizations (WMO), 3.4.5. for Farmers Forums (FF) and 3.4.6. for Social Forestry Groups (SFG).

    - NGOs

See 3.4.7.

    - Technical Assistance Team

The Chief Technical Adviser (from Euroconsult Mott Mac Donald) spent in total 27 days on the project (21 days in August and six in December). The CTA\ visited the project in November on an IFGAD\ -assignment to facilitate the transfer tp CDSP IV.The expatriate civil engineer for quality control worked for 10 days on the project in November/December (see Mission Report no. 20).

BETS Consulting Services Ltd. provided 13.17 months of long term and 4.99 months of short term experts in the July to December period.. Socioconsult provided one long term expert for 5.44 months.. Through BETS, 32 support staff members were posted on 29 full time positions.

The list of members of the TA-team during the reporting period is taken up as Annex 5.

  - Formal coordination mechanisms

- National Steering Committee:

The National Steering Committee (NSC) had its 4th meeting in August. Most important subjects that were discussed were: the evaluation by IMED of CDSP III; the conflict between the Social Forestry Rules of 2004 and the Tree Plantation Manual of BWDB of 2003; the completion of CDSP III; the preparation of DPPs for CDSP IV; and the cross dam between Noakhali mainland and Urir Char.

- Project Management Committee:

The PMC met four times in the reporting period. Subjects that were discussed included review of progress and inventarisation of pending activities, the need to complete all activities before 31st December 2010, reimbursement requests, preparation of DPPs for CDSP IV, fund requisitions, study tour to West Bengal, NSC meeting. Attendance rate of the Project Directors/Project Coordinators of the  participating agencies stood at a little over 50%. See annex 6 for a list of the members of the PMC on 31st December 2010.

4.4. Monitoring, reporting and review

The PMC meetings were the main monitoring tool in the reporting period. The central monitoring instrument for the project is the PMC, fed by progress reports of the agencies and by the overall six month Progress Reports on the overall project. In a sense, the work of the preparatory missions of IFAD for CDSP IV contributed to the information available on CDSP III.

The following reports were published:

- Mission Report no 20 on quality control of infrastructure development

- Technical Report no. 5 on monitoring of land settlement (especially retention) and agricultural development

- Technical Report no. 6 on agriculture and forestry

- Technical Report no. 7 on impact of CDSDP I, II and III.

The Project Coordination Board of the three consulting firms Euroconsult Mott MacDonald, BETS and Socioconsult did not meet in the reporting period.

###### Chapter 5  BUDGET AND TIME FRAME

5.1. Introduction

Paragraph 5.2 gives information on the expenditures upto to 31st December from the side of the Government of Bangladesh and paragraph 5.3. on the Dutch contribution (Financial Assistance and Technical Assistance).

5.2. Contribution of the Government of Bangladesh

The following table reflects the agency wise expenditure from the side of the Government of Bangladesh as on 31-12-2010

Tk. in Lakh.

| Name of Agency | Amount as per RDPP-2 (GoB) | Expenditure up to 31st December 2010 | Expenditure in % |
| --- | --- | --- | --- |
| BWDB | 821.99 | 667.94 | 81 |
| LGED | 507.54 | 505.56 | 99 |
| DPHE | 74.35 | 69.35 | 93 |
| MoL | 516.00 | 325.30 | 63 (Check with LSA) |
| DAE | 13.67 | 9.20 | 67 |
| DoF | 24.05 | 23.71 | 99 |
| Total: |  |  |  |

5.3. Contribution of the Government of the Netherlands

-   Financial Assistance

Up to 31st December 2010, requests for re-imbursement were received for a total of Taka 7936.40 lakh of which Taka 1198.39 lakh in the reporting period. Of the received request an amount of Taka 7876.46 was indeed recommended for re-imbursement by the TA Team, of which an amount of Taka 1228.40 lakh (including some pending) in the reporting period. The table gives the agency wise break up.

#### Reimbursement position (Financial Assistance)  as on 30-06-2010

Tk in Lakh

| SL No. | Agency | Revised PP amount (RPA) | Claimed amount | Recommended amount | Amount not yet disposed. |
| --- | --- | --- | --- | --- | --- |
| 01 | BWDB | 4412.07 | 3955.65 | 3955.65 | 0.00 |
| 02 | DAE | 66.50 | 61.04 | 61.04 | 0.00 |
| 03 | FD | 535.43 | 342.09 | 312.18 | 29.91 |
| 04 | LGED | 2910.00 | 2760.44 | 2760.29 | 0.15 |
| 05 | DPHE | 800.00 | 620.75 | 593.86 | 26.88 |
| 06 | MoL | 496.00 | 196.44 | 193.44 | 3.00 |
| Total: |  | 9,220.00 | 7936.40 | 7876.46 | 59.95 |

-    Technical Assistance

The expenditures in the reporting period totaled Euro 161,228.90 (see Annex 8).  Still available for expenditures in the planned two months bridging period in 2011 is Euro 34,531.

5.4.	Money flows and financial reporting

Money flows and ways of financial reporting did not change

5.5.	Time frame

The project period of 63 months officially ended on 31st December 2010. The very few project works that were not completed have been mentioned in the concerned sections of Chapter 3. To provide time for reporting and for activities with regard to the reimbursement procedure, and to facilitate the transfer to CDSP IV the contract with the Technical Assistance team has been extended with two months till 1st March 2011. The team will work with a skeleton staff. A separate work plan has been submitted for this bridging period.

Chapter  6    RISKS AND ASSUMPTIONS

As risks, the following five elements were identified from the beginning of the project period:

- Timeliness and availability of funds

Progress of works were hampered by funds constraints, in particular in case of BWDB and Forest Department, and to a lesser extent of DPHE and the Ministry of Land.

- Timeliness of availability and quality of inputs

Staff shortages still formed as problem for BWDB, DPHE and the Ministry of Land. The lack of staff is a continuous problem that cannot be solved within the framework of CDSP, since it is related to the overall strength of the organizations.

- Coordination of all involved institutions

The National Steering Committee met for the fourth time in August, where a number of issues were indeed resolved. This meeting proved the usefulness of the Committee. Over the whole project period however, the Committee should have convened more frequently.  The Project Management Committee met four times in the reporting period and continued its valuable coordination function. In the reporting period, in particular the preparation of the DPPs for CDSP IV benefited from the functioning of the PMC.

- Political support and political stability

Political support in the project area continued. Elected officials kept their positive attitude towards CDSP III as well as CDSP IV.

- Favourable weather conditions

Heavy rains in August and September impeded the work on Chatla sluice, while mounds, freshly constructed by the Forest Department, were washed away by unexpected high tides. Gabtali sluice was damaged by heavy rains and the subsequent unprecedented discharge through the sluice in October.

ANNEXES

Annex-1 :	Map of Project areas

Annex-2	:	Report Joint Verification Team

Annex-3	:	Overview progress infrastructural works

Annex-4	:	Training activities in reporting period

Annex-5	:	List of members Technical Assistance Team

Annex-6	:	List of Project Management Committee

Annex-7	:	Item wise FA budget and Re-imbursement

Annex-8	:	Technical Assistance Budget