TABLE OF CONTENTS

Page

TABLE OF CONTENTS.................................................................................................	i

LIST OF ABBREVIATIONS..........................................................................................	ii

Chaper 1: INTRODUCTION...........................................................................................	1

  - Background...............................................................................................................	1

  - Approaches and strategies........................................................................................	1

  - Linkages of CDSP III to other development efforts.................................................	2

  - Relation of Inception Report to Project Proformas of implementing agencies........	2

Chapter 2: OBJECTIVES AND SCOPE OF THE PROJECT...................................	4

2.1. 	Development objectives and project purposes........................................................	4

2.2. 	Components, activities and Logical Framework.....................................................	4

2.3. 	Target groups...........................................................................................................	4

2.4	Target areas..............................................................................................................	4

Chapter 3: ACTIVITIES PER COMPONENT............................................................	5

  - Introduction.............................................................................................................	5

  - Institutional development........................................................................................	5

  - Studies, knowledge management and dissemination..............................................	11

  - Interventions at field level in particular in Boyer Char..........................................	15

Chapter 4: PROJECT ORGANIZATION...................................................................	31

  - Introduction............................................................................................................	31

  - The parties involved and their responsibilities.......................................................	31

  - Formal coordination mechanisms...........................................................................	34

  - Monitoring reporting and review............................................................................	34

Chapter 5: BUEDGT AND TIMEFRAME..................................................................	36

  - Introduction............................................................................................................	36

  - Contribution of the Government of Bangladesh....................................................	36

  - Contribution of the Government of The Netherlands............................................	36

  - Money flows and financial reporting....................................................................	37

  - Time frame............................................................................................................	37

Chapter 6: RISKS AND ASSUMPTIONS..................................................................	38

Annexes

LIST OF ABBREVIATION

ADC	:	Additional Deputy Commissioner

AC (L)	:	Assistant Commissioner (Land)

ADP	:	Annual Development Plan

AEO	:	Assistant Extension Officer

BARD	:	Bangladesh Academy for Rural Development

BARI	:	Bangladesh Agricultural Research Institute

BRAC	:	Bangladesh Rural Advancement Committee

BRRI	:	Bangladesh Rice Research Institute

BWDB	:	Bangladesh Water Development Board

CBD	:	Char Baggar Dona

CBT	:	Char Bhatir Tek

CEGIS	:	Centre for Environmental and Geographic Information Services

CERDI	:	Centre for Extension Research Development Institute

CM	:	Char Majid

CDSP	:	Char Development and Settlement Project

CV	:	Cluster Village

DAE	:	Department of Agricultural Extension

DDC	:	Development and Design Consultant

DDCC	:	District Development Coordination Committee

DOC	:	Department of Cooperative

DOF	:	Department of Forest

DGLRS	:	Director General Land Reform Survey

DPHE	:	Department of Public Health Engineering

DTL	:	Deputy Team Leader

DTW	:	Deep Tube Well

FF	:	Farmers Forum

GoB	:	Government of Bangladesh

HH	:	Household

HYV	:	High Yielding Variety

ICRD	:	Integrated Coastal Resource Database

ICZM	:	Integrated Coastal Zone Management

IPSWAM	:	Integrated Planning for Sustainable Water Management

LA	:	Land Acquisition

LCS	:	Landless Contracting Society

LGED	:	Local Government Engineering Department

LGI	:	Local Government Institution

LRMS		Land Records Management System

MC	:	Management Committee

MoL	:	Ministry of Land

NGO	:	Non Governmental Organization

NSC	:	National Steering Committee

O&M	:	Operation and Maintenance

PDZ	:	Productivity Zone

PMC	:	Project Management Committee

PMU-ESPP	:	Project Management Unit-Estuary Studies and Pilot Project

PP	:	Project Proforma

RDA	:	Rural Development Academy

RNE	:	Royal Netherlands Embassy

SRDI	:	Soil Research Development Institute

SFG	:	Social Forestry Group

TA	:	Technical Assistance

TL	:	Team Leader

TOT	:	Training of Trainers

UNO	:	Upazila Nirbahi Officer

UP	:	Union Parishad

XEN	:	Executive Engineer

XO	:	Extension Overseer

WARPO	:	Water Resource Planning Organisation

WMA	:	Water Management Association

WMF	:	Water Management Federation

WMG	:	Water Management Group

WMO	:	Water Management Organization