## Overview infra CDSP-III
Item of work | Design available (y/n) | Design concurred (y/n) | Estimate concurrence given (y/n) | Floating tender (y/n) | Contract signed (y/n) | Work order given (y/n) | Physical progress % | Contract amount (Tk. Lac) | Reinbursement claimed (Tk. Lac) | Reinbursement recommended (Tk. Lac)
BWDB
1) Embankments
1.1) Sea dyke, 0.63km-3.365km (2.735 km), Lakshmipur | y | y | y | y | y | y | 39.3333 | 102.01 | 29.502 | 29.502
1.2) Sea dyke, 3.365km-5.085km (1.72 km), Lakshmipur | y | y | y | y | y | y | 64.65 | 76.12 | 32.54 | 32.54
1.3) Sea dyke, 5.085km-8.585km (3.5 km), Noakhali | y | y | y | y | y | y | 100 | 154.8742 | 74.933 | 74.933
1.4) Sea dyke, 8.585km-11.5km (2.915 km), Noakhali | y | y | y | y | n | n | 0 | - | - | -
1.5) Interior dyke, 11.5km-13.0km (1.5 km), Noakhali | y | y | y | n | n | n | 0 | - | - | -
1.6) Interior dyke, 13.0km-21.5km (8.5 km), Noakhali | y | y | n | n | n | n | 0 | - | - | -
2) Guide dyke
2.1) Guide dyke cum rural road, 7.035km-9.195km, Noakhali | y | y | y | y | y | y | 0 | 53.03 | - | -
3) Re-excavations
3.1) Re-excavation Jarirdona, 0km-2.625km (2.625 km), Lakshmipur | y | y | n | n | n | n | 0 | - | - | -
3.2) Re-excavation Jarirdona, 2.625km-3.535km (0.91 km), Lakshmipur | y | y | y | y | y | y | 0 | 105.58 | - | -
3.3) Re-excavation Baggardona, Noakhali | y | y | n | n | n | n | 0 | - | - | -
4) Short cuts
4.1) Jarirdona shortcut, 3.535km-4.535km (1 km), Lakshmipur | y | y | y | y | y | y | 0 | 107.34 | - | -
4.2) Jarirdona shortcut, 4.535km-6.035km (1.5 km), Lakshmipur | y | y | y | y | n | n | 0 | - | - | -
4.3) Jarirdona shortcut, 6.035km-7.035km (1 km), Noakhali | y | y | y | y | y | y | 15 | 158.97 | - | -
4.4) drainage channel Gabtali khal (6.5km), Noakhali | y | n | n | n | n | n | 0 | - | - | -
4.5) drainage channel Banshkhali (1.45km), Noakhali | n | n | n | n | n | n | 0 | - | - | -
4.6) improvement secondary drainage (35km), Noakhali & Lakshmipur | n | n | n | n | n | n | 0 | - | - | -
5) Sluices
5.1) Gabtali Khal sluice, Lakshmipur | y | y | y | y | n | n | 0 | - | - | -
5.2) Tankir Khal sluice, Noakhali | y | y | y | n | n | n | 0 | - | - | -
5.3) Chatla Khal sluice, Noakhali | y | y | n | n | n | n | 0 | - | - | -
5.4) Hatiya Khal sluice, Noakhali | n | n | n | n | n | n | 0 | - | - | -
5.5) Basumajhir Khal sluice, Noakhali | n | n | n | n | n | n | 0 | - | - | -
6) Closures
6.1) closure 1 (Steamer Ghat?), Noakhali | y | n | n | n | n | n | 0 | - | - | -
6.2) closure 2 (CBD-1), Noakhali | y | n | n | n | n | n | 0 | - | - | -
LGED
7) Bridges
7.1) bridges (3 no's), Lakshmipur | n | n | n | n | n | n | 0 | - | - | -
7.1) bridges (3 no's), Lakshmipur | n | n | n | n | n | n | 0 | - | - | -
7.2) bridge (20m), Noakhali | n | n | n | n | n | n | 0 | - | - | -
7.2) bridge (20m), Noakhali | n | n | n | n | n | n | 0 | - | - | -
8) Busstand
8.1) Busstand, Noakhali | n | n | n | n | n | n | 0 | - | - | -
9) Community ponds
9.1) 5 ponds, Lakshmipur | y | y | y | y | y | y | 0 | 4.007 | - | -
9.2) 24 ponds, Lakshmipur & Noakhali | n | n | n | n | n | n | 0 | - | - | -
9.3) 15 ponds, LGED, Noakhali | y | y | y | y | y | y | 82.6667 | 19.6449 | 0 | 0
9.4) 6 ponds, LCS, Noakhali | y | y | y | y | y | y | 100 | 13.1014 | 6.7816 | 6.7816
10) Culverts
10.1) box culverts (2 no's), Lakshmipur | y | y | y | y | n | n | 0 | 0 | 0 | 0
10.2) pipe culverts (5 no's), Lakshmipur | y | y | y | y | n | n | 0 | 0 | 0 | 0
10.3) box culverts (4 nos), Noakhali | y | y | y | y | y | y | 71.25 | 47.287 | 11.864 | 11.864
10.4) pipe culverts (7 no's), Noakhali | y | y | y | y | y | y | 34.2857 | 8.3947 | 0 | 0
11) Cyclone shelters
11.1) 4 cyclone shelters, Lakshmipur | y | y | y | y | y | y | 0 | 229.0012 | - | -
11.2) 3 cyclone shelters, Lakshmipur | y | y | y | y | n | n | 0 | - | - | -
11.3) 5 cyclone shelters 2005-06, Noakhali | y | y | y | y | y | y | 64.2 | 267.3533 | 102.602 | 102.602
11.4) 8 cyclone shelters 2006-07, Noakhali | y | y | y | y | y | y | 37.25 | 450.5268 | 80.459 | 77.916
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12) Roads
12.1) paved (7.5 km), Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | 0
12.2) rural (3 rds / 8.20 km), Lakshmipur | y | y | y | y | y | y | 73.6667 | 22.48 | 8.8231 | 6.7421
12.3) rural (1 rd / 2.5 km), Lakshmipur | y | y | y | y | n | n | 0 | 0 | 0 | 0
12.4) rural (11.5 km), Lakshmipur & Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | 0
12.5) paved (7.5 km), Noakhali | y | y | y | y | n | n | 0 | 0 | 0 | 0
12.6) rural (5 roads, 13.6 km) 2005-06, Noakhali | y | y | y | y | y | y | 73.74 | 37.9413 | 14.8947 | 14.8947
12.7) rural (4 roads, 9.4 km) 2006-07, Noakhali | y | y | y | y | y | y | 100 | 29.721 | 14.8433 | 14.8433
DPHE
13) Deep tube wells
13.2) deep tube wells (200 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 22 | 106.2834 | - | -
13.1) deep tube wells (102 nos), Noakhali | y | y | y | y | y | y | 90 | 48.8266 | 34.5743 | 29.0143
13.3) deep tube wells (298 nos), Noakhali & Lakshmipur | y | y | n | n | n | n | 0 | - | - | -
14) Pond with sand filter
14.1) 4 ponds with sf, Lakshmipur | y | y | y | y | n | n | 0 | - | - | -
14.2) ponds with sf, Noakhali | y | y | n | n | n | n | 0 | - | - | -
15) Public toilets
15.1) public toilets (10 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 21.8 | 62.32 | - | -
15.2) public toilets (10 nos), Noakhali & Lakshmipur | n | n | n | n | n | n | 0 | - | - | -
16) Rainwater harvesting
16.1) rainwater harvesting (5 nos), Lakshmipur | y | y | y | y | n | n | 0 | - | - | -
17) Single pit latrines
17.1) single pit latrines (5000 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 24.39 | 84.912 | - | -
17.2) single pit latrines (3500 nos), Noakhali & Lakshmipur | y | y | y | n | n | n | 0 | - | - | -
MoL
18) Construction work in cluster villages
18.1) construction of twin houses (144 nos), Lakshmipur | n | n | n | n | n | n | 0 | - | - | -
18.2) construction of ponds, Lakshmipur | n | n | n | n | n | n | 0 | - | - | -
18.3) construction of ponds, Noakhali | n | n | n | n | n | n | 0 | - | - | -
19) Settlement programme
19.1) Rehabilitation, Lakshmipur | n | n | n | n | n | n | 0 | - | - | -
19.2) Rehabilitation, Noakhali | n | n | n | n | n | n | 0 | - | - | -

## Overview BWDB
Table 1 - BWDB | Design available (y/n) | Design concurred (y/n) | Estimate concurrence given (y/n) | Floating tender (y/n) | Contract signed (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac)
Item of work | [7 empty] | 2007-06-30
1) Embankments
Total sea dyke (10.87 km) | 100 | 100 | 100 | 100 | 73.1831 | 73.1831 | 52.3252 | 40 | 12.3252 | 333.0042 | 136.975 | 136.975
Total interior dyke (10.00 km) | 100 | 100 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1) Sea dyke, 0.63km-3.365km (2.735 km), Lakshmipur | y | y | y | y | y | y | 39.3333 | 40 | -0.66667 | 102.01 | 29.502 | 29.502
1.2) Sea dyke, 3.365km-5.085km (1.72 km), Lakshmipur | y | y | y | y | y | y | 64.65 | 40 | 24.65 | 76.12 | 32.54 | 32.54
1.3) Sea dyke, 5.085km-8.585km (3.5 km), Noakhali | y | y | y | y | y | y | 100 | 40 | 60 | 154.8742 | 74.933 | 74.933
1.4) Sea dyke, 8.585km-11.5km (2.915 km), Noakhali | y | y | y | y | n | n | 0 | 40 | -40 | - | - | -
1.5) Interior dyke, 11.5km-13.0km (1.5 km), Noakhali | y | y | y | n | n | n | 0 | 0 | 0 | - | - | -
1.6) Interior dyke, 13.0km-21.5km (8.5 km), Noakhali | y | y | n | n | n | n | 0 | 0 | 0 | - | - | -
2) Guide dyke
2.1) Guide dyke cum rural road, 7.035km-9.195km, Noakhali | y | y | y | y | y | y | 0 | 0 | 0 | 53.03 | - | -
2.2) Guide dyke cum rural road, 9.195km-10.00km, Noakhali | y | y | n | n | n | n | 0 | 0 | 0 | 0 | - | -
3) Re-excavations
Total Jarirdona (3.00 km) | 100 | 100 | 30.3333 | 30.3333 | 30.3333 | 30.3333 | 0 | 12 | -12 | 105.58 | 0 | 0
3.1) Re-excavation Jarirdona, 0km-2.625km (2.625 km), Lakshmipur | y | y | n | n | n | n | 0 | 12 | -12 | - | - | -
3.2) Re-excavation Jarirdona, 2.625km-3.535km (0.91 km), Lakshmipur | y | y | y | y | y | y | 0 | 12 | -12 | 105.58 | - | -
3.3) Re-excavation Baggardona, Noakhali | y | y | n | n | n | n | 0 | 12 | -12 | - | - | -
4) Short cuts
Total Jarirdona shortcut (3.535 km) | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 5 | 10 | -5 | 266.31 | 0 | 0
Gabtali, Banshkhali, Secondary drainage | 33.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | -10 | 0 | 0 | 0
4.1) Jarirdona shortcut, 3.535km-4.535km (1 km), Lakshmipur | y | y | y | y | y | y | 0 | 10 | -10 | 107.34 | - | -
4.2) Jarirdona shortcut, 4.535km-6.035km (1.5 km), Lakshmipur | y | y | y | y | n | n | 0 | 10 | -10 | - | - | -
4.3) Jarirdona shortcut, 6.035km-7.035km (1 km), Noakhali | y | y | y | y | y | y | 15 | 10 | 5 | 158.97 | - | -
4.4) drainage channel Gabtali khal (6.5km), Noakhali | y | n | n | n | n | n | 0 | 10 | -10 | - | - | -
4.5) drainage channel Banshkhali (1.45km), Noakhali | n | n | n | n | n | n | 0 | 10 | -10 | - | - | -
4.6) improvement secondary drainage (35km), Noakhali & Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -
5) Sluices (3 nos)
Total sluices | 100 | 100 | 66.6667 | 33.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1) Gabtali Khal sluice, Lakshmipur | y | y | y | y | n | n | 0 | 0 | 0 | - | - | -
5.2) Tankir Khal sluice, Noakhali | y | y | y | n | n | n | 0 | 0 | 0 | - | - | -
5.3) Chatla Khal sluice, Noakhali | y | y | n | n | n | n | 0 | 0 | 0 | - | - | -
6) Closures (2 nos)
Total closures | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1) closure 1 (Steamer Ghat?), Noakhali | y | n | n | n | n | n | 0 | 0 | 0 | - | - | -
6.2) closure 2 (CBD-1), Noakhali | y | n | n | n | n | n | 0 | 0 | 0 | - | - | -

## Overview LGED
Table 2 - LGED | Design available (y/n) | Design concurred (y/n) | Estimate concurrence given (y/n) | Floating tender (y/n) | Contract signed (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac)
Item of work | [7 empty] | 2007-06-30
7) Bridges
Total bridges (4 nos.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.1) bridges (3 no's), Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -
7.2) bridge (20m), Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -
8) Busstand
8.1) Busstand, Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -
9) Community ponds
Total community ponds (50 nos.) | 52 | 52 | 52 | 52 | 52 | 52 | 36.8 | 40 | -3.2 | 36.7533 | 6.7816 | 6.7816
9.1) 5 ponds, Lakshmipur | y | y | y | y | y | y | 0 | 40 | -40 | 4.007 | - | -
9.2) 24 ponds, Lakshmipur & Noakhali | n | n | n | n | n | n | 0 | 40 | -40 | - | - | -
9.3) 15 ponds, LGED, Noakhali | y | y | y | y | y | y | 82.6667 | 40 | 42.6667 | 19.6449 | 0 | 0
9.4) 6 ponds, LCS, Noakhali | y | y | y | y | y | y | 100 | 40 | 60 | 13.1014 | 6.7816 | 6.7816
10) Culverts
Total box culverts (15 nos.) | 40 | 40 | 40 | 40 | 26.6667 | 26.6667 | 19 | 17.5 | 1.5 | 47.287 | 11.864 | 11.864
Total pipe culverts (15 nos.) | 80 | 80 | 80 | 80 | 46.6667 | 46.6667 | 16 | 17.5 | -1.5 | 8.3947 | 0 | 0
10.1) box culverts (2 no's), Lakshmipur | y | y | y | y | n | n | 0 | 14.8913 | -14.8913 | 0 | 0 | 0
10.2) pipe culverts (5 no's), Lakshmipur | y | y | y | y | n | n | 0 | 14.8913 | -14.8913 | 0 | 0 | 0
10.3) box culverts (4 nos), Noakhali | y | y | y | y | y | y | 71.25 | 14.8913 | 56.3587 | 47.287 | 11.864 | 11.864
10.4) pipe culverts (7 no's), Noakhali | y | y | y | y | y | y | 34.2857 | 14.8913 | 19.3944 | 8.3947 | 0 | 0
10.5) box culverts (9 nos), Noakhali & Lakshmipur | n | n | n | n | n | n | 0 | 14.8913 | -14.8913 | 0 | 0 | 0
10.6) pipe culverts (3 no's), Noakhali & Lakshmipur | n | n | n | n | n | n | 0 | 14.8913 | -14.8913 | 0 | 0 | 0
11) Cyclone shelters
Total cyclone shelters (20 nos.) | 100 | 100 | 100 | 100 | 85 | 85 | 30.95 | 33.625 | -2.675 | 946.8813 | 183.061 | 180.518
11.1) 4 cyclone shelters, Lakshmipur | y | y | y | y | y | y | 0 | 31.9293 | -31.9293 | 229.0012 | - | -
11.2) 3 cyclone shelters, Lakshmipur | y | y | y | y | n | n | 0 | 31.9293 | -31.9293 | 0 | 0 | 0
11.3) 5 cyclone shelters 2005-06, Noakhali | y | y | y | y | y | y | 64.2 | 31.9293 | 32.2707 | 267.3533 | 102.602 | 102.602
11.4) 8 cyclone shelters 2006-07, Noakhali | y | y | y | y | y | y | 37.25 | 31.9293 | 5.3207 | 450.5268 | 80.459 | 77.916
12) Roads
Total rural roads (51 km) | 77.451 | 77.451 | 77.451 | 77.451 | 61.1765 | 61.1765 | 49.9398 | 65 | -15.0602 | 90.1423 | 38.5611 | 36.4801
Total paved roads (15 km) | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.1) paved (7.5 km), Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0
12.2) rural (3 rds / 8.20 km), Lakshmipur | y | y | y | y | y | y | 73.6667 | 65 | 8.6667 | 22.48 | 8.8231 | 6.7421
12.3) rural (1 rd / 2.5 km), Lakshmipur | y | y | y | y | n | n | 0 | 65 | -65 | 0 | 0 | 0
12.4) rural (11.5 km), Lakshmipur & Noakhali | n | n | n | n | n | n | 0 | 65 | -65 | 0 | 0 | 0
12.5) paved (7.5 km), Noakhali | y | y | y | y | n | n | 0 | 0 | 0 | 0 | 0 | 0
12.6) rural (5 roads, 13.6 km) 2005-06, Noakhali | y | y | y | y | y | y | 73.74 | 65 | 8.74 | 37.9413 | 14.8947 | 14.8947
12.7) rural (4 roads, 9.4 km) 2006-07, Noakhali | y | y | y | y | y | y | 100 | 65 | 35 | 29.721 | 14.8433 | 14.8433
12.8) rural (3 roads, 5.8 km), Noakhali | y | y | y | y | n | n | 0 | 65 | -65 | 0 | 0 | 0

## Overview DPHE
Table 3 - DPHE | Design available (y/n) | Design concurred (y/n) | Estimate concurrence given (y/n) | Floating tender (y/n) | Contract signed (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac)
Item of work | [7 empty] | 2007-06-30
13) Deep tube wells
Total deep tube wells (600) | 100 | 100 | 50.3333 | 50.3333 | 50.3333 | 50.3333 | 22.6333 | 30.125 | -7.4917 | 155.11 | 34.5743 | 29.0143
13.1) deep tube wells (102 nos), Noakhali | y | y | y | y | y | y | 90 | 27.9076 | 62.0924 | 48.8266 | 34.5743 | 29.0143
13.2) deep tube wells (200 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 22 | 27.9076 | -5.9076 | 106.2834 | - | -
13.3) deep tube wells (298 nos), Noakhali & Lakshmipur | y | y | n | n | n | n | 0 | 27.9076 | -27.9076 | - | - | -
14) Pond with sand filter
Total ponds with sand filter (10 nos) | 100 | 100 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14.1) 4 ponds with sf, Lakshmipur | y | y | y | y | n | n | 0 | 0 | 0 | - | - | -
14.2) ponds with sf, Noakhali | y | y | n | n | n | n | 0 | 0 | 0 | - | - | -
15) Public toilets
Total public toilets (20 nos) | 50 | 50 | 50 | 50 | 50 | 50 | 10.9 | 11.25 | 0.35 | 62.32 | 0 | 0
15.1) public toilets (10 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 21.8 | 9.9457 | 11.8543 | 62.32 | - | -
15.2) public toilets (10 nos), Noakhali & Lakshmipur | n | n | n | n | n | n | 0 | 9.9457 | -9.9457 | - | - | -
16) Rainwater harvesting
Total rainwater harvesting (20 nos) | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16.1) rainwater harvesting (5 nos), Lakshmipur | y | y | y | y | n | n | 0 | 0 | 0 | - | - | -
16.2) rainwater harvesting (15 nos), Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -
17) Single pit latrines
Total single pit latrines (8500 nos) | 100 | 100 | 100 | 58.8235 | 58.8235 | 58.8235 | 14.3471 | 10.75 | -3.5971 | 84.912 | 0 | 0
17.1) single pit latrines (5000 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 24.39 | 7.8804 | 16.5096 | 84.912 | - | -
17.2) single pit latrines (3500 nos), Noakhali & Lakshmipur | y | y | y | n | n | n | 0 | 7.8804 | -7.8804 | - | - | -

## Overview MoL
Table 4 - MoL | Design available (y/n) | Design concurred (y/n) | Estimate concurrence given (y/n) | Floating tender (y/n) | Contract signed (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac)
Item of work | [7 empty] | 2007-06-30
18) Construction work in cluster villages
Total construction work (144 twin houses & ponds) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18.1) construction of twin houses (144 nos), Lakshmipur & Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -
18.2) construction of 3 ponds, Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -
18.3) construction of ponds, Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -
19) Settlement programme
Total rehabilitation (3000 families) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19.1) Rehabilitation, Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -
19.2) Rehabilitation, Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -

## data status
|  | Design available | Design concurred | Estimate concurred | Floating tender | Contract signed | Work order given | physical progress
bwdb | sea dyke | 100 | 100 | 100 | 100 | 73.1831 | 73.1831 | 52.3252
| interior dyke | 100 | 100 | 15 | 0 | 0 | 0 | 0
| guide dykes | 100 | 100 | 100 | 100 | 100 | 100 | 0
| re-excavations jarirdona | 100 | 100 | 69.6667 | 69.6667 | 69.6667 | 69.6667 | 0
| re-excavation bagardona | 100 | 100 | 0 | 0 | 0 | 0 | 0
| Jarirdona shortcut | 100 | 100 | 100 | 100 | 66.6667 | 66.6667 | 5
| other shortcuts | 33.3333 | 0 | 0 | 0 | 0 | 0 | 0
| Gabtali sluice | 100 | 100 | 100 | 100 | 0 | 0 | 0
| sluices | 100 | 100 | 50 | 0 | 0 | 0 | 0
| closures | 100 | 0 | 0 | 0 | 0 | 0 | 0
lged | bridges | 0 | 0 | 0 | 0 | 0 | 0 | 0
| busstand | 0 | 0 | 0 | 0 | 0 | 0 | 0
| community ponds | 52 | 52 | 52 | 52 | 52 | 52 | 36.8
| box culverts | 40 | 40 | 40 | 40 | 26.6667 | 26.6667 | 19
| pipe culverts | 80 | 80 | 80 | 80 | 46.6667 | 46.6667 | 16
| cyclone shelters | 100 | 100 | 100 | 100 | 85 | 85 | 30.95
| rural roads | 77.451 | 77.451 | 77.451 | 77.451 | 61.1765 | 61.1765 | 49.7447
| paved roads | 50 | 50 | 50 | 50 | 0 | 0 | 0
dphe | deep tube wells | 100 | 100 | 50.3333 | 50.3333 | 50.3333 | 50.3333 | 22.6333
| ponds with sand filter | 100 | 100 | 40 | 40 | 0 | 0 | 0
| public toilets | 50 | 50 | 50 | 50 | 50 | 50 | 10.9
| rainwater harvesting | 25 | 25 | 25 | 25 | 0 | 0 | 0
| single pit latrines | 100 | 100 | 100 | 58.8235 | 58.8235 | 58.8235 | 14.3471
mol | cluster villages | 0 | 0 | 0 | 0 | 0 | 0 | 0
| settlement programme | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PLANNING | table exists of planned progress for project period (and resulting necessary progress per day), which is linked to overview sheets
| March 2007 | planned | progress | planned | result from planning | result from planning | planned | planned | planned | planned | planned
|  | 2007-01-01 | 2007-06-30 | 2007-07-01 | progress per day (%) | 2007-06-30 | 2008-01-01 | 2008-07-01 | 2009-01-01 | 2009-07-01 | 2010-07-01
bwdb | sea dyke | 0 | 52.3252 | 40 | 0 | 40 | 40 | 70 | 70 | 100
| interior dyke | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 100
| re-excavations | 0 | 0 | 12 | 0 | 12 | 12 | 60 | 60 | 100
| shortcut | 0 | 5 | 10 | 0 | 10 | 10 | 60 | 60 | 100
| Gabtali sluice |  | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 100
| 5 sluices | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 100
| closures | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
| secondary drainage |  | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 100
lged | bridges | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 100
| busstand | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 100
| community ponds | 0 | 36.8 | 40 | 0 | 40 | 40 | 80 | 80 | 100
| culverts | 0 | #VALUE! | 15 | 0.1087 | 14.8913 | 35 | 75 | 75 | 100
| cyclone shelters | 0 | #VALUE! | 32 | 0.070652 | 31.9293 | 45 | 80 | 80 | 100
| unpaved roads | 0 | 49.7447 | 65 | 0 | 65 | 65 | 100 | 100 | 100
| paved roads |  | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 100
dphe | deep tube wells | 0 | 26.6275 | 28 | 0.092391 | 27.9076 | 45 | 50 | 50 | 100
| ponds with sand filter | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 100
| public toilets | 0 | 10.9 | 10 | 0.054348 | 9.9457 | 20 | 60 | 60 | 100
| rainwater harvesting | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 100
| single pit latrines | 0 | 11.0864 | 8 | 0.11957 | 7.8804 | 30 | 60 | 60 | 100
mol | cluster villages | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 100
| settlement programme | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 100
|  | 2006-07-01 | 2007-03-25 | 2007-07-01 |  | 2008-07-01: 2008-07-01; 2009-07-01: 2009-07-01; 2010-07-01: 2010-07-01
| BWDB | 0 | #DIV/0! | 7.75 |  | 2008-07-01: 48.75; 2009-07-01: 87.5; 2010-07-01: 100
| LGED | 0 | #VALUE! | 21.7143 |  | 2008-07-01: 66.4286; 2009-07-01: 100
| DPHE | 0 | 9.7228 | 9.2 |  | 2008-07-01: 54; 2009-07-01: 100
| MoL | 0 | 0 | 0 |  | 2008-07-01: 55; 2009-07-01: 100

## hulp sheet
10.1) box culverts (2 no's), Lakshmipur | y | y | y | y | n | n | 0 | 2 | 2 | 2 | 2 | 0 | 0
10.3) box culverts (4 nos), Noakhali | y | y | y | y | y | y | 71.25 | 4 | 4 | 4 | 4 | 4 | 4
10.5) box culverts (9 nos), Noakhali & Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.2) pipe culverts (5 no's), Lakshmipur | y | y | y | y | n | n | 0 | 5 | 5 | 5 | 5 | 0 | 0
10.4) pipe culverts (7 no's), Noakhali | y | y | y | y | y | y | 34.2857 | 7 | 7 | 7 | 7 | 7 | 7
10.6) pipe culverts (3 no's), Noakhali & Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.2) rural (3 rds / 8.20 km), Lakshmipur | y | y | y | y | y | y | 73.6667 | 8.2 | 8.2 | 8.2 | 8.2 | 8.2 | 8.2
12.3) rural (1 rd / 2.5 km), Lakshmipur | y | y | y | y | n | n | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0
12.4) rural (11.5 km), Lakshmipur & Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.6) rural (5 roads, 13.6 km) 2005-06, Noakhali | y | y | y | y | y | y | 73.74 | 13.6 | 13.6 | 13.6 | 13.6 | 13.6 | 13.6
12.7) rural (4 roads, 9.4 km) 2006-07, Noakhali | y | y | y | y | y | y | 100 | 9.4 | 9.4 | 9.4 | 9.4 | 9.4 | 9.4
12.8) rural (3 roads, 5.8 km), Noakhali | y | y | y | y | n | n | 0 | 5.8 | 5.8 | 5.8 | 5.8 | 0 | 0
12.1) paved (7.5 km), Lakshmipur | n | n | n | n | n | n | 0
12.5) paved (7.5 km), Noakhali | y | y | y | y | n | n | 0
9.1) 5 ponds, Lakshmipur | y | y | y | y | y | y | 0 | 5 | 5 | 5 | 5 | 5 | 5
9.2) 24 ponds, Lakshmipur & Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.3) 15 ponds, LGED, Noakhali | y | y | y | y | y | y | 82.6667 | 15 | 15 | 15 | 15 | 15 | 15
9.4) 6 ponds, LCS, Noakhali | y | y | y | y | y | y | 100 | 6 | 6 | 6 | 6 | 6 | 6
11.1) 4 cyclone shelters, Lakshmipur | y | y | y | y | y | y | 0 | 4 | 4 | 4 | 4 | 4 | 4
11.2) 3 cyclone shelters, Lakshmipur | y | y | y | y | n | n | 0 | 3 | 3 | 3 | 3 | 0 | 0
11.3) 5 cyclone shelters 2005-06, Noakhali | y | y | y | y | y | y | 64.2 | 5 | 5 | 5 | 5 | 5 | 5
11.4) 8 cyclone shelters 2006-07, Noakhali | y | y | y | y | y | y | 37.25 | 8 | 8 | 8 | 8 | 8 | 8
13.1) deep tube wells (102 nos), Noakhali | y | y | y | y | y | y | 90 | 102 | 102 | 102 | 102 | 102 | 102
13.2) deep tube wells (200 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 22 | 200 | 200 | 200 | 200 | 200 | 200
13.3) deep tube wells (298 nos), Noakhali & Lakshmipur | y | y | n | n | n | n | 0 | 298 | 298 | 0 | 0 | 0 | 0
14.1) 4 ponds with sf, Lakshmipur | y | y | y | y | n | n | 0 | 4 | 4 | 4 | 4 | 0 | 0
14.2) ponds with sf, Noakhali | y | y | n | n | n | n | 0 | 6 | 6 | 0 | 0 | 0 | 0
16.1) rainwater harvesting (5 nos), Lakshmipur | y | y | y | y | n | n | 0 | 5 | 5 | 5 | 5 | 0 | 0
16.2) rainwater harvesting (15 nos), Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.1) single pit latrines (5000 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 24.39 | 5 | 5 | 5 | 5 | 5 | 5
17.2) single pit latrines (3500 nos), Noakhali & Lakshmipur | y | y | y | n | n | n | 0 | 3.5 | 3.5 | 3.5 | 0 | 0 | 0
3.1) Re-excavation Jarirdona, 0km-2.625km (2.625 km), Lakshmipur | y | y | n | n | n | n | 0 | 0.91 | 0.91 | 0 | 0 | 0 | 0
3.2) Re-excavation Jarirdona, 2.625km-3.535km (0.91 km), Lakshmipur | y | y | y | y | y | y | 0 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09 | 2.09
3.3) Re-excavation Baggardona, Noakhali | y | y | n | n | n | n | 0 | 1 | 1 | 0 | 0 | 0 | 0
1.1) Sea dyke, 0.63km-3.365km (2.735 km), Lakshmipur | y | y | y | y | y | y | 39.3333 | 2.735 | 2.735 | 2.735 | 2.735 | 2.735 | 2.735
1.2) Sea dyke, 3.365km-5.085km (1.72 km), Lakshmipur | y | y | y | y | y | y | 64.65 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72
1.3) Sea dyke, 5.085km-8.585km (3.5 km), Noakhali | y | y | y | y | y | y | 100 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
1.4) Sea dyke, 8.585km-11.5km (2.915 km), Noakhali | y | y | y | y | n | n | 0 | 2.915 | 2.915 | 2.915 | 2.915 | 0 | 0
1.5) Interior dyke, 11.5km-13.0km (1.5 km), Noakhali | y | y | y | n | n | n | 0 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0
1.6) Interior dyke, 13.0km-21.5km (8.5 km), Noakhali | y | y | n | n | n | n | 0 | 8.5 | 8.5 | 0 | 0 | 0 | 0