## LS Progress
Month | Total field hearing (day) |  | Landless family selection (#) |  | Settlement cases started (#) |  | Jamabandi preparation (#) |  | Jamabandi approval by upazila (#) |  | Landless family approval District (#) |  | Jamabandi approval by DC (#) |  | Selami realisation (#) |  | Kabuliyat execution (#) |  | Kabuliyat registration (#) |  | Khatian preparation (#) |  | Khatian hand over (#)
| plan | achievement | plan | ach. | plan | ach. | plan | ach. | plan | ach. | plan | ach. | plan | ach. | plan | ach. | plan | ach. | plan | ach. | plan | ach. | plan | ach.
2007-05-01 | 7 | 4 | 476 | 476 | 0
2007-06-01 | 9 | 0 | 0 |  | 0
2007-07-01 | 3 | 0 | 500 |  | 476 | 462 | 300 | 462 | 300 |  | 300
2007-08-01 | 3 |  | 500 |  | 400 |  | 300 |  | 300 |  | 300 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2007-09-01 | 3 |  | 500 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 0 |  | 0 |  | 0
2007-10-01 | 3 |  | 500 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 0 |  | 0
2007-11-01 | 3 |  | 500 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2007-12-01 | 3 |  | 500 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2008-01-01 | 3 |  | 500 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 300 |  | 300
2008-02-01 | 3 |  | 500 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2008-03-01 | 3 |  | 500 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2008-04-01 | 3 |  | 500 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2008-05-01 | 3 |  | 500 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2008-06-01 | 3 |  | 500 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2008-07-01 |  |  | 500 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2008-08-01 |  |  | 500 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2008-09-01 |  |  | 500 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2008-10-01 |  |  | 500 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2008-11-01 |  |  | 500 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2008-12-01 |  |  | 524 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2009-01-01 |  |  |  |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2009-02-01 |  |  |  |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2009-03-01 |  |  |  |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2009-04-01 |  |  |  |  | 512 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2009-05-01 |  |  |  |  | 512 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2009-06-01 | [6 empty] | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2009-07-01 | [6 empty] | 250 |  | 250 |  | 250 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2009-08-01 | [6 empty] | 250 |  | 250 |  | 250 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400 |  | 400
2009-09-01 | [12 empty] | 300 |  | 300 |  | 300 |  | 400 |  | 400 |  | 400
Total (#) | 52 | 4 | 9500 | 476 | 9500 | 462 | 9500 | 462 | 9500 | 0 | 9500 | 0 | 9500 | 0 | 9500 | 0 | 9500 | 0 | 9300 | 0 | 8900 | 0 | 8900 | 0

## LS hulp
month | total field hearing (day) |  |  |  | landless family selection (#) |  |  |  | settlement cases started (#) |  |  |  | jamabandi preparation (#) |  |  |  | jamabandi approval by upazila (#) |  |  |  | Landless family approval by District committee (#) |  |  |  | jamabandi approval by DC (#) |  |  |  | Selami realisation (#) |  |  |  | kabuliyat execution (#) |  |  |  | kabuliyat registration (#) |  |  |  | khatian preparation (#) |  |  | khatian hand over (#)
| plan | plan cumm. | achievement | achieved cumm. | plan | plan cumm. | achievement | achieved cumm. | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement |  | plan | achievement |  | plan |  | achievement
2007-05-01 | 7 | 7 | 4 | 4 | 476 | 476 | 476 | 476 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0
2007-06-01 | 9 | 16 | 0 | 4 | 0 | 476 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0
2007-07-01 | 3 | 19 | 0 | 4 | 500 | 976 |  | 0 | 476 | 476 | 462 | 462 | 300 | 300 | 462 | 462 | 300 | 300 |  | 0 | 300 | 300 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0
2007-08-01 | 3 | 22 |  | 0 | 500 | 1476 |  | 0 | 400 | 876 |  | 0 | 300 | 600 |  | 0 | 300 | 600 |  | 0 | 300 | 600 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0
2007-09-01 | 3 | 25 |  | 0 | 500 | 1976 |  | 0 | 400 | 1276 |  | 0 | 300 | 900 |  | 0 | 300 | 900 |  | 0 | 300 | 900 |  | 0 | 300 | 300 |  | 0 | 300 | 300 |  | 0 | 300 | 300 |  | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0
2007-10-01 | 3 | 28 |  | 0 | 500 | 2476 |  | 0 | 400 | 1676 |  | 0 | 300 | 1200 |  | 0 | 300 | 1200 |  | 0 | 300 | 1200 |  | 0 | 300 | 600 |  | 0 | 300 | 600 |  | 0 | 300 | 600 |  | 0 | 300 | 300 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0
2007-11-01 | 3 | 31 |  | 0 | 500 | 2976 |  | 0 | 400 | 2076 |  | 0 | 300 | 1500 |  | 0 | 300 | 1500 |  | 0 | 300 | 1500 |  | 0 | 300 | 900 |  | 0 | 300 | 900 |  | 0 | 300 | 900 |  | 0 | 300 | 600 |  | 0 | 300 |  | 0 | 300 | 300 |  | 0
2007-12-01 | 3 | 34 |  | 0 | 500 | 3476 |  | 0 | 400 | 2476 |  | 0 | 300 | 1800 |  | 0 | 300 | 1800 |  | 0 | 300 | 1800 |  | 0 | 300 | 1200 |  | 0 | 300 | 1200 |  | 0 | 300 | 1200 |  | 0 | 300 | 900 |  | 0 | 300 |  | 0 | 300 | 600 |  | 0
2008-01-01 | 3 | 37 |  | 0 | 500 | 3976 |  | 0 | 400 | 2876 |  | 0 | 400 | 2200 |  | 0 | 400 | 2200 |  | 0 | 400 | 2200 |  | 0 | 400 | 1600 |  | 0 | 400 | 1600 |  | 0 | 400 | 1600 |  | 0 | 400 | 1300 |  | 0 | 300 |  | 0 | 300 | 900 |  | 0
2008-02-01 | 3 | 40 |  | 0 | 500 | 4476 |  | 0 | 400 | 3276 |  | 0 | 400 | 2600 |  | 0 | 400 | 2600 |  | 0 | 400 | 2600 |  | 0 | 400 | 2000 |  | 0 | 400 | 2000 |  | 0 | 400 | 2000 |  | 0 | 400 | 1700 |  | 0 | 400 |  | 0 | 400 | 1300 |  | 0
2008-03-01 | 3 | 43 |  | 0 | 500 | 4976 |  | 0 | 400 | 3676 |  | 0 | 400 | 3000 |  | 0 | 400 | 3000 |  | 0 | 400 | 3000 |  | 0 | 400 | 2400 |  | 0 | 400 | 2400 |  | 0 | 400 | 2400 |  | 0 | 400 | 2100 |  | 0 | 400 |  | 0 | 400 | 1700 |  | 0
2008-04-01 | 3 | 46 |  | 0 | 500 | 5476 |  | 0 | 400 | 4076 |  | 0 | 400 | 3400 |  | 0 | 400 | 3400 |  | 0 | 400 | 3400 |  | 0 | 400 | 2800 |  | 0 | 400 | 2800 |  | 0 | 400 | 2800 |  | 0 | 400 | 2500 |  | 0 | 400 |  | 0 | 400 | 2100 |  | 0
2008-05-01 | 3 | 49 |  | 0 | 500 | 5976 |  | 0 | 400 | 4476 |  | 0 | 400 | 3800 |  | 0 | 400 | 3800 |  | 0 | 400 | 3800 |  | 0 | 400 | 3200 |  | 0 | 400 | 3200 |  | 0 | 400 | 3200 |  | 0 | 400 | 2900 |  | 0 | 400 |  | 0 | 400 | 2500 |  | 0
2008-06-01 | 3 | 52 |  | 0 | 500 | 6476 |  | 0 | 400 | 4876 |  | 0 | 400 | 4200 |  | 0 | 400 | 4200 |  | 0 | 400 | 4200 |  | 0 | 400 | 3600 |  | 0 | 400 | 3600 |  | 0 | 400 | 3600 |  | 0 | 400 | 3300 |  | 0 | 400 |  | 0 | 400 | 2900 |  | 0
2008-07-01 |  | 52 |  | 0 | 500 | 6976 |  | 0 | 400 | 5276 |  | 0 | 400 | 4600 |  | 0 | 400 | 4600 |  | 0 | 400 | 4600 |  | 0 | 400 | 4000 |  | 0 | 400 | 4000 |  | 0 | 400 | 4000 |  | 0 | 400 | 3700 |  | 0 | 400 |  | 0 | 400 | 3300 |  | 0
2008-08-01 |  | 52 |  | 0 | 500 | 7476 |  | 0 | 400 | 5676 |  | 0 | 400 | 5000 |  | 0 | 400 | 5000 |  | 0 | 400 | 5000 |  | 0 | 400 | 4400 |  | 0 | 400 | 4400 |  | 0 | 400 | 4400 |  | 0 | 400 | 4100 |  | 0 | 400 |  | 0 | 400 | 3700 |  | 0
2008-09-01 |  | 52 |  | 0 | 500 | 7976 |  | 0 | 400 | 6076 |  | 0 | 400 | 5400 |  | 0 | 400 | 5400 |  | 0 | 400 | 5400 |  | 0 | 400 | 4800 |  | 0 | 400 | 4800 |  | 0 | 400 | 4800 |  | 0 | 400 | 4500 |  | 0 | 400 |  | 0 | 400 | 4100 |  | 0
2008-10-01 |  | 52 |  | 0 | 500 | 8476 |  | 0 | 400 | 6476 |  | 0 | 400 | 5800 |  | 0 | 400 | 5800 |  | 0 | 400 | 5800 |  | 0 | 400 | 5200 |  | 0 | 400 | 5200 |  | 0 | 400 | 5200 |  | 0 | 400 | 4900 |  | 0 | 400 |  | 0 | 400 | 4500 |  | 0
2008-11-01 |  | 52 |  | 0 | 500 | 8976 |  | 0 | 400 | 6876 |  | 0 | 400 | 6200 |  | 0 | 400 | 6200 |  | 0 | 400 | 6200 |  | 0 | 400 | 5600 |  | 0 | 400 | 5600 |  | 0 | 400 | 5600 |  | 0 | 400 | 5300 |  | 0 | 400 |  | 0 | 400 | 4900 |  | 0
2008-12-01 |  | 52 |  | 0 | 524 | 9500 |  | 0 | 400 | 7276 |  | 0 | 400 | 6600 |  | 0 | 400 | 6600 |  | 0 | 400 | 6600 |  | 0 | 400 | 6000 |  | 0 | 400 | 6000 |  | 0 | 400 | 6000 |  | 0 | 400 | 5700 |  | 0 | 400 |  | 0 | 400 | 5300 |  | 0
2009-01-01 |  | 52 |  | 0 | 0 | 9500 |  | 0 | 400 | 7676 |  | 0 | 400 | 7000 |  | 0 | 400 | 7000 |  | 0 | 400 | 7000 |  | 0 | 400 | 6400 |  | 0 | 400 | 6400 |  | 0 | 400 | 6400 |  | 0 | 400 | 6100 |  | 0 | 400 |  | 0 | 400 | 5700 |  | 0
2009-02-01 |  | 52 |  | 0 | 0 | 9500 |  | 0 | 400 | 8076 |  | 0 | 400 | 7400 |  | 0 | 400 | 7400 |  | 0 | 400 | 7400 |  | 0 | 400 | 6800 |  | 0 | 400 | 6800 |  | 0 | 400 | 6800 |  | 0 | 400 | 6500 |  | 0 | 400 |  | 0 | 400 | 6100 |  | 0
2009-03-01 |  | 52 |  | 0 | 0 | 9500 |  | 0 | 400 | 8476 |  | 0 | 400 | 7800 |  | 0 | 400 | 7800 |  | 0 | 400 | 7800 |  | 0 | 400 | 7200 |  | 0 | 400 | 7200 |  | 0 | 400 | 7200 |  | 0 | 400 | 6900 |  | 0 | 400 |  | 0 | 400 | 6500 |  | 0
2009-04-01 |  | 52 |  | 0 | 0 | 9500 |  | 0 | 512 | 8988 |  | 0 | 400 | 8200 |  | 0 | 400 | 8200 |  | 0 | 400 | 8200 |  | 0 | 400 | 7600 |  | 0 | 400 | 7600 |  | 0 | 400 | 7600 |  | 0 | 400 | 7300 |  | 0 | 400 |  | 0 | 400 | 6900 |  | 0
2009-05-01 |  | 52 |  | 0 | 0 | 9500 |  | 0 | 512 | 9500 |  | 0 | 400 | 8600 |  | 0 | 400 | 8600 |  | 0 | 400 | 8600 |  | 0 | 400 | 8000 |  | 0 | 400 | 8000 |  | 0 | 400 | 8000 |  | 0 | 400 | 7700 |  | 0 | 400 |  | 0 | 400 | 7300 |  | 0
2009-06-01 |  | 52 |  | 0 | 0 | 9500 |  | 0 | 0 | 9500 |  | 0 | 400 | 9000 |  | 0 | 400 | 9000 |  | 0 | 400 | 9000 |  | 0 | 400 | 8400 |  | 0 | 400 | 8400 |  | 0 | 400 | 8400 |  | 0 | 400 | 8100 |  | 0 | 400 |  | 0 | 400 | 7700 |  | 0
2009-07-01 |  | 52 |  | 0 | 0 | 9500 |  | 0 | 0 | 9500 |  | 0 | 250 | 9250 |  | 0 | 250 | 9250 |  | 0 | 250 | 9250 |  | 0 | 400 | 8800 |  | 0 | 400 | 8800 |  | 0 | 400 | 8800 |  | 0 | 400 | 8500 |  | 0 | 400 |  | 0 | 400 | 8100 |  | 0
2009-08-01 |  | 52 |  | 0 | 0 | 9500 |  | 0 | 0 | 9500 |  | 0 | 250 | 9500 |  | 0 | 250 | 9500 |  | 0 | 250 | 9500 |  | 0 | 400 | 9200 |  | 0 | 400 | 9200 |  | 0 | 400 | 9200 |  | 0 | 400 | 8900 |  | 0 | 400 |  | 0 | 400 | 8500 |  | 0
2009-09-01 |  | 52 |  | 0 | 0 | 9500 |  | 0 | 0 | 9500 |  | 0 | 0 | 9500 |  | 0 | 0 | 9500 |  | 0 | 0 | 9500 |  | 0 | 300 | 9500 |  | 0 | 300 | 9500 |  | 0 | 300 | 9500 |  | 0 | 400 | 9300 |  | 0 | 400 |  | 0 | 400 | 8900 |  | 0
Total (#) | 52 |  | 4 |  | 9500 |  | 476 |  | 9500 |  | 462 |  | 9500 |  | 462 |  | 9500 |  |  |  | 9500 |  |  |  | 9500 |  |  |  | 9500 |  |  |  | 9500 |  |  |  | 9300 |  |  |  | 8900 |  |  | 8900
Total achievement (%) |  |  | 7.6923 |  |  |  | 5.0105 |  |  |  | 4.8632 |  |  |  | 4.8632 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0

## LS hulp 2
month: | 2007-08-01
month | total field hearing (day) |  | landless family selection (#) |  | settlement cases started (#) |  | Jamabandi preparation (#) |  | Jamabandi approval by upazila (#) |  | Landless family approval by District committee (#) |  | jamabandi approval by DC (#) |  | Selami execution (#) |  | kabuliyat execution (#) |  | kabuliyat registration (#) |  | khatian preparation (#) |  | khatian hand over (#)
| plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement
Total | 52 | 4 | 9500 | 476 | 9500 | 462 | 9500 | 462 | 9500 | 0 | 9500 | 0 | 9500 | 0 | 9500 | 0 | 9500 | 0 | 9300 | 0 | 8900 | 0 | 8900 | 0
current total | 22 | 0 | 1476 | 0 | 876 | 0 | 600 | 0 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| plan end of project | current achievement | current plan
total field hearing (day) | 52 | 4 | 22
landless family selection | 9500 | 476 | 1476
settlement cases started | 9500 | 462 | 876
jamabandi preparation | 9500 | 462 | 600
Jamabandi approval upazila | 9500 | 462 | 600
Landless family approval | 9500 | 0 | 600
jamabandi approval by DC | 9500 | 0 | 0
Selami execution | 9500 | 0 | 0
kabuliyat execution | 9500 | 0 | 0
kabuliyat registration | 9300 | 0 | 0
khatian preparation | 8900 | 0 | 0
khatian hand over | 8900 | 0 | 0