## Overview BWDB
Table 1 - BWDB | Design available (y/n) | Design concurred (y/n) | Estimate concurrence given (y/n) | Floating tender (y/n) | Contract signed (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac)
Item of work | [7 empty] | 2007-12-31
Total BWDB | 83.3333 | 77.7778 | 77.7778 | 77.7778 | 25.9832 | 25.9832 | 6.7252 | 12.1123 | -5.3871 | 1050.7609 | 235.15 | 235.15
1) Embankments
Total sea dyke (10.87 km) | 100 | 100 | 100 | 100 | 73.1831 | 73.1831 | 52.3252 | 60 | -7.6748 | 333.0042 | 217.41 | 217.41
Total interior dyke (8 km) | 100 | 100 | 100 | 100 | 0 | 0 | 0 | -0.32967 | 0.32967 | 0 | 0 | 0
1.1) Sea dyke, 0.63km-3.365km (2.735 km), Lakshmipur | y | y | y | y | y | y | 39.3333 | 39.7569 | -0.42358 | 102.01 | 32.25 | 32.25
1.2) Sea dyke, 3.365km-5.085km (1.72 km), Lakshmipur | y | y | y | y | y | y | 64.65 | 39.7569 | 24.8931 | 76.12 | 40.02 | 40.02
1.3) Sea dyke, 5.085km-8.585km (3.5 km), Noakhali | y | y | y | y | y | y | 100 | 39.7569 | 60.2431 | 154.8742 | 145.14 | 145.14
1.4) Sea dyke, 8.585km-11.5km (2.915 km), Noakhali | y | y | y | y | n | n | 0 | 39.7569 | -39.7569 | - | - | -
1.5) Interior dyke, 11.5km-19.5km (8 km), Noakhali | y | y | y | y | n | n | 0 | -0.32967 | 0.32967 | - | - | -
2) Individual guide dyke
Total guide dyke (2.965 km) | 100 | 100 | 100 | 100 | 73.0185 | 73.0185 | 2.7852 | -0.43956 | 3.2248 | 53.03 | 0 | 0
2.1) Guide dyke cum rural road, 7.035km-9.2km (2.165 km), Noakhali | y | y | y | y | y | y | 5.5704 | -0.43956 | 6.01 | 53.03 | - | -
2.2) Guide dyke cum rural road, 9.2km-10.00km (0.80 km), Noakhali | y | y | y | y | n | n | 0 | -0.43956 | 0.43956 | 0 | - | -
3) Re-excavations
Total Jarirdona (3.535 km) | 100 | 100 | 100 | 100 | 25.7426 | 25.7426 | 0 | 30 | -30 | 105.58 | 0 | 0
Total Bagardona (10 km) | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1) Re-excavation Jarirdona, 0km-2.625km (2.625 km), Lakshmipur | y | y | y | y | n | n | 0 | 9.7018 | -9.7018 | - | - | -
3.2) Re-excavation Jarirdona, 2.625km-3.535km (0.91 km), Lakshmipur | y | y | y | y | y | y | 0 | 9.7018 | -9.7018 | 105.58 | - | -
3.3) Re-excavation Baggardona, 7.035km-13.935km (6.9 km), Noakhali | y | y | y | y | n | n | 0 | 0 | 0 | - | - | -
3.4) Re-excavation Baggardona, 13.935km-17.035km (3.1 km), Lakshmipur | y | y | y | y | n | n | 0 | 0 | 0 | - | - | -
4) Short cuts
Total Jarirdona shortcut (3.5 km) | 100 | 100 | 100 | 100 | 28.5714 | 28.5714 | 8.8333 | 60 | -51.1667 | 158.97 | 17.74 | 17.74
Gabtali khal (6.155 km) | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | - | - | -
Secondary drainage (21 km) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.21978 | 0.21978 | - | - | -
4.1) Jarirdona shortcut, 3.535km-4.535km (1 km), Lakshmipur | y | y | y | y | n | n | 0 | 9.7018 | -9.7018 | 0 | - | -
4.2) Jarirdona shortcut, 4.535km-6.035km (1.5 km), Lakshmipur | y | y | y | y | n | n | 0 | 9.7018 | -9.7018 | - | - | -
4.3) Jarirdona shortcut, 6.035km-7.035km (1 km), Noakhali | y | y | y | y | y | y | 26.5 | 9.7018 | 16.7982 | 158.97 | 17.74 | 17.74
4.4) drainage channel Gabtali khal (6.155km), Lakshmipur | y | y | y | y | n | n | 0 | 9.7018 | -9.7018 | - | - | -
4.6) improvement secondary drainage (21km), Noakhali & Lakshmipur | n | n | n | n | n | n | 0 | -0.21978 | 0.21978 | - | - | -
5) Sluices (3 nos)
Total sluices | 100 | 100 | 100 | 100 | 33.3333 | 33.3333 | 0.33333 | 10 | -9.6667 | 400.1768 | 0 | 0
5.1) Gabtali Khal sluice, Lakshmipur | y | y | y | y | y | y | 1 | 10 | -9 | 400.1768 | - | -
5.2) Tankir Khal sluice, Noakhali | y | y | y | y | n | n | 0 | 10 | -10 | - | - | -
5.3) Chatla Khal sluice, Noakhali | y | y | y | y | n | n | 0 | 10 | -10 | - | - | -
6) Closures (2 nos)
Total closures | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1) closure 1 (Downstream Banshkhali), Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -
6.2) closure 2 (CBD-1), Noakhali | y | n | n | n | n | n | 0 | 0 | 0 | - | - | -

## Overview LGED
Table 2 - LGED | Design available (y/n) | Design concurred (y/n) | Estimate concurrence given (y/n) | Floating tender (y/n) | Contract signed (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac)
Item of work | [7 empty] | 2007-12-31
Total LGED | 89.5681 | 74.2394 | 74.2394 | 61.0401 | 41.244 | 41.244 | 20.3611 | 32.1456 | -11.7845 | 1673.6411 | 502.0237 | 478.7937
7) Bridges | 100 | 100 | 100 | 0 | 0 | 0
7.1) bridges (3 no's), Noakhali | y | y | y | n | n | n | 0 | 20 | -20 | - | - | -
8) Busstand | 100 | 0 | 0 | 0 | 0 | 0
8.1) Busstand, Noakhali | y | n | n | n | n | n | 0 | 10 | -10 | - | - | -
9) Community ponds
Total community ponds (50 nos.) | 96 | 94 | 94 | 94 | 52 | 52 | 36.8 | 50 | -13.2 | 36.7533 | 22.96 | 20.76
9.1) 5 ponds, Lakshmipur | y | y | y | y | y | y | 0 | 50 | -50 | 4.007 | - | -
9.2) 13 ponds, Lakshmipur (4 LCS) | y | y | y | y | n | n | 0 | 50 | -50 | - | - | -
9.3) 2 ponds, Lakshmipur | n | n | n | n | n | n | 0 | 50 | -50 | - | - | -
9.4) 15 ponds, LGED, Noakhali | y | y | y | y | y | y | 82.6667 | 50 | 32.6667 | 19.6449 | 12.12 | 11.93
9.5) 6 ponds, LCS, Noakhali | y | y | y | y | y | y | 100 | 50 | 50 | 13.1014 | 10.84 | 8.83
9.6) 8 ponds, Noakhali | y | y | y | y | n | n | 0 | 50 | -50 | - | - | -
9.7) 1 pond, Noakhali | y | n | n | n | n | n | 0 | 50 | -50 | - | - | -
10) Culverts
Total box culverts (28 nos.) | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 32.1429 | 32.1429 | 13.75 | 37.5 | -23.75 | 67.557 | 33.42 | 31.09
Total pipe culverts (38 nos.) | 69.4444 | 69.4444 | 69.4444 | 69.4444 | 36.1111 | 36.1111 | 13.6842 | 9.6644 | 4.0198 | 12.7187 | 1.9087 | 1.9087
10.1) box culverts (2 no's), Lakshmipur | y | y | y | y | y | y | 0 | 37.5 | -37.5 | 20.27 | 0 | 0
10.2) box culverts (5 no's), Lakshmipur | n | n | n | n | n | n | 0 | 37.5 | -37.5 | 0 | 0 | 0
10.3) box culverts (7 nos), Noakhali | y | y | y | y | y | y | 55 | 37.5 | 17.5 | 47.287 | 33.42 | 31.09
10.4) box culverts (7 nos), Noakhali | y | y | y | y | n | n | 0 | 37.5 | -37.5 | 0 | 0 | 0
10.5) box culverts (7 nos), Noakhali | n | n | n | n | n | n | 0 | 37.5 | -37.5 | 0 | 0 | 0
10.6) pipe culverts (5 no's), Lakshmipur | y | y | y | y | y | y | 0 | 9.6644 | -9.6644 | 4.324 | 0 | 0
10.7) pipe culverts (2 no's), Lakshmipur | n | n | n | n | n | n | 0 | 9.6644 | -9.6644 | 0 | 0 | 0
10.8) pipe culverts (8 no's), Noakhali | y | y | y | y | y | y | 65 | 9.6644 | 55.3356 | 8.3947 | 1.9087 | 1.9087
10.9) pipe culverts (12 nos), Noakhali | y | y | y | y | n | n | 0 | 9.6644 | -9.6644 | 0 | 0 | 0
10.10) pipe culverts (11 nos), Noakhali | n | n | n | n | n | n | 0 | 9.6644 | -9.6644 | 0 | 0 | 0
11) Cyclone shelters
Total cyclone shelters (20 nos.) | 100 | 100 | 100 | 100 | 100 | 100 | 48.8 | 40 | 8.8 | 1117.33 | 372.94 | 357.31
11.1) 7 cyclone shelters, Lakshmipur | y | y | y | y | y | y | 0.57143 | 40 | -39.4286 | 399.45 | - | -
11.2) 13 cyclone shelters, Noakhali | y | y | y | y | y | y | 74.7692 | 40 | 34.7692 | 717.88 | 372.94 | 357.31
11.3) Field raising near cyclone shelters (7 nos), Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0
11.4) Field raising near cyclone shelters (13 nos), Noakhali | y | y | y | y | n | n | 0 | 0 | 0 | 0 | 0 | 0
12) Roads
Total rural roads (55 km) | 100 | 79.3706 | 79.3706 | 73.7762 | 69.0559 | 69.0559 | 47.769 | 70 | -22.231 | 132.9121 | 70.795 | 67.725
Total paved roads (18.7 km) | 93.9572 | 93.9572 | 93.9572 | 93.9572 | 40.6417 | 40.6417 | 2.0856 | 20 | -17.9144 | 306.37 | 0 | 0
12.1) paved (7 km), Lakshmipur | y | y | y | y | n | n | 0 | 20 | -20 | 0 | 0 | 0
12.2) paved (5 km), Noakhali | y | y | y | y | y | y | 0 | 20 | -20 | 206.61 | 0 | 0
12.3) paved (2.6 km), Noakhali | y | y | y | y | y | y | 15 | 20 | -5 | 99.76 | 0 | 0
12.4) paved (2.97 km), Noakhali | y | y | y | y | n | n | 0 | 20 | -20 | 0 | 0 | 0
12.5) paved (1.13 km), Noakhali | n | n | n | n | n | n | 0 | 20 | -20 | 0 | 0 | 0
12.6) rural (3 roads, 8.2 km), Lakshmipur | y | y | y | y | y | y | 73.6667 | 70 | 3.6667 | 22.48 | 11.362 | 9.282
12.7) rural (1 road, 2.5 km), Lakshmipur | y | y | y | y | y | y | 0 | 70 | -70 | 8.01 | 0 | 0
12.8) rural (11.8 km), Lakshmipur | y | n | n | n | n | n | 0 | 70 | -70 | 0 | 0 | 0
12.9) rural (12 roads, 28.8 km), Noakhali | y | y | y | y | y | y | 73.9 | 70 | 3.9 | 102.4221 | 59.433 | 58.443
12.10) rural (3.2 km), Noakhali | y | y | y | n | n | n | 0 | 70 | -70 | 0 | 0 | 0
12.11) Earthen road for cyclone shelter approach (2.7 km), Noakhali | y | y | y | y | n | n | 0 | 0 | 0 | 0 | 0 | 0

## Overview DPHE
Table 3 - DPHE | Design available (y/n) | Design concurred (y/n) | Estimate concurrence given (y/n) | Floating tender (y/n) | Contract signed (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac)
Item of work | [7 empty] | 2007-12-31
Total DPHE | 100 | 100 | 86.1176 | 86.1176 | 58.7647 | 58.7647 | 21.2928 | 37.4 | -16.1072 | 338.122 | 168.14 | 111.75
13) Deep tube wells
Total deep tube wells (600) | 100 | 100 | 60 | 60 | 60 | 60 | 38.4833 | 50 | -11.5167 | 155.11 | 91.64 | 71.58
13.1) deep tube wells (102 nos), Noakhali | y | y | y | y | y | y | 90 | 50 | 40 | 48.8266 | 45.11 | 37.9
13.2) deep tube wells (200 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 69.55 | 50 | 19.55 | 106.2834 | 46.53 | 33.68
13.3) deep tube wells (58 nos), Noakhali & Lakshmipur | y | y | y | y | y | y | 0 | 50 | -50 | - | - | -
13.4) deep tube wells (240 nos), Noakhali & Lakshmipur | y | y | n | n | n | n | 0 | 50 | -50 | - | - | -
13.5) test deep tube wells (4 nos), Noakhali & Lakshmipur | y | y | y | y | n | n | 0 | 0 | 0 | - | - | -
13.6) test deep tube wells 2 (4 nos), Noakhali & Lakshmipur | y | y | y | n | n | n | 0 | 0 | 0 | - | - | -
14) Pond with sand filter
14.1) 10 ponds with sf, Lakshmipur | y | y | y | y | n | n | 0 | 40 | -40 | - | - | -
15) Public toilets
Total public toilets (20 nos) | 100 | 100 | 100 | 100 | 75 | 75 | 32.9 | 50 | -17.1 | 95.1 | 28.3 | 14.7
15.1) public toilets (10 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 56.8 | 50 | 6.8 | 62.32 | 28.3 | 14.7
15.2) public toilets (5 nos), Noakhali & Lakshmipur | y | y | y | y | y | y | 9 | 50 | -41 | 32.78 | - | -
15.3) public toilets (5 nos), Noakhali & Lakshmipur | y | y | y | y | n | n | 0 | 50 | -50 | - | - | -
16) Rainwater harvesting
16.1) rainwater harvesting (18 nos), Lakshmipur | y | y | y | y | y | y | 0 | 22 | -22 | 3 | - | -
17) Single pit latrines
Total single pit latrines (8500 nos) | 100 | 100 | 70.5882 | 70.5882 | 58.8235 | 58.8235 | 35.0808 | 25 | 10.0808 | 84.912 | 48.2 | 25.47
17.1) single pit latrines (5000 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 59.6374 | 25 | 34.6374 | 84.912 | 48.2 | 25.47
17.2) single pit latrines (1000 nos), Noakhali & Lakshmipur | y | y | y | y | n | n | 0 | 25 | -25 | - | - | -
17.3) single pit latrines (2500 nos), Noakhali & Lakshmipur | y | y | n | n | n | n | 0 | 25 | -25 | - | - | -

## Overview MoL
Table 4 - MoL | Design available (y/n) | Design concurred (y/n) | Estimate concurrence given (y/n) | Floating tender (y/n) | Contract signed (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac)
Item of work | [7 empty] | 2007-12-31
Total MoL | 84.7222 | 84.7222 | 69.4444 | 50 | 0 | 0 | 0.34722 | 20 | -19.6528 | 0 | 0 | 0
18) Construction work in cluster villages
Total construction work (144 twin houses & 9 ponds) | 100 | 100 | NA | 100 | 0 | 0 | 0 | 40 | -40 | 0 | 0 | 0
18.1) construction of twin houses (96 nos), Lakshmipur & Noakhali | y | y | NA | y | n | n | 0 | 40 | -40 | - | - | -
18.2) construction of 6 ponds, Lakshmipur & Noakhali | y | y | NA | y | n | n | 0 | 40 | -40 | - | - | -
19) Settlement programme
Total rehabilitation (1100 families), with 36 ponds | 69.4444 | 69.4444 | 69.4444 | 0 | 0 | 0 | 0.69444 | 0 | 0.69444 | 0 | 0 | 0
19.1) Rehabilitation, 25 cv with ponds only, Noakhali and Lakshmipur | y | y | y | n | n | n | 1 | 0 | 1 | - | - | -
19.2) Rehabilitation, 11 cv with ponds only, Noakhali and Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | - | - | -

## data status
|  | Design available | Design concurred | Estimate concurred | Floating tender | Contract signed | Work order given | physical progress
bwdb | sea dyke | 100 | 100 | 100 | 100 | 73.1831 | 73.1831 | 52.3252
| interior dyke | 100 | 100 | 100 | 100 | 0 | 0 | 0
| guide dykes | 100 | 100 | 100 | 100 | 73.0185 | 73.0185 | 2.7852
| re-excavations jarirdona | 100 | 100 | 100 | 100 | 25.7426 | 25.7426 | 0
| re-excavation bagardona | 100 | 100 | 100 | 100 | 0 | 0 | 0
| Jarirdona shortcut | 100 | 100 | 100 | 100 | 28.5714 | 28.5714 | 8.8333
| other shortcuts | 50 | 50 | 50 | 50 | 0 | 0 | 0
| Gabtali sluice | 100 | 100 | 100 | 100 | 100 | 100 | 1
| 2 sluices | 100 | 100 | 100 | 100 | 0 | 0 | 0
| closures | 50 | 0 | 0 | 0 | 0 | 0 | 0
lged | bridges | 100 | 100 | 100 | 0 | 0 | 0 | 0
| busstand | 100 | 0 | 0 | 0 | 0 | 0 | 0
| community ponds | 96 | 94 | 94 | 94 | 52 | 52 | 36.8
| box culverts | 57.1429 | 57.1429 | 57.1429 | 57.1429 | 32.1429 | 32.1429 | 13.75
| pipe culverts | 69.4444 | 69.4444 | 69.4444 | 69.4444 | 36.1111 | 36.1111 | 13.6842
| cyclone shelters | 100 | 100 | 100 | 100 | 100 | 100 | 48.8
| rural roads | 100 | 79.3706 | 79.3706 | 73.7762 | 69.0559 | 69.0559 | 47.769
| paved roads | 93.9572 | 93.9572 | 93.9572 | 93.9572 | 40.6417 | 40.6417 | 2.0856
dphe | deep tube wells | 100 | 100 | 60 | 60 | 60 | 60 | 38.4833
| ponds with sand filter | 100 | 100 | 100 | 100 | 0 | 0 | 0
| public toilets | 100 | 100 | 100 | 100 | 75 | 75 | 32.9
| rainwater harvesting | 100 | 100 | 100 | 100 | 100 | 100 | 0
| single pit latrines | 100 | 100 | 70.5882 | 70.5882 | 58.8235 | 58.8235 | 35.0808
mol | twin houses | 100 | 100 | NA | 100 | 0 | 0 | 0
| community ponds | 100 | 100 | NA | 100 | 0 | 0 | 0
| settlement programme | 69.4444 | 69.4444 | 69.4444 | 0 | 0 | 0 | 0.69444
| PLANNING | table exists of planned progress for project period (and resulting necessary progress per day), which is linked to overview sheets
| March 2007 | planned | progress | planned | planned | result from planning | result from planning | planned | planned | planned | planned
|  | 2007-01-01 | 2007-12-31 | 2007-07-01 | 2008-01-01 | progress per day (%) | 2007-12-31 | 2008-07-01 | 2009-01-01 | 2009-07-01 | 2010-07-01
bwdb | sea dyke | 0 | 52.3252 | 40 | 40 | 0.24308 | 39.7569 | 84.241 | 90.7797 | 100
| interior dyke | 0 | 0 | 0 | 0 | 0.32967 | -0.32967 | 60 | 75 | 100
| re-excavations jarirdona | 0 | 0 | 10 | 10 | 0.29816 | 9.7018 | 64.2644 | 80 | 100
| re-excavation bagardona | 0 | 0 | 12 | 12 | 0.26374 | 11.7363 | 60 | 70 | 100
| shortcut | 0 | 8.8333 | 10 | 10 | 0.29816 | 9.7018 | 64.2644 | 80 | 100
| Gabtali sluice | 0 | 1 | 0 | 0 | 0.27473 | -0.27473 | 50 | 70 | 100
| 2 sluices | 0 | 0 | 0 | 0 | 0.27473 | -0.27473 | 50 | 75 | 100
| closures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
| secondary drainage | 0 | 0 | 0 | 0 | 0.21978 | -0.21978 | 40 | 40 | 100
| Individual guide dyke | 0 | 4.0675 | 0 | 0 | 0.43956 | -0.43956 | 80 | 90 | 100
lged | bridges | 0 | 0 | 0 | 0 | 0.32967 | -0.32967 | 60 | 80 | 100
| busstand | 0 | 0 | 0 | 0 | 0.32967 | -0.32967 | 60 | 80 | 100
| community ponds | 0 | 36.8 | 40 | 40 | 0.28022 | 39.7198 | 91 | 100 | 100
| culverts | 0 | 13.7121 | 8 | 10 | 0.33556 | 9.6644 | 71.0714 | 85.7143 | 100
| cyclone shelters | 0 | 48.8 | 33 | 45 | 0.20879 | 44.7912 | 83 | 92.25 | 100
| unpaved roads | 0 | 47.769 | 66 | 66 | 0.10729 | 65.8927 | 85.5273 | 94.3636 | 100
| paved roads | 0 | 2.0856 | 0 | 0 | 0.37786 | -0.37786 | 68.7701 | 80.6417 | 100
dphe | deep tube wells | 0 | 38.4833 | 27 | 45 | 0.028938 | 44.9711 | 50.2667 | 65.1667 | 100
| ponds with sand filter | 0 | 0 | 0 | 0 | 0.38462 | -0.38462 | 70 | 79 | 100
| public toilets | 0 | 32.9 | 10 | 20 | 0.3022 | 19.6978 | 75 | 80 | 100
| rainwater harvesting | 0 | 0 | 0 | 0 | 0.27473 | -0.27473 | 50 | 80 | 100
| single pit latrines | 0 | 35.0808 | 7 | 30 | 0.22301 | 29.777 | 70.5882 | 80.8824 | 100
mol | cluster villages | 0 | 0 | 0 | 0 | 0.10989 | -0.10989 | 20 | 40 | 100
| settlement programme | 0 | 0.69444 | 0 | 0 | 0.10989 | -0.10989 | 20 | 40 | 100
|  | 2006-07-01 | 2007-03-25 | 2007-07-01 |  |  |  | 2008-07-01 |  | 2009-07-01 | 2010-07-01
| BWDB | 0 | 6.9065 | 8 |  |  |  | 52.53 |  | 88.8889 | 100
| LGED | 0 | 21.3095 | 21 |  |  |  | 74.1955 |  | 100
| DPHE | 0 | 21.2928 | 8.8 |  |  |  | 63.171 |  | 100
| MoL | 0 | 0.34722 | 0 |  |  |  | 20 |  | 100

## hulp sheet
10.1) box culverts (2 no's), Lakshmipur | y | y | y | y | y | y | 0 | 2 | 2 | 2 | 2 | 2 | 2
10.2) box culverts (5 no's), Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.3) box culverts (7 nos), Noakhali | y | y | y | y | y | y | 55 | 7 | 7 | 7 | 7 | 7 | 7
10.4) box culverts (7 nos), Noakhali | y | y | y | y | n | n | 0 | 7 | 7 | 7 | 7 | 0
10.5) box culverts (7 nos), Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.6) pipe culverts (5 no's), Lakshmipur | y | y | y | y | y | y | 0 | 5 | 5 | 5 | 5 | 5 | 5
10.7) pipe culverts (2 no's), Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.8) pipe culverts (8 no's), Noakhali | y | y | y | y | y | y | 65 | 8 | 8 | 8 | 8 | 8 | 8
10.10) pipe culverts (11 nos), Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.9) pipe culverts (12 nos), Noakhali | y | y | y | y | n | n | 0 | 12 | 12 | 12 | 12 | 0 | 0
12.6) rural (3 roads, 8.2 km), Lakshmipur | y | y | y | y | y | y | 73.6667 | 8.2 | 8.2 | 8.2 | 8.2 | 8.2 | 8.2
12.7) rural (1 road, 2.5 km), Lakshmipur | y | y | y | y | y | y | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
12.8) rural (11.8 km), Lakshmipur | y | n | n | n | n | n | 0 | 11.8 | 0 | 0 | 0 | 0 | 0
12.9) rural (12 roads, 28.8 km), Noakhali | y | y | y | y | y | y | 73.9 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8 | 28.8
12.10) rural (3.2 km), Noakhali | y | y | y | n | n | n | 0 | 3.2 | 3.2 | 3.2 | 0 | 0 | 0
12.11) Earthen road for cyclone shelter approach (2.7 km), Noakhali | y | y | y | y | n | n | 0 | 2.7 | 2.7 | 2.7 | 2.7 | 0 | 0
12.1) paved (7 km), Lakshmipur | y | y | y | y | n | n | 0 | 7 | 7 | 7 | 7 | 0 | 0
12.2) paved (5 km), Noakhali | y | y | y | y | y | y | 0 | 5 | 5 | 5 | 5 | 5 | 5
12.3) paved (2.6 km), Noakhali | y | y | y | y | y | y | 15 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6
12.4) paved (2.97 km), Noakhali | y | y | y | y | n | n | 0 | 2.97 | 2.97 | 2.97 | 2.97 | 0 | 0
12.5) paved (1.13 km), Noakhali | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.1) 5 ponds, Lakshmipur | y | y | y | y | y | y | 0 | 5 | 5 | 5 | 5 | 5 | 5
9.2) 13 ponds, Lakshmipur (4 LCS) | y | y | y | y | n | n | 0 | 13 | 13 | 13 | 13 | 0 | 0
9.3) 2 ponds, Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0
9.4) 15 ponds, LGED, Noakhali | y | y | y | y | y | y | 82.6667 | 15 | 15 | 15 | 15 | 15 | 15
9.5) 6 ponds, LCS, Noakhali | y | y | y | y | y | y | 100 | 6 | 6 | 6 | 6 | 6 | 6
9.6) 8 ponds, Noakhali | y | y | y | y | n | n | 0 | 8 | 8 | 8 | 8 | 0 | 0
9.7) 1 pond, Noakhali | y | n | n | n | n | n | 0 | 1 | 0 | 0 | 0 | 0 | 0
11.1) 7 cyclone shelters, Lakshmipur | y | y | y | y | y | y | 0.57143 | 7 | 7 | 7 | 7 | 7 | 7
11.2) 13 cyclone shelters, Noakhali | y | y | y | y | y | y | 74.7692 | 13 | 13 | 13 | 13 | 13 | 13
13.1) deep tube wells (102 nos), Noakhali | y | y | y | y | y | y | 90 | 102 | 102 | 102 | 102 | 102 | 102
13.2) deep tube wells (200 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 69.55 | 200 | 200 | 200 | 200 | 200 | 200
13.3) deep tube wells (58 nos), Noakhali & Lakshmipur | y | y | y | y | y | y | 0 | 58 | 58 | 58 | 58 | 58 | 58
13.4) deep tube wells (240 nos), Noakhali & Lakshmipur | y | y | n | n | n | n | 0 | 240 | 240 | 0 | 0 | 0 | 0
14.1) 10 ponds with sf, Lakshmipur | y | y | y | y | n | n | 0 | 10 | 10 | 10 | 10 | 0 | 0
16.1) rainwater harvesting (18 nos), Lakshmipur | y | y | y | y | y | y | 0 | 20 | 20 | 20 | 20 | 20 | 20
17.1) single pit latrines (5000 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 59.6374 | 5 | 5 | 5 | 5 | 5 | 5
17.3) single pit latrines (2500 nos), Noakhali & Lakshmipur | y | y | n | n | n | n | 0 | 2.5 | 2.5 | 0 | 0 | 0 | 0
17.2) single pit latrines (1000 nos), Noakhali & Lakshmipur | y | y | y | y | n | n | 0 | 1 | 1 | 1 | 1 | 0 | 0
3.1) Re-excavation Jarirdona, 0km-2.625km (2.625 km), Lakshmipur | y | y | y | y | n | n | 0 | 2.625 | 2.625 | 2.625 | 2.625 | 0 | 0
3.2) Re-excavation Jarirdona, 2.625km-3.535km (0.91 km), Lakshmipur | y | y | y | y | y | y | 0 | 0.91 | 0.91 | 0.91 | 0.91 | 0.91 | 0.91
3.3) Re-excavation Baggardona, 7.035km-13.935km (6.9 km), Noakhali | y | y | y | y | n | n | 0 | 6.9 | 6.9 | 6.9 | 6.9 | 0 | 0
3.4) Re-excavation Baggardona, 13.935km-17.035km (3.1 km), Lakshmipur | y | y | y | y | n | n | 0 | 3.1 | 3.1 | 3.1 | 3.1 | 0 | 0
1.1) Sea dyke, 0.63km-3.365km (2.735 km), Lakshmipur | y | y | y | y | y | y | 39.3333 | 2.735 | 2.735 | 2.735 | 2.735 | 2.735 | 2.735
1.2) Sea dyke, 3.365km-5.085km (1.72 km), Lakshmipur | y | y | y | y | y | y | 64.65 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72
1.3) Sea dyke, 5.085km-8.585km (3.5 km), Noakhali | y | y | y | y | y | y | 100 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
1.4) Sea dyke, 8.585km-11.5km (2.915 km), Noakhali | y | y | y | y | n | n | 0 | 2.915 | 2.915 | 2.915 | 2.915 | 0 | 0
1.5) Interior dyke, 11.5km-19.5km (8 km), Noakhali | y | y | y | y | n | n | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0
4.1) Jarirdona shortcut, 3.535km-4.535km (1 km), Lakshmipur | y | y | y | y | n | n | 0 | 1 | 1 | 1 | 1 | 0 | 0
4.2) Jarirdona shortcut, 4.535km-6.035km (1.5 km), Lakshmipur | y | y | y | y | n | n | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0
4.3) Jarirdona shortcut, 6.035km-7.035km (1 km), Noakhali | y | y | y | y | y | y | 26.5 | 1 | 1 | 1 | 1 | 1 | 1
15.1) public toilets (10 nos), Lakshmipur & Noakhali | y | y | y | y | y | y | 56.8 | 10 | 10 | 10 | 10 | 10 | 10
15.2) public toilets (5 nos), Noakhali & Lakshmipur | y | y | y | y | y | y | 9 | 5 | 5 | 5 | 5 | 5 | 5
15.3) public toilets (5 nos), Noakhali & Lakshmipur | y | y | y | y | n | n | 0 | 5 | 5 | 5 | 5 | 0 | 0
2.1) Guide dyke cum rural road, 7.035km-9.2km (2.165 km), Noakhali | y | y | y | y | y | y | 5.5704 | 2.165 | 2.165 | 2.165 | 2.165 | 2.165 | 2.165
2.2) Guide dyke cum rural road, 9.2km-10.00km (0.80 km), Noakhali | y | y | y | y | n | n | 0 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0
19.1) Rehabilitation, 25 cv with ponds only, Noakhali and Lakshmipur | y | y | y | n | n | n | 1 | 25 | 25 | 25 | 0 | 0 | 0
19.2) Rehabilitation, 11 cv with ponds only, Noakhali and Lakshmipur | n | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0 | 0