## LS Progress
Annex 2
Revised Monthwise Work Plan of Settlement of Khas Lands under CDSP-III
|  |  | District : Noakhali | [14 empty] | Upazila : Hatiya
House hold found during PTPS: 9500 | [13 empty] | Target (Landless family) : 9500
Month | Field Hearing (day) |  | Landless Family Selection (#) |  | Settlement Cases Started (#) |  | Jamabandi preparation (#) |  | Jamabandi Approval (#) |  |  |  | Selami & Khatian fee realisation & Kabuliyat execution (#) |  | Kabuliyat registration (#) |  | Khatian preparation (#) |  | Opening of Holding (#) |  | khatian hand over (#)
[9 empty] | Upazila |  | District
| Target | Achieve-ment | Target | Achieve-ment | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achieve-ment | Target | Achieve-ment
2007-05-01 | 7 | 1 | 104 | 105 | 0 | [13 empty] | 0
2007-06-01 | 9 | 3 | 372 | 371 | 0 | [13 empty] | 0
2007-07-01 | 3 | 0 | 500 | 0 | 476 | 462 | 300 | 462 | 250 | 444 | 0 | 392 | [6 empty] | 0
2007-08-01 | 3 | 2 | 500 | 231 | 400 | 190 | 300 | 175 | 250 | 193 | 250 | 52 | 0 |  | 0 |  | 0 |  | 0 |  | 0
2007-09-01 | 3 | 4 | 500 | 376 | 400 | 205 | 300 | 186 | 250 | 186 | 250 | 379 | 250 |  | 250 |  | 0 |  | 0 |  | 0
2007-10-01 | 3 | 2 | 500 | 132 | 400 | 160 | 300 | 150 | 250 | 0 | 250 | 0 | 250 |  | 250 |  | 250 |  | 250 |  | 250
2007-11-01 | 3 | 1 | 500 | 94 | 400 | 150 | 300 | 170 | 250 | 0 | 250 | 319 | 250 | 299 | 250 |  | 250 |  | 250 |  | 250
2007-12-01 | 3 | 4 | 500 | 425 | 400 | 180 | 300 | 165 | 250 | 325 | 250 |  | 250 | 90 | 250 | 247 | 250 | 100 | 250 |  | 250
Total | 34 | 17 | 3476 | 1734 | 2476 | 1347 | 1800 | 1308 | 1500 | 1148 | 1250 | 1142 | 1000 | 389 | 1000 | 247 | 750 | 100 | 750 | 0 | 750 | 0
2008-01-01 | 3 | 2 | 500 | 134 | 400 | 250 | 400 | 253 | 300 | 360 | 250 |  | 250 |  | 250 |  | 250 | 147 | 250 |  | 250
2008-02-01 | 3 | 2 | 500 | 68 | 400 |  | 400 |  | 300 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 | 247 | 250 | 247
2008-03-01 | 3 |  | 500 |  | 400 |  | 400 |  | 300 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250
2008-04-01 | 3 |  | 500 |  | 400 |  | 400 |  | 300 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250
2008-05-01 | 3 |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2008-06-01 | 3 |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2008-07-01 |  |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2008-08-01 |  |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2008-09-01 |  |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2008-10-01 |  |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2008-11-01 |  |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2008-12-01 |  |  | 524 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
Total (#) | 52 |  | 9500 |  | 7276 |  | 6600 |  | 5100 |  | 4650 |  | 4400 |  | 4400 |  | 4150 |  | 4150 |  | 4150
Month | Field Hearing (day) |  | Landless Family Selection (#) |  | Settlement Cases Started (#) |  | Jamabandi preparation (#) |  | Jamabandi Approval (#) |  |  |  | Selami & Khatian fee realisation & Kabuliyat execution (#) |  | Kabuliyat registration (#) |  | Khatian preparation (#) |  | Opening of Holding (#) |  | khatian hand over (#)
[9 empty] | Upazila |  | District
| Target | Achieve-ment | Target | Achieve-ment | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achieve-ment | Target | Achieve-ment
2009-01-01 |  |  | 0 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2009-02-01 |  |  | 0 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2009-03-01 |  |  | 0 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2009-04-01 |  |  | 0 |  | 512 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2009-05-01 |  |  | 0 |  | 512 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2009-06-01 |  |  | 0 |  | 0 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
Total | 52 |  | 9500 |  | 9500 |  | 9000 |  | 6900 |  | 6450 |  | 6200 |  | 6200 |  | 5950 |  | 5950 |  | 5950
2009-07-01 |  |  |  |  | 0 |  | 250 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2009-08-01 | [6 empty] | 250 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2009-09-01 | [8 empty] | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2009-10-01 | [8 empty] | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2009-11-01 | [8 empty] | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2009-12-01 | [8 empty] | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2010-01-01 | [8 empty] | 250 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2010-02-01 | [8 empty] | 250 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2010-03-01 | [8 empty] | 200 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2010-04-01 | [8 empty] | 100 |  | 350 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300
2010-05-01 | [12 empty] | 300 |  | 300 |  | 300 |  | 300 |  | 300
2010-06-01 | [16 empty] | 250 |  | 250 |  | 250
Total | 107 |  | 9500 |  | 9500 |  | 9500 |  | 9500 |  | 9500 |  | 9500 |  | 9500 |  | 9500 |  | 9500 |  | 9500

## LS hulp
month | total field hearing (day) |  |  |  | landless family selection (#) |  |  |  | settlement cases started (#) |  |  |  | jamabandi preparation (#) |  |  |  | jamabandi approval by upazila (#) |  |  |  | jamabandi approval by DC (#) |  |  |  | Selami realisation (#) |  |  |  | kabuliyat registration (#) |  |  |  | khatian preparation (#) |  |  |  | khatian hand over (#)
| plan | plan cumm. | achievement | achieved cumm. | plan | plan cumm. | achievement | achieved cumm. | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement |  | plan |  | achievement
2007-05-01 | 7 | 7 | 1 | 1 | 104 | 104 | 105 | 105 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
2007-06-01 | 9 | 16 | 3 | 4 | 372 | 476 | 371 | 476 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
2007-07-01 | 3 | 19 | 0 | 4 | 500 | 976 | 0 | 476 | 476 | 476 | 462 | 462 | 300 | 300 | 462 | 462 | 250 | 250 | 444 | 444 | 0 | 0 | 392 | 392 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
2007-08-01 | 3 | 22 | 2 | 6 | 500 | 1476 | 231 | 707 | 400 | 876 | 190 | 652 | 300 | 600 | 175 | 637 | 250 | 500 | 193 | 637 | 250 | 250 | 52 | 444 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
2007-09-01 | 3 | 25 | 4 | 10 | 500 | 1976 | 376 | 1083 | 400 | 1276 | 205 | 857 | 300 | 900 | 186 | 823 | 250 | 750 | 186 | 823 | 250 | 500 | 379 | 823 | 250 | 250 |  | 0 | 250 | 250 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
2007-10-01 | 3 | 28 | 2 | 12 | 500 | 2476 | 132 | 1215 | 400 | 1676 | 160 | 1017 | 300 | 1200 | 150 | 973 | 250 | 1000 | 0 | 823 | 250 | 750 | 0 | 823 | 250 | 500 |  | 0 | 250 | 500 |  | 0 | 250 | 250 |  | 0 | 250 | 250 |  | 0
2007-11-01 | 3 | 31 | 1 | 13 | 500 | 2976 | 94 | 1309 | 400 | 2076 | 150 | 1167 | 300 | 1500 | 170 | 1143 | 250 | 1250 | 0 | 823 | 250 | 1000 | 319 | 1142 | 250 | 750 | 299 | 299 | 250 | 750 |  | 0 | 250 | 500 |  | 0 | 250 | 500 |  | 0
2007-12-01 | 3 | 34 | 4 | 17 | 500 | 3476 | 425 | 1734 | 400 | 2476 | 180 | 1347 | 300 | 1800 | 165 | 1308 | 250 | 1500 | 325 | 1148 | 250 | 1250 |  | 1142 | 250 | 1000 | 90 | 389 | 250 | 1000 | 247 | 247 | 250 | 750 | 100 | 100 | 250 | 750 |  | 0
2008-01-01 | 3 | 37 | 2 | 19 | 500 | 3976 | 134 | 1868 | 400 | 2876 | 250 | 1597 | 400 | 2200 | 253 | 1561 | 300 | 1800 | 360 | 1508 | 250 | 1500 |  | 1142 | 250 | 1250 |  | 389 | 250 | 1250 |  | 247 | 250 | 1000 | 147 | 247 | 250 | 1000 |  | 0
2008-02-01 | 3 | 40 | 2 | 21 | 500 | 4476 | 68 | 1936 | 400 | 3276 |  | 1597 | 400 | 2600 |  | 1561 | 300 | 2100 |  | 1508 | 250 | 1750 |  | 1142 | 250 | 1500 |  | 389 | 250 | 1500 |  | 247 | 250 | 1250 |  | 247 | 250 | 1250 | 247 | 247
2008-03-01 | 3 | 43 |  | 21 | 500 | 4976 |  | 0 | 400 | 3676 |  | 1597 | 400 | 3000 |  | 1561 | 300 | 2400 |  | 1508 | 250 | 2000 |  | 1142 | 250 | 1750 |  | 389 | 250 | 1750 |  | 247 | 250 | 1500 |  | 247 | 250 | 1500 |  | 247
2008-04-01 | 3 | 46 |  | 21 | 500 | 5476 |  | 0 | 400 | 4076 |  | 1597 | 400 | 3400 |  | 1561 | 300 | 2700 |  | 1508 | 250 | 2250 |  | 1142 | 250 | 2000 |  | 389 | 250 | 2000 |  | 247 | 250 | 1750 |  | 247 | 250 | 1750 |  | 247
2008-05-01 | 3 | 49 |  | 21 | 500 | 5976 |  | 0 | 400 | 4476 |  | 1597 | 400 | 3800 |  | 1561 | 300 | 3000 |  | 1508 | 300 | 2550 |  | 1142 | 300 | 2300 |  | 389 | 300 | 2300 |  | 247 | 300 | 2050 |  | 247 | 300 | 2050 |  | 247
2008-06-01 | 3 | 52 |  | 21 | 500 | 6476 |  | 0 | 400 | 4876 |  | 1597 | 400 | 4200 |  | 1561 | 300 | 3300 |  | 1508 | 300 | 2850 |  | 1142 | 300 | 2600 |  | 389 | 300 | 2600 |  | 247 | 300 | 2350 |  | 247 | 300 | 2350 |  | 247
2008-07-01 |  | 52 |  | 21 | 500 | 6976 |  | 0 | 400 | 5276 |  | 1597 | 400 | 4600 |  | 1561 | 300 | 3600 |  | 1508 | 300 | 3150 |  | 1142 | 300 | 2900 |  | 389 | 300 | 2900 |  | 247 | 300 | 2650 |  | 247 | 300 | 2650 |  | 247
2008-08-01 |  | 52 |  | 21 | 500 | 7476 |  | 0 | 400 | 5676 |  | 1597 | 400 | 5000 |  | 1561 | 300 | 3900 |  | 1508 | 300 | 3450 |  | 1142 | 300 | 3200 |  | 389 | 300 | 3200 |  | 247 | 300 | 2950 |  | 247 | 300 | 2950 |  | 247
2008-09-01 |  | 52 |  | 21 | 500 | 7976 |  | 0 | 400 | 6076 |  | 1597 | 400 | 5400 |  | 1561 | 300 | 4200 |  | 1508 | 300 | 3750 |  | 1142 | 300 | 3500 |  | 389 | 300 | 3500 |  | 247 | 300 | 3250 |  | 247 | 300 | 3250 |  | 247
2008-10-01 |  | 52 |  | 21 | 500 | 8476 |  | 0 | 400 | 6476 |  | 1597 | 400 | 5800 |  | 1561 | 300 | 4500 |  | 1508 | 300 | 4050 |  | 1142 | 300 | 3800 |  | 389 | 300 | 3800 |  | 247 | 300 | 3550 |  | 247 | 300 | 3550 |  | 247
2008-11-01 |  | 52 |  | 21 | 500 | 8976 |  | 0 | 400 | 6876 |  | 1597 | 400 | 6200 |  | 1561 | 300 | 4800 |  | 1508 | 300 | 4350 |  | 1142 | 300 | 4100 |  | 389 | 300 | 4100 |  | 247 | 300 | 3850 |  | 247 | 300 | 3850 |  | 247
2008-12-01 |  | 52 |  | 21 | 524 | 9500 |  | 0 | 400 | 7276 |  | 1597 | 400 | 6600 |  | 1561 | 300 | 5100 |  | 1508 | 300 | 4650 |  | 1142 | 300 | 4400 |  | 389 | 300 | 4400 |  | 247 | 300 | 4150 |  | 247 | 300 | 4150 |  | 247
2009-01-01 |  | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2009-02-01 |  | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2009-03-01 |  | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2009-04-01 |  | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2009-05-01 |  | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2009-06-01 |  | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2009-07-01 |  | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2009-08-01 |  | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2009-09-01 |  | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total (#) | 52 |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
Total achievement (%) |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 0 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF!

## LS hulp 2
month: | 2007-12-31
month | total field hearing (day) |  | landless family selection (#) |  | settlement cases started (#) |  | Jamabandi preparation (#) |  | Jamabandi approval by upazila (#) |  | jamabandi approval by DC (#) |  | Selami execution (#) |  | kabuliyat registration (#) |  | khatian preparation (#) |  | khatian hand over (#)
| plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement | plan | achievement
Total | 52 | 0 | 9500 | 0 | 7276 | 0 | 6600 | 0 | 5100 | 0 | 4650 | 0 | 4400 | 0 | 4400 | 0 | 4150 | 0 | 4150 | 0
current total | 34 | 17 | 3476 | 1734 | 2476 | 1347 | 1800 | 1308 | 1500 | 1148 | 1250 | 1142 | 1000 | 389 | 1000 | 247 | 750 | 100 | 750 | 0
| plan end of project | current achievement | current plan
total field hearing (day) | 52 | 17 | 34
landless family selection | 9500 | 1734 | 3476
settlement cases started | 7276 | 1347 | 2476
jamabandi preparation | 6600 | 1308 | 1800
Jamabandi approval upazila | 5100 | 1148 | 1500
jamabandi approval by DC | 4650 | 1142 | 1250
Selami execution | 4400 | 389 | 1000
kabuliyat registration | 4400 | 247 | 1000
khatian preparation | 4150 | 100 | 750
khatian hand over | 4150 | 0 | 750