## FA budget
Itemwise FA Budget & Reimbursement Position under CDSP-III as on 31st December 2007
Sl. No. | Item | Revised Budget Allocation (BDT in lakh) | Expenditure incurred & claimed by IAs (BDT in lakh) | Recommended by TA Team (BDT in lakh)
Name of Agency: BWDB
A. | Baggardona Upstream area
(Civil Work)
1 | Re-excavation of Baggardona
| (Bhulua river) River | 680 | 0 | 0
2 | Re-excavation of Jarirdona khal | 408 | 0 | 0
3 | Short cut Drainage cannel (Jarirdona) | 573 | 17.74 | 17.74
| Sub-Total of A. | 1661 | 17.74 | 17.74
B. | Boyer Char & Char Moradona area
1 | Drainage Sluice (DS-2) | 550 | 0 | 0
2 | Closure-1 (at D/S of steamer ghat) | 232 | 0 | 0
3 | Closure-2 (at CBD-I) | 62 | 0 | 0
4 | Embankment in Boyer Char | 896 | 217.42 | 217.42
5 | Guide dyke cum rural road | 87 | 0 | 0
6 | Short cut Drainage channel at Gabtoli | 272 | 0 | 0
7 | Re-excavation of Banskhali Khal at D/S of sluice | 23 | 0 | 0
8 | Improvement of Secondary drainage channel | 279.87 | 0 | 0
9 | Drainage cum flushing sluices | 250 | 0 | 0
| Sub-Total of B. | 2651.87 | 217.42 | 217.42
C. | Other cost
1 | Additional drainage study | 99.2 | 0 | 0
| Sub-Total of C. | 99.2 | 0 | 0
Total of BWDB |  | 4412.07 | 235.16 | 235.16
Name of Agency : LGED
Boyer Char & Char Moradona area
i) | Rural Infrastructure
| a) Road (Paved) | 680 | 0 | 0
| b) Rural Road (Earthen) | 215 | 70.79 | 67.72
| c) Bridge | 200 | 0 | 0
| d) Foot bridge | 10 | 0 | 0
| e) Box culvert | 355 | 33.43 | 31.09
| f) Pipe Culvert | 50 | 1.91 | 1.91
ii) | Settlement Infrastructure
| a) Cyclone shelter | 1200 | 372.95 | 357.31
| b) Community Pond | 140 | 22.96 | 20.79
| c) Bus stand | 60 | 0 | 0
Total of LGED |  | 2910 | 502.04 | 478.82
Name of Agency : DPHE
A. | Boyer Char area
| a) Single pit latrine | 187 | 48.45 | 25.72
| b) Public Toilet in Market | 140 | 27.8 | 14.2
| c) Deep Tubewell | 352 | 91.89 | 71.83
d) Development of community pond with
| arrangement of PSF | 60 | 0 | 0
| e) Rain Water Harvesting | 3 | 0 | 0
| Sub-Total of A. | 742 | 168.14 | 111.75
B. | Other cost
| a) Training software activities | 50 | 0 | 0
| b) Test Tubewell | 8 | 0 | 0
| Sub-Total of B. | 58 | 0 | 0
Total of DPHE |  | 800 | 168.14 | 111.75
Name of Agency : FD
A. | Plantation Programme
1 | Establishment of Mangrove plantation | 30.5 | 30.5 | 30.5
2 | Establishment of Foreshore Plantation | 204.36 | 26.08 | 26.08
3 | Establishment of strip Plantation
| a) Embankment Plantation | 14.4 | 7.67 | 7.67
| b) Feeder Road Plantation | 7.9 | 7.9 | 6.4
4 | Village/Homestead Plantation | 49 | 48.98 | 48.98
| Sub-Total of A. | 306.16 | 121.13 | 119.63
B. | Plantation Maintenance
| a) Mangrove plantation | 15.6 | 5.2 | 4.89
| b) Foreshore Plantation | 52.33 | 0 | 0
| c) Embankment Plantation | 20.93 | 0 | 0
| d) Feeder Road Plantation | 3.5 | 1.17 | 1.17
| Sub-Total of B. | 92.36 | 6.37 | 6.06
C. | Other cost
| a) Contingencies | 6.37 | 4.26 | 1.6
| b) Local Training & Logistic | 55.15 | 32.12 | 32.12
| c) Manpower (MR Basis) | 75.39 | 24.74 | 24.74
| Sub-Total of C. | 136.91 | 61.12 | 58.46
Total of FD |  | 535.43 | 188.62 | 184.15
Name of Agency : DAE
A. | Boyerchar area
1 | Field Demonstration | 20.4 | 10.27 | 10.09
2 | Farmers Training (Local) | 17.28 | 6 | 6
3 | Farmer Motivation Tour | 11.2 | 3.52 | 3.52
4 | Workshop/ saminar (Local) | 3.12 | 1.18 | 1.18
5 | On-farm testing of new technology | 3.4 | 0.42 | 0.42
6 | Procurement of support materials | 7 | 4 | 4
7 | Training of Trainers | 2.4 | 0.42 | 0.42
8 | Printing Extension Materials | 1 | 0.1 | 0.1
9 | Contingency | 0.7 | 0.2 | 0.2
Total of DAE |  | 66.5 | 26.11 | 25.93
Name of Agency : MoL
A. | Settlement Progamme
| a) Rehabilitation of 3000 families | 496 | 0 | 0
Total of MoL |  | 496 | 0 | 0
Grand Total (BWDB+LGED+DPHE+FD+DAE+MoL) |  | 9220 | 1120.07 | 1035.81

## Sheet2
| E/R |  | C/S |  | Pond | BC
| 517890 |  | 989887 |  | 51673
| 295480 |  | 458178 |  | 65672
| 350363 |  | 834794 |  | 57529
| 325738 |  | 472787 |  | 57632
| 362460 |  | 1113663 |  | 41171
| 357714 |  | 1009784 |  | 37958
| 321021 |  | 435973 |  | 51159
| 297593 |  | 898742 |  | 65229
| 208055 | 208055 | 893204 |  | 63291
| 376711 |  | 898484 |  | 59742
| 3413025 | 208055 | 8005496 |  | 57647
71253
| 204362 |  | 1363279 | 254250 | 679956 | 538066
| 150195 |  | 951430 |  |  | 648257
| 51090 |  | 278416 |  |  | 1186323
| 37549 |  | 897226
| 443196 |  | 108993
1055103
1348184
1361099
1094377
559655
569923
713070
|  |  | 10300755 | 254250
Total | 3856221 | 208055 | 18306251 | 254250 | 679956 | 1186323