Revised Monthwise Work Plan of Settlement of Khas Lands under CDSP-III

District : Noakhali	Upazila : Hatiya

House hold found during PTPS: 9500	Target (Landless family): 9500

| Month | Field Hearing (day) |  | Landless Family Selection (#) |  | Settlement Cases Started (#) |  | Jamabandi preparation (#) |  | Jamabandi Approval (#) |  |  |  | Selami & Khatian fee realisation & Kabuliyat execution (#) |  | Kabuliyat registration (#) |  | Khatian preparation (#) |  | Opening of Holding (#) |  | khatian hand over (#) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Upazila |  | District |  |  |  |  |  |  |  |  |  |  |  |
|  | Target | Achieve-ment | Target | Achieve-ment | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achieve-ment | Target | Achieve-ment |
| May-07 | 7 | 1 | 104 | 105 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |
| Jun-07 | 9 | 3 | 372 | 371 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |
| Jul-07 | 3 | 0 | 500 | 0 | 476 | 462 | 300 | 462 | 250 | 444 | 0 | 392 |  |  |  |  |  |  | 0 |  |  |  |
| Aug-07 | 3 | 2 | 500 | 231 | 400 | 190 | 300 | 175 | 250 | 193 | 250 | 52 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |
| Sep-07 | 3 | 4 | 500 | 376 | 400 | 205 | 300 | 186 | 250 | 186 | 250 | 379 | 250 |  | 250 |  | 0 |  | 0 |  | 0 |  |
| Oct-07 | 3 | 2 | 500 | 132 | 400 | 160 | 300 | 150 | 250 | 0 | 250 | 0 | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  |
| Nov-07 | 3 | 1 | 500 | 94 | 400 | 150 | 300 | 170 | 250 | 0 | 250 | 319 | 250 | 299 | 250 |  | 250 |  | 250 |  | 250 |  |
| Dec-07 | 3 | 4 | 500 | 425 | 400 | 180 | 300 | 165 | 250 | 325 | 250 |  | 250 | 90 | 250 | 247 | 250 | 100 | 250 |  | 250 |  |
| Total | 34 | 17 | 3476 | 1734 | 2476 | 1347 | 1800 | 1308 | 1500 | 1148 | 1250 | 1142 | 1000 | 389 | 1000 | 247 | 750 | 100 | 750 | 0 | 750 | 0 |
| Jan-08 | 3 | 2 | 500 | 134 | 400 | 250 | 400 | 253 | 300 | 360 | 250 |  | 250 |  | 250 |  | 250 | 147 | 250 |  | 250 |  |
| Feb-08 | 3 | 2 | 500 | 68 | 400 |  | 400 |  | 300 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 | 247 | 250 | 247 |
| Mar-08 | 3 |  | 500 |  | 400 |  | 400 |  | 300 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  |
| Apr-08 | 3 |  | 500 |  | 400 |  | 400 |  | 300 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  |
| May-08 | 3 |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  |
| Jun-08 | 3 |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  |
| Jul-08 |  |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  |
| Aug-08 |  |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  |
| Sep-08 |  |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  |
| Oct-08 |  |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  |
| Nov-08 |  |  | 500 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  |
| Dec-08 |  |  | 524 |  | 400 |  | 400 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  | 300 |  |
| Total (#) | 52 |  | 9500 |  | 7276 |  | 6600 |  | 5100 |  | 4650 |  | 4400 |  | 4400 |  | 4150 |  | 4150 |  | 4150 |  |