## Overview BWDB
Table 1 - BWDB | Design available (y/n) | Design concurred (y/n) | Estimate concurred (y/n) | Floating tender (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Invested amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks | Estimated amount Tk. In Lakh
Item of work | [6 empty] | 2009-06-30 |  |  | 90.0225
Total BWDB | 100 | 100 | 100 | 88.8889 | 88.8889 | 82.2899 | 85.7207 | -3.4308 | 3715.5033 | 3344.7876 | 2092.49 | 1656.59
1) Embankments
Total sea dyke (10.87 km) | 100 | 100 | 100 | 100 | 100 | 88.0352 | 100 | -11.9648 | 542.6342 | 469.7374 | 323.22 | 274.94
Total interior dyke (8 km) | 100 | 100 | 100 | 100 | 100 | 93.1041 | 100 | -6.8959 | 390.65 | 363.7113 | 193.56 | 157.31
1.1) Sea dyke, 0.63km-3.365km (2.5 km), Lakshmipur | y | y | y | y | y | 81.892 | 100 | -18.108 | 132.44 | 108.4578 | 68.81 | 56.08 | Group 02, 03 completed, 01 almost completed & 05 on progress
1.2) Sea dyke, 3.365km-5.085km (1.72 km), Lakshmipur | y | y | y | y | y | 98 | 100 | -2 | 76.12 | 74.5976 | 65.51 | 65.51 | Group 4; completed, rectification needed
1.3) Sea dyke, 5.085km-8.585km (3.5 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 154.8742 | 154.8742 | 153.35 | 153.35 | Group 1- 5 all completed
1.4) Sea dyke, 8.585km-11.5km (2.915 km), Noakhali | y | y | y | y | y | 73.5535 | 100 | -26.4465 | 179.2 | 131.8079 | 35.55 | 0 | Group 6 is in progress & Group 7 almost completed
1.5) Interior dyke, 11.5km-19.5km (8 km), Noakhali | y | y | y | y | y | 93.1041 | 100 | -6.8959 | 390.65 | 363.7113 | 193.56 | 157.31 | 5 Groups, Group 8 is in progress and Group-09 to 12 are completed.
2) Individual guide dyke
Total guide dyke (2.965 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 82.09 | 82.09 | 80.77 | 80.77
2.1) Guide dyke cum rural road, 7.035km-10.00km (2.965 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 82.09 | 82.09 | 80.77 | 80.77 | 2 groups, all completed.
3) Re-excavations
Total Jarirdona (3.535 km) | 100 | 100 | 100 | 100 | 100 | 97.5813 | 93.6034 | 3.9779 | 387.12 | 377.5509 | 172.15 | 90.15
Total Bagardona (10 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 625.654 | 625.654 | 332.54 | 241.09
3.1) Re-excavation Jarirdona, 0km-2.625km (2.625 km), Lakshmipur | y | y | y | y | y | 98.4762 | 93.6034 | 4.8728 | 281.54 | 277.2499 | 100.66 | 18.66 | 4 groups, all are in progress
3.2) Re-excavation Jarirdona, 2.625km-3.535km (0.91 km), Lakshmipur | y | y | y | y | y | 95 | 93.6034 | 1.3966 | 105.58 | 100.301 | 71.49 | 71.49 | 1 group, work is in progress
3.3) Re-excavation Baggardona, 7.035km-13.935km (6.9 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 400.452 | 400.452 | 189.35 | 137.35 | 5 groups, all are completed.
3.4) Re-excavation Baggardona, 13.935km-17.035km (3.1 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 225.202 | 225.202 | 143.19 | 103.74 | 3 groups, all are completed.
4) Short cuts
Total Jarirdona shortcut (3.5 km) | 100 | 100 | 100 | 100 | 100 | 98.8571 | 93.6034 | 5.2537 | 589.09 | 582.1503 | 375.92 | 328.81
Gabtali khal (6.155 km) | 100 | 100 | 100 | 100 | 100 | 98.7308 | 100 | -1.2692 | 266.36 | 262.9793 | 200.35 | 200.35
Secondary drainage (21 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 36.68 | 30.15 | 8.67 | 4.37
4.1) Jarirdona shortcut, 3.535km-3.925km (0.39 km), Lakshmipur | y | y | y | y | y | 99 | 93.6034 | 5.3966 | 58.97 | 58.3803 | 23.05 | 7 | 1 group, Mostly completed
4.2) Jarirdona shortcut, 3.925km-6.035km (2.11 km), Lakshmipur | y | y | y | y | y | 98.2891 | 93.6034 | 4.6857 | 371.15 | 364.8 | 207.71 | 180.35 | 5 groups, all mostly completed
4.3) Jarirdona shortcut, 6.035km-7.035km (1 km), Noakhali | y | y | y | y | y | 100 | 93.6034 | 6.3966 | 158.97 | 158.97 | 145.16 | 141.46 | 2 groups, completed & flow well.
4.4) drainage channel Gabtali khal (6.155 km), Lakshmipur | y | y | y | y | y | 98.7308 | 100 | -1.2692 | 266.36 | 262.9793 | 200.35 | 200.35 | 4 groups, all started & mostly completed
4.5) improvement secondary drainage (6 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 6.53 | 6.53 | 4.37 | 4.37 | 1 group, completed
4.6) improvement secondary drainage (15 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 30.15 | 30.15 | 4.3 | 0 | 1 group, completed
4.7) Improvement of Banshkhali khal (2.1 km) | y | n | n | n | n | 0 | 0 | 0 | - |  | - | - | Design & estimate under process (pp revision needed) | 110
5) Sluices (3 nos)
Total sluices | 100 | 100 | 100 | 100 | 100 | 76.9519 | 70 | 6.9519 | 715.7251 | 550.7644 | 360.65 | 234.14
5.1) Gabtali Khal sluice, Lakshmipur | y | y | y | y | y | 95 | 90 | 5 | 508.8468 | 483.4044 | 352.65 | 234.14 | Work is in progress
5.2) Tankir Khal sluice, Noakhali | y | y | y | y | y | 40 | 60 | -20 | 104.2694 | 41.7077 | 4 | - | Work is in progress
5.3) Chatla Khal sluice, Noakhali | y | y | y | y | y | 25 | 60 | -35 | 102.609 | 25.6522 | 4 | - | Work is in progress
6) Closures (2 nos)
Total closures | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 349.04
6.1) closure 1 (Downstream Banshkhali), Noakhali | y | y | y | n | n | 0 | 0 | 0 | - | 0 | - | - | Design & estimate done, tender floating under process | 241.93
6.2) closure 2 (CBD-1), Noakhali | y | y | y | n | n | 0 | 0 | 0 | - | 0 | - | - | Design & estimate done, tender floating under process | 107.11
Maintenance khals
Maintenance khals (17 nos) | y | y | y | y | y | 100 | #REF! | #REF! | 133.5505 | 133.5505 | 0 | 0
7) Additional drainage study at upper Baggardona | - | - | - | - | - | 95 | - | - | 79.5 | 75.525 | 44.66 | 44.66 | Draft Final Report prepared

## Overview LGED
Table 2 - LGED | Design available (y/n) | Design concurred (y/n) | Estimate concurred (y/n) | Floating tender (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2009-06-30
Total LGED | 98.3518 | 98.3518 | 98.3518 | 98.3518 | 98.3518 | 85.0952 | 95.9375 | -10.8423 | 2710.062 | 1947.94 | 1805.27
7) Bridges | 100 | 100 | 100 | 100 | 100
7.1) bridges (3 no's), Noakhali | y | y | y | y | y | 97 | 100 | -3 | 196.09 | 185.05 | 147.08 | all are in progress
7.2) foot bridge (1 no), Noakhali | y | y | y | y | y | 42 | 50 | -8 | 9.3977 | 2.94 | 0 | work is in progress
8) Busstand | 100 | 100 | 100 | 100 | 100
8.1) Busstand, Noakhali | y | y | y | y | y | 95 | 100 | -5 | 56.7459 | 24.75 | 24.75 | work is in progress
9) Community ponds
Total community ponds (49 nos.) | 100 | 100 | 100 | 100 | 100 | 97.7143 | 100 | -2.2857 | 74.9549 | 61.73 | 61.61
9.1) 19 ponds, Lakshmipur (4 LCS) | y | y | y | y | y | 99.1053 | 100 | -0.89474 | 25.36 | 20.87 | 20.75 | few ponds partly to be completed
9.2) 15 ponds, LGED, Noakhali | y | y | y | y | y | 94.3333 | 100 | -5.6667 | 19.6449 | 14.47 | 14.47 | out of 15, 12 completed & 3 partly to be completed
9.3) 15 ponds, LCS, Noakhali | y | y | y | y | y | 99.3333 | 100 | -0.66667 | 29.95 | 26.39 | 26.39 | one pond partly to be completed
10) Culverts
Total box culverts (28 nos.) | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 94.2143 | 100 | -5.7857 | 290.58 | 214.64 | 152.11
Total pipe culverts (38 + 26 = 64 nos.) | 100 | 100 | 100 | 100 | 100 | 53.5938 | 67.5 | -13.9062 | 49.735 | 44.45 | 43.56
10.2) box culverts (7 no's), Lakshmipur | y | y | y | y | y | 76.8571 | 100 | -23.1429 | 61.85 | 25.28 | 25.28 | out of 7, 5 completed, 1 is in progress & 1 yet to start
10.3) box culverts (21 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 228.73 | 189.36 | 126.83 | all structures completed
10.6) pipe culverts (31 nos), Noakhali | y | y | y | y | y | 88.0645 | 100 | -11.9355 | 41.055 | 36.51 | 35.62 | out of 31, 27 completed, 1 is in progress & 3 yet to start.
10.5) pipe culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 67.5 | 32.5 | 8.68 | 7.94 | 7.94 | all 7 completed
10.7) pipe culverts (26 nos), Noakhali | n | n | n | n | n | 0 | 0 | 0 | - | - | - | New proposal, pp revision needed
11) Cyclone shelters
Total cyclone shelters (20 nos.) | 100 | 100 | 100 | 100 | 100 | 85.75 | 100 | -14.25 | 1176.4124 | 895.48 | 876.84
11.1) 7 cyclone shelters, Lakshmipur | y | y | y | y | y | 59.2857 | 100 | -40.7143 | 425.7659 | 145.04 | 142.52 | work is in progress for all 7.
11.2) 13 cyclone shelters, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 731.9973 | 724.54 | 708.42 | all 13 completed
11.3) Field raising near cyclone shelters (7 nos), Lakshmipur | n | n | n | n | n | 0 | 100 | -100 | 0 | - | - | After major progress of cyclone shelter
11.4) Field raising near cyclone shelters (13 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 18.6492 | 18.62 | 18.62 | all 13 completed
12) Roads
Total rural roads (54.6 km) | 100 | 100 | 100 | 100 | 100 | 98.9705 | 100 | -1.0295 | 189.4921 | 151.75 | 148.67
Total paved roads (18.7 km) | 93.9572 | 93.9572 | 93.9572 | 93.9572 | 93.9572 | 75.6767 | 100 | -24.3233 | 659.224 | 367.15 | 350.65
12.1) paved (7 km), Lakshmipur | y | y | y | y | y | 78.5714 | 100 | -21.4286 | 259.803 | 147.96 | 147.96 | 3 groups, 1 completed & 2 are in progress
12.2) paved (11.57 km), Noakhali | y | y | y | y | y | 73.7597 | 100 | -26.2403 | 399.421 | 219.19 | 202.69 | 5 groups, 2 completed & 3 are in progress
12.3) paved (1.13 km), Noakhali | n | n | n | n | n | 0 | 100 | -100 | 0 | 0 | 0 | will be spent for the revision purpose of ongoing roads
12.4) rural, 13 roads (22.6 km), Lakshmipur | y | y | y | y | y | 98.8938 | 100 | -1.1062 | 78.16 | 43.87 | 41.78 | 12 completed and 1 yet to start
12.5) 13 rural roads (32 km), Noakhali | y | y | y | y | y | 98.9375 | 100 | -1.0625 | 111.3321 | 107.88 | 106.89 | 12 completed and 1 yet to start
12.6) 8 earthen roads for cyclone shelter approach (2.7 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 7.43 | 7.28 | 7.28 | all 8 completed
Maintenance
Maintenance (12 items) | y | y | y | y | y | 0 | 0 | 0 | 99.2192 | 0 | 0 | for 6 items contracts have been awarded, the other 6 have to be retendered

## Overview DPHE
Table 3 - DPHE | Design available (y/n) | Design concurred (y/n) | Estimate concurred (y/n) | Floating tender (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2009-06-30
Total DPHE | 94.1176 | 94.1176 | 87.451 | 87.451 | 87.451 | 71.9833 | 100 | -28.0167 | 491.0675 | 306.687 | 288.527
13) Deep tube wells
Total deep tube wells (600) | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 61.15 | 100 | -38.85 | 200.75 | 129.32 | 116.62
13.1) deep tube wells (400 nos), Lakshmipur & Noakhali | y | y | y | y | y | 91.725 | 100 | -8.275 | 200.75 | 127.83 | 116.62 | 40 groups & all groups started, 371 nos sunk
13.3) deep tube wells (200 nos), Noakhali & Lakshmipur | y | y | n | n | n | 0 | 100 | -100 | - | - | - | no suitable locations found
13.4) test deep tube wells (8 nos), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 4.96 | 1.49 | 1.16 | all sunk
14) Pond with sand filter
14.1) 10 ponds with sf, Lakshmipur | y | y | y | y | y | 25 | 100 | -75 | 4.9275 | - | - | work started
15) Public toilets
15.1) public toilets (20 nos), Lakshmipur & Noakhali | y | y | y | y | y | 95.15 | 100 | -4.85 | 125.32 | 88.41 | 87.11 | all are in progress
16) Rainwater harvesting
16.1) rainwater harvesting (18 nos), Lakshmipur | y | y | y | y | y | 98 | 100 | -2 | 3 | 2.187 | 2.187 | works for all are in progress
17) Single pit latrines
Total single pit latrines (8500 nos) | 70.5882 | 70.5882 | 70.5882 | 70.5882 | 70.5882 | 71.8953 | 100 | -28.1047 | 157.07 | 86.77 | 82.61
17.1) single pit latrines (8500 nos), Noakhali & Lakshmipur | y | y | y | y | y | 71.8953 | 100 | -28.1047 | 157.07 | 86.77 | 82.61 | cast:6240, installed: 4951(15 groups started out of 17)

## Overview MoL
Table 4 - MoL | Design available (y/n) | Design concurred (y/n) | Estimate concurred (y/n) | Floating tender (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2009-06-30
Total MoL | 100 | 100 | 100 | 100 | 68.1034 | 34.2341 | 76.6667 | -18.0532 | 184.6735 | 62.04 | 60.04
18) Construction work in cluster villages
Total construction work (144 twin houses & 9 ponds GoB) | 100 | 100 | NA | 100 | 50 | 16.6667 | 30 | -13.3333 | 35.503 | 0 | 0
18.1) construction of twin houses (144 nos), Lakshmipur & Noakhali | y | y | NA | y | n | 0 | 30 | -30 | - | - | -
18.2) construction of 6 ponds, Lakshmipur & Noakhali | y | y | NA | y | y | 100 | 100 | 0 | 35.503 | - | - | all completed
18.3) construction of 3 ponds, Lakshmipur & Noakhali | y | y | NA | n | n | 0 | 100 | -100 | - | - | - | Tender floated for 2
19) Settlement programme (RPA) | [5 empty] | 42.0885
19.1)Total : excavation of CV ponds (35 cv ponds) | 100 | 100 | 100 | 100 | 86.2069 | 77.227 | 100 | -22.773 | 149.1705 | 62.04 | 60.04
19.1.1) Excavation of 25 cv ponds, Noakhali and Lakshmipur | y | y | y | y | y | 89.5833 | 100 | -10.4167 | 149.1705 | 62.04 | 60.04 | Out of 25, 21 completed & 4 are in progress
19.1.2) Excavation of 10 cv ponds, Noakhali and Lakshmipur | y | y | y | y | n | 0 | 100 | -100 | - | - | - | Tender floated for 4
19.2)Total house shifting cost for 1100 families (budget 496 lakh) | Exp. for house shifting yet done =Tk.22.38 lakh |  |  |  |  | 6.95 | 100 | -93.05 |  |  |  | 241 families temporary shifted from the alignment of infrastructures.

## Maintnance
Table 5 - MAINTENANCE | Design available (y/n) | Design concurred (y/n) | Estimate concurred (y/n) | Floating tender (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2009-06-30 |  |  | 63.9387 | 59.367
Total LGED | 98.3518 | 98.3518 | 98.3518 | 98.3518 | 98.3518 | 87.2399 | 95.9375 | -8.6976 | 2599.257 | 1661.93 | 1543.1
7) Bridges | 100 | 100 | 100 | 100 | 100
7.1) bridges (3 no's), Noakhali | 0 | y | y | y | y | 97 | 100 | -3 | 97 | 196.09 | 119.32 | Work going on in all three
7.2) foot bridge (1 no), Noakhali | 0 | y | y | y | y | 42 | 0 | 42 | 42 | 9.3977 | - | w.o. issued
8) Busstand | 100 | 100 | 100 | 100 | 100
8.1) Busstand, Noakhali | y | y | y | y | y | 95 | 100 | -5 | 56.7459 | 17.43 | 17.43 | earth filling 75% complete
9) Community ponds
Total community ponds (49 nos.) | 100 | 100 | 100 | 100 | 100 | 97.7143 | 100 | -2.2857 | 74.9549 | 61.73 | 61.61
9.1) 19 ponds, Lakshmipur (4 LCS) | y | y | y | y | y | 99.1053 | 100 | -0.89474 | 25.36 | 20.87 | 20.75 | work started for 18
9.2) 15 ponds, LGED, Noakhali | y | y | y | y | y | 94.3333 | 100 | -5.6667 | 19.6449 | 14.47 | 14.47 | Work started for all 15
9.3) 15 ponds, LCS, Noakhali | y | y | y | y | y | 99.3333 | 100 | -0.66667 | 29.95 | 26.39 | 26.39 | Work started for all 15
10) Culverts
Total box culverts (28 nos.) | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 94.2143 | 100 | -5.7857 | 331.635 | 142.32 | 142.32
Total pipe culverts (64 nos.) | 100 | 100 | 100 | 100 | 100 | 53.5938 | 67.5 | -13.9062 | 8.68 | 3.53 | 3.53
0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -100 | 0 | 0 | 0 | work started for both
10.2) box culverts (7 no's), Lakshmipur | y | y | y | y | y | 76.8571 | 100 | -23.1429 | 61.85 | 7.6 | 7.6 | W.O. issued
10.3) box culverts (21 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 228.73 | 103.14 | 103.14 | 5 yet to start work
10.6) pipe culverts (31 nos), Noakhali | y | y | y | y | y | 88.0645 | 100 | -11.9355 | 41.055 | 31.58 | 31.58 | work started for 28 (21 completed), 2 yet to start, 1 tender held up.
10.5) pipe culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 67.5 | 32.5 | 8.68 | 3.53 | 3.53 | work started for all 7
10.7) pipe culverts (26 nos), Noakhali | n | n | n | n | n | 0 | 67.5 | -67.5 | - | - | - | number and locations yet to be decided
11) Cyclone shelters
Total cyclone shelters (20 nos.) | 100 | 100 | 100 | 100 | 100 | 85.75 | 100 | -14.25 | 1174.0951 | 809.81 | 806.87
11.1) 7 cyclone shelters, Lakshmipur | y | y | y | y | y | 59.2857 | 100 | -40.7143 | 425.7659 | 82.53 | 80.01 | work started for 5, W.O. canceled for 2. One w.o. and one estimate under process
11.2) 13 cyclone shelters, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 729.68 | 708.84 | 708.42 | work started for all 13
11.3) Field raising near cyclone shelters (7 nos), Lakshmipur | n | n | n | n | n | 0 | 100 | -100 | 0 | - | - | After major construction of cyclone shelter
11.4) Field raising near cyclone shelters (13 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 18.6492 | 18.44 | 18.44 | work started for 13 & final for 12
12) Roads
Total rural roads (54.6 km) | 100 | 100 | 100 | 100 | 100 | 98.9705 | 100 | -1.0295 | 111.3321 | 107.92 | 106.93
Total paved roads (18.7 km) | 93.9572 | 93.9572 | 93.9572 | 93.9572 | 93.9572 | 75.6767 | 100 | -24.3233 | 737.384 | 316.5 | 278.49
12.1) paved (7 km), Lakshmipur | y | y | y | y | y | 78.5714 | 100 | -21.4286 | 259.803 | 104.63 | 71.92 | work started in both groups
12.4) rural, 13 roads (22.6 km), Lakshmipur | y | y | y | y | y | 98.8938 | 100 | -1.1062 | 78.16 | 43.87 | 38.57 | W.O. issued
12.2) paved (11.57 km), Noakhali | y | y | y | y | y | 73.7597 | 100 | -26.2403 | 399.421 | 168 | 168 | work started on all 5 groups
12.3) paved (1.13 km), Noakhali | n | n | n | n | n | 0 | 100 | -100 | 0 | 0 | 0 | will be divided over the other roads
0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -100 | 0 | 0 | 0 | work started on 12 roads
12.5) 13 rural roads (32 km), Noakhali | y | y | y | y | y | 98.9375 | 100 | -1.0625 | 111.3321 | 107.92 | 106.93 | 13 started, 12 made final
12.6) 8 earthen roads for cyclone shelter approach (2.7 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 7.43 | 6.6 | 6.6 | 7 made final out of 8

## data status
|  | Design available | Design concurred | Estimate concurred | Floating tender | Work order given | physical progress | current planning
bwdb | sea dyke | 100 | 100 | 100 | 100 | 100 | 88.0352 | 100
| interior dyke | 100 | 100 | 100 | 100 | 100 | 93.1041 | 100
| guide dykes | 100 | 100 | 100 | 100 | 100 | 100 | 100
| re-excavations jarirdona | 100 | 100 | 100 | 100 | 100 | 97.5813 | 93.6034
| re-excavation bagardona | 100 | 100 | 100 | 100 | 100 | 100 | 100
| Jarirdona shortcut | 100 | 100 | 100 | 100 | 100 | 98.8571 | 93.6034
| Secondary drainage | 100 | 100 | 100 | 100 | 100 | 100 | 100
| Gabtali sluice | 100 | 100 | 100 | 100 | 100 | 95 | 90
| 2 sluices | 100 | 100 | 100 | 100 | 100 | 32.5 | 60
| closures | 100 | 100 | 100 | 0 | 0 | 0 | 0
lged | bridges | 100 | 100 | 100 | 100 | 100 | 97 | 100
| busstand | 100 | 100 | 100 | 100 | 100 | 95 | 100
| community ponds | 100 | 100 | 100 | 100 | 100 | 97.7143 | 100
| box culverts | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 94.2143 | 100
| pipe culverts | 100 | 100 | 100 | 100 | 100 | 53.5938 | 67.5
| cyclone shelters | 100 | 100 | 100 | 100 | 100 | 85.75 | 100
| rural roads | 100 | 100 | 100 | 100 | 100 | 98.9705 | 100
| paved roads | 93.9572 | 93.9572 | 93.9572 | 93.9572 | 93.9572 | 75.6767 | 100
dphe | deep tube wells | 100 | 100 | 66.6667 | 66.6667 | 66.6667 | 61.15 | 100
| ponds with sand filter | 100 | 100 | 100 | 100 | 100 | 25 | 100
| public toilets | 100 | 100 | 100 | 100 | 100 | 95.15 | 100
| rainwater harvesting | 100 | 100 | 100 | 100 | 100 | 98 | 100
| single pit latrines | 70.5882 | 70.5882 | 70.5882 | 70.5882 | 70.5882 | 71.8953 | 100
mol | twin houses | 100 | 100 | NA | 100 | 0 | 0 | 30
| community ponds | 100 | 100 | NA | 100 | 100 | 66.6667 | 100
| settlement programme | 100 | 100 | 100 | 100 | 86.2069 | 77.227 | 100

## hulp sheet
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.2) box culverts (7 no's), Lakshmipur | y | y | y | y | y | 76.8571 | 5 | 5 | 5 | 5 | 5
10.3) box culverts (21 nos), Noakhali | y | y | y | y | y | 100 | 21 | 21 | 21 | 21 | 21
10.6) pipe culverts (31 nos), Noakhali | y | y | y | y | y | 88.0645 | 31 | 31 | 31 | 31 | 31
10.5) pipe culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 7 | 7 | 7 | 7 | 7
10.7) pipe culverts (26 nos), Noakhali | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0
12.4) rural, 13 roads (22.6 km), Lakshmipur | y | y | y | y | y | 98.8938 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5
12.5) 13 rural roads (32 km), Noakhali | y | y | y | y | y | 98.9375 | 32 | 32 | 32 | 32 | 32
12.6) 8 earthen roads for cyclone shelter approach (2.7 km), Noakhali | y | y | y | y | y | 100 | 2.7 | 2.7 | 2.7 | 2.7 | 2.7
12.1) paved (7 km), Lakshmipur | y | y | y | y | y | 78.5714 | 7 | 7 | 7 | 7 | 7
12.2) paved (11.57 km), Noakhali | y | y | y | y | y | 73.7597 | 10.57 | 10.57 | 10.57 | 10.57 | 10.57
12.3) paved (1.13 km), Noakhali | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0
9.1) 19 ponds, Lakshmipur (4 LCS) | y | y | y | y | y | 99.1053 | 19 | 19 | 19 | 19 | 19
9.2) 15 ponds, LGED, Noakhali | y | y | y | y | y | 94.3333 | 15 | 15 | 15 | 15 | 15
9.3) 15 ponds, LCS, Noakhali | y | y | y | y | y | 99.3333 | 15 | 15 | 15 | 15 | 15
11.1) 7 cyclone shelters, Lakshmipur | y | y | y | y | y | 59.2857 | 7 | 7 | 7 | 7 | 7
11.2) 13 cyclone shelters, Noakhali | y | y | y | y | y | 100 | 13 | 13 | 13 | 13 | 13
13.1) deep tube wells (400 nos), Lakshmipur & Noakhali | y | y | y | y | y | 91.725 | 400 | 400 | 400 | 400 | 400
13.3) deep tube wells (200 nos), Noakhali & Lakshmipur | y | y | n | n | n | 0 | 200 | 200 | 0 | 0 | 0
14.1) 10 ponds with sf, Lakshmipur | y | y | y | y | y | 25 | 10 | 10 | 10 | 10 | 10
16.1) rainwater harvesting (18 nos), Lakshmipur | y | y | y | y | y | 98 | 20 | 20 | 20 | 20 | 20
17.1) single pit latrines (8500 nos), Noakhali & Lakshmipur | y | y | y | y | y | 71.8953 | 6 | 6 | 6 | 6 | 6
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1) Re-excavation Jarirdona, 0km-2.625km (2.625 km), Lakshmipur | y | y | y | y | y | 98.4762 | 2.625 | 2.625 | 2.625 | 2.625 | 2.625
3.2) Re-excavation Jarirdona, 2.625km-3.535km (0.91 km), Lakshmipur | y | y | y | y | y | 95 | 0.91 | 0.91 | 0.91 | 0.91 | 0.91
3.3) Re-excavation Baggardona, 7.035km-13.935km (6.9 km), Noakhali | y | y | y | y | y | 100 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9
3.4) Re-excavation Baggardona, 13.935km-17.035km (3.1 km), Lakshmipur | y | y | y | y | y | 100 | 3.1 | 3.1 | 3.1 | 3.1 | 3.1
1.1) Sea dyke, 0.63km-3.365km (2.5 km), Lakshmipur | y | y | y | y | y | 81.892 | 2.735 | 2.735 | 2.735 | 2.735 | 2.735
1.2) Sea dyke, 3.365km-5.085km (1.72 km), Lakshmipur | y | y | y | y | y | 98 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72
1.3) Sea dyke, 5.085km-8.585km (3.5 km), Noakhali | y | y | y | y | y | 100 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
1.4) Sea dyke, 8.585km-11.5km (2.915 km), Noakhali | y | y | y | y | y | 73.5535 | 2.915 | 2.915 | 2.915 | 2.915 | 2.915
1.5) Interior dyke, 11.5km-19.5km (8 km), Noakhali | y | y | y | y | y | 93.1041 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
4.1) Jarirdona shortcut, 3.535km-3.925km (0.39 km), Lakshmipur | y | y | y | y | y | 99 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39
4.2) Jarirdona shortcut, 3.925km-6.035km (2.11 km), Lakshmipur | y | y | y | y | y | 98.2891 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11
4.3) Jarirdona shortcut, 6.035km-7.035km (1 km), Noakhali | y | y | y | y | y | 100 | 1 | 1 | 1 | 1 | 1
4.4) drainage channel Gabtali khal (6.155 km), Lakshmipur | y | y | y | y | y | 98.7308
4.5) improvement secondary drainage (6 km), Lakshmipur | y | y | y | y | y | 100 | 6 | 6 | 6 | 6 | 6
4.6) improvement secondary drainage (15 km), Noakhali | y | y | y | y | y | 100 | 15 | 15 | 15 | 15 | 15
15.1) public toilets (20 nos), Lakshmipur & Noakhali | y | y | y | y | y | 95.15 | 20 | 20 | 20 | 20 | 20
2.1) Guide dyke cum rural road, 7.035km-10.00km (2.965 km), Noakhali | y | y | y | y | y | 100 | 2.965 | 2.965 | 2.965 | 2.965 | 2.965
19.1.1) Excavation of 25 cv ponds, Noakhali and Lakshmipur | y | y | y | y | y | 89.5833 | 25 | 25 | 25 | 25 | 25
Excavation of 10 cv ponds (actually 4 needed), Noakhali & Lakshmipur | y | y | y | y | n | 0 | 4 | 4 | 4 | 4 | 0