## Sheet1
Annex-6
Itemwise FA Budget & Reimbursement Position under CDSP-III as on 30th June 2009
SL. No. | Item | Revised Budget Allocation (BDT in lakh) | Expenditure incurred & claimed by IAs (BDT in lakh) | Recommended by TA Team (BDT in lakh)
A. | Baggardona Upstream area
(Civil Work)
1 | Re-excavation of Baggardona
| (Bhulua river) River | 680 | 332.54 | 241.09
2 | Re-excavation of Jarirdona khal | 408 | 172.15 | 90.15
3 | Short cut Drainage cannel (Jarirdona) | 573 | 375.92 | 328.81
| Sub-Total of A. | 1661 | 880.61 | 660.05
B. | Boyer Char & Char Moradona area
1 | Drainage Sluice (DS-2) | 550 | 352.65 | 234.14
2 | Closure-1 (at D/S of steamer ghat) | 232 | 0 | 0
3 | Closure-2 (at CBD-I) | 62 | 0 | 0
4 | Embankment in Boyer Char | 896 | 516.78 | 432.25
5 | Guide dyke cum rural road | 87 | 80.77 | 80.77
6 | Short cut Drainage channel at Gabtoli | 272 | 200.35 | 200.35
7 | Re-excavation of Banskhali Khal at D/S of sluice | 23 | 0 | 0
8 | Improvement of Secondary drainage channel | 279.87 | 8.67 | 4.37
9 | Drainage cum flushing sluices | 250 | 8 | 0
| Sub-Total of B. | 2651.87 | 1167.22 | 951.88
C. | Other cost
1 | Additional drainage study | 99.2 | 44.66 | 44.66
| Sub-Total of C. | 99.2 | 44.66 | 44.66
Total of BWDB |  | 4412.07 | 2092.49 | 1656.59
Name of Agency : LGED
Boyer Char & Char Moradona area
i) | Rural Infrastructure
| a) Road (Paved) | 680 | 367.15 | 350.65
| b) Rural Road (Earthen) | 215 | 151.75 | 148.67
| c) Bridge | 200 | 185.05 | 147.08
| d) Foot bridge | 10 | 2.94 | 0
| e) Box culvert | 355 | 214.64 | 152.11
| f) Pipe Culvert | 50 | 44.45 | 43.56
ii) | Settlement Infrastructure
| a) Cyclone shelter | 1200 | 895.48 | 876.84
| b) Community Pond | 140 | 61.73 | 61.61
| c) Bus stand | 60 | 24.75 | 24.75
Total of LGED |  | 2910 | 1947.94 | 1805.27
Name of Agency : DPHE
A. | Boyer Char area
| a) Single pit latrine | 187 | 86.77 | 82.61
| b) Public Toilet in Market | 140 | 88.41 | 87.11
| c) Deep Tubewell | 352 | 127.83 | 115.46
d) Development of community pond with
| arrangement of PSF | 60 | 0 | 0
| e) Rain Water Harvesting | 3 | 2.19 | 2.187
| Sub-Total of A. | 742 | 305.2 | 287.367
B. | Other cost
| a) Training software activities | 50 | 0 | 0
| b) Test Tubewell | 8 | 1.49 | 1.16
| Sub-Total of B. | 58 | 1.49 | 1.16
Total of DPHE |  | 800 | 306.69 | 288.527
Name of Agency : FD
A. | Plantation Programme
1 | Establishment of Mangrove plantation | 30.5 | 30.5 | 30.5
2 | Establishment of Foreshore Plantation | 204.36 | 26.08 | 26.08
3 | Establishment of strip Plantation
| a) Embankment Plantation | 14.4 | 9.11 | 8.68
| b) Feeder Road Plantation | 7.9 | 7.9 | 7.9
4 | Village/Homestead Plantation | 49 | 48.98 | 48.98
| Sub-Total of A. | 306.16 | 122.57 | 122.14
B. | Plantation Maintenance
| a) Mangrove plantation | 15.6 | 9.26 | 9.26
| b) Foreshore Plantation | 52.33 | 0.89 | 0.89
| c) Embankment Plantation | 20.93 | 1.03 | 0.67
| d) Feeder Road Plantation | 3.5 | 2.28 | 2.28
| Sub-Total of B. | 92.36 | 13.46 | 13.1
C. | Other cost
| a) Contingencies | 6.37 | 6.38 | 4.65
| b) Local Training & Logistic | 55.15 | 48.14 | 33.37
| c) Manpower (MR Basis) | 75.39 | 52.82 | 52.82
| Sub-Total of C. | 136.91 | 107.34 | 90.84
Total of FD |  | 535.43 | 243.37 | 226.08
Name of Agency : DAE
A. | Boyerchar area
1 | Field Demonstration | 20.4 | 19.32 | 17.49
2 | Farmers Training (Local) | 17.28 | 15.36 | 11.22
3 | Farmer Motivation Tour | 11.2 | 9.86 | 8.974
4 | Workshop/ saminar (Local) | 3.12 | 3.08 | 2.14
5 | On-farm testing of new technology | 3.4 | 1.18 | 0.9
6 | Procurement of support materials | 7 | 4.1 | 4
7 | Training of Trainers | 2.4 | 2.08 | 1.32
8 | Printing Extension Materials | 1 | 1 | 0.7
9 | Contingency | 0.7 | 0.7 | 0.6
Total of DAE |  | 66.5 | 56.68 | 47.344
Name of Agency : MoL
A. | Settlement Progamme
| a) Rehabilitation of 3000 families | 496 | 62.04 | 60.04
Total of MoL |  | 496 | 62.04 | 60.04
Grand Total (BWDB+LGED+DPHE+FD+DAE+MoL) |  | 9220 | 4709.21 | 4083.851

## Sheet2
| E/R |  | C/S |  | Pond | BC
| 517890 |  | 989887 |  | 51673
| 295480 |  | 458178 |  | 65672
| 350363 |  | 834794 |  | 57529
| 325738 |  | 472787 |  | 57632
| 362460 |  | 1113663 |  | 41171
| 357714 |  | 1009784 |  | 37958
| 321021 |  | 435973 |  | 51159
| 297593 |  | 898742 |  | 65229
| 208055 | 208055 | 893204 |  | 63291
| 376711 |  | 898484 |  | 59742
| 3413025 | 208055 | 8005496 |  | 57647
71253
| 204362 |  | 1363279 | 254250 | 679956 | 538066
| 150195 |  | 951430 |  |  | 648257
| 51090 |  | 278416 |  |  | 1186323
| 37549 |  | 897226
| 443196 |  | 108993
1055103
1348184
1361099
1094377
559655
569923
713070
|  |  | 10300755 | 254250
Total | 3856221 | 208055 | 18306251 | 254250 | 679956 | 1186323