## Sheet1
Annex-6
Itemwise FA Budget & Reimbursement Position under CDSP-III as on 31st December 2009
Sl. No. | Item | 2nd Revised Budget Allocation (BDT in lakh) | Expenditure incurred & claimed by IAs (BDT in lakh) | Recommended by TA Team (BDT in lakh)
Name of Agency: BWDB
A. | Baggardona Upstream area
(Civil Work)
1 | Re-excavation of Baggardona
| (Bhulua river) River (10 km.) | 648 | 587.61 | 587.61
2 | Re-excavation of Jarirdona khal(3.535 km) | 400 | 338.07 | 338.07
3 | Short cut Drainage cannel (Jarirdona 3.50 km) | 629 | 536.22 | 536.22
| Sub-Total of A. | 1677 | 1461.9 | 1461.9
B. | Boyer Char & Char Moradona area
1 | Drainage Sluice (DS-2, 7V-2.20x2.20m) | 570 | 426.31 | 399.14
2 | Closure-1 (D/S of steamer ghat) | 246.87 | 0 | 0
3 | Closure-2 (at CBD-I) | 113 | 0 | 0
4 | Embankment in Boyer Char (18.87 km) | 950 | 754.28 | 754.28
5 | Guide dyke cum rural road (2.96 km) | 81 | 80.77 | 80.77
6 | Short cut Drainage channel at Gabtoli (6.00 km) | 267 | 224.17 | 224.17
7 | Re-excavation of Banskhali Khal at D/S of sluice (2.10 km) | 110 | 0 | 0
8 | Improvement of Secondary drainage channel (38 km) | 68 | 30.59 | 30.59
9 | Drainage cum flushing sluices (Tanki & Chatla) | 230 | 57.13 | 49.13
| Sub-Total of B. | 2635.87 | 1573.25 | 1538.08
C. | Other cost
1 | Additional drainage study | 99.2 | 73.07 | 73.07
| Sub-Total of C. | 99.2 | 73.07 | 73.07
Total of BWDB |  | 4412.07 | 3108.22 | 3073.05
Name of Agency : LGED
Boyer Char & Char Moradona area
i) | Rural Infrastructure
| a) Road (Paved 18.75 km.) | 714 | 510.87 | 510.87
| b) Rural Road (Earthen 62 km.) | 230 | 184.32 | 184.32
| c) Bridge (3 nos.) | 200 | 187.53 | 187.53
| d) Foot bridge (1 no.) | 11 | 2.94 | 2.94
| e) Box culvert (29 nos.) | 320 | 271.55 | 271.55
| f) Pipe Culvert (40 nos.) | 55 | 45.03 | 45.03
ii) | Settlement Infrastructure
| a) Cyclone shelter (20 nos.) | 1240 | 985.31 | 977.31
| b) Community Pond (50 nos.) | 80 | 67.1 | 67.1
| c) Bus stand (1 no.) | 60 | 54.22 | 54.22
Total of LGED |  | 2910 | 2308.87 | 2300.87
Name of Agency : DPHE
A. | Boyer Char area
| a) Single pit latrine (8500 nos.) | 187 | 119.58 | 105.96
| b) Public Toilet in Market (20 nos.) | 150 | 114.3 | 105.26
| c) Deep Tubewell (600 nos.) | 300 | 165.87 | 150.97
d) Development of community pond with
| arrangement of PSF (47 nos.) | 105.75 | 2 | 0
| e) Rain Water Harvesting (60 nos.) | 13.5 | 3.07 | 3.07
| Sub-Total of A. | 756.25 | 404.82 | 365.26
B. | Other cost
| a) Training software activities (LS) | 31.15 | 1.9 | 0
| b) Test Tubewell (18 nos.) | 12.6 | 4.19 | 4.19
| Sub-Total of B. | 43.75 | 6.09 | 4.19
Total of DPHE |  | 800 | 410.91 | 369.45
Name of Agency : FD
A. | Plantation Programme
1 | Establishment of Mangrove plantation (500 ha) | 30.5 | 30.5 | 30.5
2 | Establishment of Foreshore Plantation (200 ha) | 236.4 | 26.08 | 26.08
3 | Establishment of strip Plantation
| a) Embankment Plantation (28.5 km.) | 14.4 | 12.03 | 12.03
| b) Feeder Road Plantation (120 km.) | 15.78 | 7.9 | 7.9
4 | Village afforestation (52 nos.) | 63.844 | 48.98 | 48.98
| Sub-Total of A. | 360.924 | 125.49 | 125.49
B. | Plantation Maintenance
| a) Mangrove plantation (500 ha) | 13 | 13 | 13
| b) Foreshore Plantation (200 ha) | 11.65 | 0 | 0
| c) Embankment Plantation (28.5 km) | 14.71 | 6.55 | 6.55
| d) Feeder Road Plantation (60 ha) | 2.334 | 2.34 | 2.34
| Sub-Total of B. | 41.694 | 21.89 | 21.89
C. | Other cost
| a) Contingencies (LS) | 6.37 | 6.14 | 5.97
| b) Local Training & Logistic (1800 person) | 51.052 | 51.31 | 40.35
| c) Manpower (MR Basis) | 75.39 | 59.06 | 59.06
| Sub-Total of C. | 132.812 | 116.51 | 105.38
Total of FD |  | 535.43 | 263.89 | 252.76
Name of Agency : DAE
A. | Boyerchar area
1 | Demonstration (7 items) | 20.4 | 20.3 | 19.89
2 | Farmers Training (Local 288 nos.) | 17.28 | 17.28 | 17.28
3 | Farmer Motivation Tour (32 nos.) | 11.2 | 11.2 | 11.2
4 | Workshop/ seminar (Local 6 nos.) | 3.12 | 3.08 | 3.08
5 | On-farm testing of new technology (LS) | 3.4 | 1.3 | 1.3
6 | Procurement of support materials (LS) | 7 | 4.1 | 4.1
7 | Training of Trainers (9 nos.) | 2.4 | 2.08 | 2.08
8 | Printing Extension Materials (LS) | 1 | 1 | 1
9 | Contingency (LS) | 0.7 | 0.7 | 0.7
Total of DAE |  | 66.5 | 61.04 | 60.63
Name of Agency : MoL
A. | Settlement Progamme
| a) Construction of twin houses | 33.26 | 0 | 0
| b) Rehabilitation of 3000 families | 462.74 | 141.91 | 141.91
Total of MoL |  | 496 | 141.91 | 141.91
Grand Total (BWDB+LGED+DPHE+FD+DAE+MoL) |  | 9220 | 6294.85 | 6198.68

## Sheet2
| E/R |  | C/S |  | Pond | BC
| 517890 |  | 989887 |  | 51673
| 295480 |  | 458178 |  | 65672
| 350363 |  | 834794 |  | 57529
| 325738 |  | 472787 |  | 57632
| 362460 |  | 1113663 |  | 41171
| 357714 |  | 1009784 |  | 37958
| 321021 |  | 435973 |  | 51159
| 297593 |  | 898742 |  | 65229
| 208055 | 208055 | 893204 |  | 63291
| 376711 |  | 898484 |  | 59742
| 3413025 | 208055 | 8005496 |  | 57647
71253
| 204362 |  | 1363279 | 254250 | 679956 | 538066
| 150195 |  | 951430 |  |  | 648257
| 51090 |  | 278416 |  |  | 1186323
| 37549 |  | 897226
| 443196 |  | 108993
1055103
1348184
1361099
1094377
559655
569923
713070
|  |  | 10300755 | 254250
Total | 3856221 | 208055 | 18306251 | 254250 | 679956 | 1186323