## Overview BWDB
Table 1 - BWDB | Design available (y/n) | Design concurred (y/n) | Estimate concurred (y/n) | Floating tender (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Invested amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks | Estimated amount Tk. In Lakh
Item of work | [6 empty] | 2010-06-30 |  |  | 92.3005
Total BWDB | 100 | 100 | 100 | 100 | 100 | 96.1968 | 100 | -3.8032 | 4236.9013 | 3910.6814 | 3350.5813 | 3342.5813
1) Embankments | [10 empty] | 779.619 | 779.619
Total sea dyke (10.87 km) | 100 | 100 | 100 | 100 | 100 | 95.1527 | 100 | -4.8473 | 542.6342 | 510.2429 | 445.57 | 445.57
Total interior dyke (8 km) | 100 | 100 | 100 | 100 | 100 | 97.0863 | 100 | -2.9137 | 390.65 | 379.2674 | 334.049 | 334.049
1.1) Sea dyke, 0.63km-3.365km (2.5 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 132.44 | 132.44 | 98.92 | 98.92 | Group 1 to 5 all completed
1.2) Sea dyke, 3.365km-5.085km (1.72 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 76.12 | 76.12 | 70.44 | 70.44 | Group 4 completed
1.3) Sea dyke, 5.085km-8.585km (3.5 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 154.8742 | 154.8742 | 153.35 | 153.35 | Group 1- 5 all completed
1.4) Sea dyke, 8.585km-11.5km (2.915 km), Noakhali | y | y | y | y | y | 81.9245 | 100 | -18.0755 | 179.2 | 146.8088 | 122.86 | 122.86 | Group 6 is in progress & Group 7 completed
1.5) Interior dyke, 11.5km-19.5km (8 km), Noakhali | y | y | y | y | y | 97.0863 | 100 | -2.9137 | 390.65 | 379.2674 | 334.049 | 334.049 | 5 Groups, Group 8 is in progress and Group-09 to 12 all completed
2) Individual guide dyke
Total guide dyke (2.965 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 82.09 | 82.09 | 80.77 | 80.77
2.1) Guide dyke cum rural road, 7.035km-10.00km (2.965 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 82.09 | 82.09 | 80.77 | 80.77 | 2 groups, all completed.
3) Re-excavations
Total Jarirdona (3.535 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 387.12 | 387.12 | 367.4903 | 367.4903
Total Bagardona (10 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 644.942 | 644.942 | 626.034 | 626.034
3.1) Re-excavation Jarirdona, 0km-2.625km (2.625 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 281.54 | 281.54 | 272.04 | 272.04 | 4 groups, all completed
3.2) Re-excavation Jarirdona, 2.625km-3.535km (0.91 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 105.58 | 105.58 | 95.4502 | 95.4502 | 1 group, completed
3.3) Re-excavation Baggardona, 7.035km-13.935km (6.9 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 419.74 | 419.74 | 404.969 | 404.969 | 5 groups, all completed.
3.4) Re-excavation Baggardona, 13.935km-17.035km (3.1 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 225.202 | 225.202 | 221.065 | 221.065 | 3 groups, all completed.
4) Excavations
4) Short cuts
Total Jarirdona shortcut (3.5 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 592.79 | 592.79 | 576.582 | 576.582
Total Gabtali khal (6.155 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 266.36 | 266.36 | 240.183 | 240.183
Total Secondary drainage channel (21 km) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 36.68 | 30.15 | 30.6 | 30.6
4.1) Jarirdona shortcut, 3.535km-3.925km (0.39 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 62.67 | 62.67 | 57.766 | 57.766 | 1 group, completed
4.2) Jarirdona shortcut, 3.925km-6.035km (2.11 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 371.15 | 371.15 | 360.066 | 360.066 | 5 groups, all completed
4.3) Jarirdona shortcut, 6.035km-7.035km (1 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 158.97 | 158.97 | 158.75 | 158.75 | 2 groups, completed.
4.4) drainage channel Gabtali khal (6.155 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 266.36 | 266.36 | 240.183 | 240.183 | 4 groups, all completed
4.5) improvement of secondary drainage (6 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 6.53 | 6.53 | 6.39 | 6.39 | 1 group, completed
4.6) improvement secondary drainage (15 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 30.15 | 30.15 | 24.21 | 24.21 | 1 group, completed
110
4.7) improvement of Banshkhali khal (2.1 km) | y | y | y | y | y | 100 | 100 | 0 | 109.21 |  | 0 | 0 | completed
5) Sluices (3 nos)
Total sluices | 100 | 100 | 100 | 100 | 100 | 93.5022 | 100 | -6.4978 | 715.7251 | 669.219 | 547.237 | 539.237
5.1) Gabtali Khal sluice, Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 508.8468 | 508.8468 | 487.541 | 487.541
5.2) Tankir Khal sluice, Noakhali | y | y | y | y | y | 80 | 100 | -20 | 104.2694 | 83.4155 | 41.13 | 37.13 | work is in progress,
5.3) Chatla Khal sluice, Noakhali | y | y | y | y | y | 75 | 100 | -25 | 102.609 | 76.9567 | 18.566 | 14.566 | work is in progress,
6) Closures (2 nos)
Total closures | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 348.5 | 348.5 | 0 | 0 |  | 349.04
6.1) closure 1 (Downstream Banshkhali), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 242 | 242 | 0 | 0 | completed | 241.93
6.2) closure 2 (CBD-1), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 106.5 | 106.5 | 0 | 0 | completed | 107.11
Maintenance khals
Maintenance khals (17 nos) | y | y | y | y | y | 100 | #REF! | #REF! | 133.5505 | 133.5505 | 0 | 0
7.1) Additional drainage study at upper Baggardona | - | - | - | - | - | 100 | 100 | 0 | 81.18 | 81.18 | 81.178 | 81.178 | final Report submitted | Name of work | Total cost | Average progress %
7.2) Emergency Protective work for Jaridona, Laxmipur | - | - | - | - | - | 100 | 100 | 0 | 21.02 | 21.02 | 20.888 | 20.888 | work done in June 2009
7.3) Upper Baggardona Monitoring work | y | y | y | y | y | 45 | 49.4505 | -4.4505 | 18 | 8.1 | - | - | Monitoring started from 1st March 2010 by IWM | Secondary drainage | 68 | 55.2632
7.4) Additional improvement of secondary drainage channel (13.5 km) | y | y | y | y | n | 0 | 100 | -100 | - | 0 | - | - | NoA issued
7.4) Additional improvement of secondary drainage channel (3.5 km) | n | n | n | n | n | 0 | 100 | -100 | - | 0 | - | - | Design & estimate under process

## Overview LGED
Table 2 - LGED | Design available (y/n) | Design concurred (y/n) | Estimate concurred (y/n) | Floating tender (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2010-06-30
Total LGED | 99.1018 | 99.1018 | 99.1018 | 99.1018 | 99.1018 | 96.9089 | 100 | -3.0911 | 2782.8795 | 2452.508 | 2452.508
7) Bridges | 100 | 100 | 100 | 100 | 100
7.1) bridges (3 no's), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 196.09 | 197.266 | 197.266 | all completed
7.2) foot bridge (1 no), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 9.3977 | 9.402 | 9.402 | completed
8) Busstand | 100 | 100 | 100 | 100 | 100
8.1) Busstand, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 56.7459 | 54.22 | 54.22 | completed
9) Community ponds
Total community ponds (49 nos.) | 100 | 100 | 100 | 100 | 100 | 99.7959 | 100 | -0.20408 | 74.9549 | 67.384 | 67.384
9.1) 19 ponds, Lakshmipur (4 LCS) | y | y | y | y | y | 100 | 100 | 0 | 25.36 | 24.82 | 24.82 | all completed
9.2) 15 ponds, LGED, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 19.6449 | 15.27 | 15.27 | all completed
9.3) 15 ponds, LCS, Noakhali | y | y | y | y | y | 99.3333 | 100 | -0.66667 | 29.95 | 27.294 | 27.294 | one pond partly to be completed
10) Culverts
Total box culverts (28 nos.) | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 95.6897 | 100 | -4.3103 | 290.58 | 277.686 | 277.686
Total pipe culverts (38 nos.) | 100 | 100 | 100 | 100 | 100 | 98.6842 | 100 | -1.3158 | 53.6503 | 45.03 | 45.03
10.1) box culverts (7 no's), Lakshmipur | y | y | y | y | y | 96.4286 | 100 | -3.5714 | 61.85 | 49.716 | 49.716 | out of 7, 6 completed & other is in progress
10.2) box culverts (21 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 228.73 | 227.97 | 227.97 | all structures completed
10.3) pipe culverts (31 nos), Noakhali | y | y | y | y | y | 98.3871 | 100 | -1.6129 | 44.9703 | 36.51 | 36.51 | out of 31, 30 completed, 1 is in progress.
10.4) pipe culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 8.68 | 8.52 | 8.52 | all 7 completed
11) Cyclone shelters
Total cyclone shelters (20 nos.) | 100 | 100 | 100 | 100 | 100 | 99.2 | 100 | -0.8 | 1198.7224 | 1084.467 | 1084.467
11.1) 7 cyclone shelters, Lakshmipur | y | y | y | y | y | 97.7143 | 100 | -2.2857 | 425.7659 | 318.014 | 318.014 | progress for all 7 is within 96% to 98%.
11.2) 13 cyclone shelters, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 731.9973 | 732.132 | 732.132 | all 13 completed
11.3) Field raising near cyclone shelters (7 nos), Lakshmipur | y | y | y | y | y | 97 | 100 | -3 | 22.3101 | - | - | 5 completed & other two 90% completed
11.4) Field raising near cyclone shelters (13 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 18.6492 | 22.421 | 22.421 | all 13 completed
11.5) Additional furniture supply to 15 cyclone shelters, Noakhali | y | y | y | y | y | 80 | 100 | -20 | 5.37 | 4.62 | 4.62 | all furniture supplied
12) Roads
Total rural roads (55.00 km) | 100 | 100 | 100 | 100 | 100 | 99.8818 | 100 | -0.11817 | 189.4921 | 184.34 | 184.34
Total paved roads (18.70 km) | 99.9572 | 99.9572 | 99.9572 | 99.9572 | 99.9572 | 100 | 100 | 0 | 662.824 | 532.663 | 532.663
12.1) paved (7 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 259.803 | 229.793 | 229.793 | 3 groups, all completed
12.2) paved (11.56 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 399.421 | 299.28 | 299.28 | All 5 groups completed.
12.3) paved (0.14 km), Noakhali | n | n | n | n | n | 0 | 100 | -100 | 3.6 | 3.59 | 3.59 | will be spent for the revision purpose of ongoing works
12.4) 13 rural roads (22.6 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 78.16 | 75.03 | 75.03 | All 13 completed
12.5) 13 rural roads (32 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 111.3321 | 109.31 | 109.31 | all 13 completed
12.6) 8 earthen roads for cyclone shelter approach (2.7 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 7.43 | 7.28 | 7.28 | all 8 completed
13) Additional works: | [8 empty] | 42.992 |  |  |  | Name of Works | Total Cost (lac) | Average progress in%
Maintenance
Maintenance (12 items) | y | y | y | y | y | 0 | 0 | 0 | 99.2192 | 0 | 0 | for 6 items contracts have been awarded, the other 6 have to be retendered
13.1) Box culvert 1 no, Lakshmipur | y | y | y | y | y | 0 | 100 | -100 | 9.1461 | - | - | Work Order issued on 23rd June 2010, work yet not started. | Box culvert | 320 | 92.39
13.2) Pipe culvert 1 no, Noakhali | y | y | y | y | y | 0 | 100 | -100 | 2.7011 | - | - | work completed | Pipe culvert | 58 | 96.1538
13.3) 16 Rural roads (earthen, 6.18km, additional & CV house connecting road ), Noakhali | y | y | y | y | y | 98 | 100 | -2 | 24.7531 | - | - | 15 roads completed out of 16 & the other 60% done | Rural earthen roads | 222 | 101.1119
13.4) Additional work for bus stand on Tankir Bazar (Water supply, drain etc.) | y | y | y | y | y | 95 | 100 | -5 | 3.1959 |  |  | Work is in progress
13.5) Emergency work of Steamerghat to Chairmanghat road (HBB road construction) | y | y | y | y | y | 100 | 100 | 0 | 3.1959 |  |  | Work completed

## Overview DPHE
Table 3 - DPHE | Design available (y/n) | Design concurred (y/n) | Estimate concurred (y/n) | Floating tender (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2010-06-30
Total DPHE | 100 | 100 | 100 | 100 | 100 | 86.4339 | 100 | -13.5661 | 609.467 | 468.062 | 397.645
13) Deep tube wells
Total deep tube wells (600) | 100 | 100 | 100 | 100 | 100 | 79.85 | 100 | -20.15 | 301.8595 | 181.157 | 160.463
13.1) deep tube wells (400 nos), Lakshmipur & Noakhali | y | y | y | y | y | 99.075 | 100 | -0.925 | 200.75 | 181.157 | 160.463 | 398 sunk out of 400
13.3) deep tube wells (200 nos), Noakhali, Lakshmipur & new chars | y | y | y | y | y | 41.4 | 100 | -58.6 | 101.1095 | - | - | work is in progress
13.4) test deep tube wells (8 nos), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 4.96 | 4.2 | 4.2 | all sunk
14) Pond with sand filter
14.1) 10 ponds with sf, Lakshmipur | y | y | y | y | y | 90 | 100 | -10 | 4.9275 | 4.786 | 2 | all almost finished
15) Public toilets
15.1) public toilets (20 nos), Lakshmipur & Noakhali (With water facilities) | y | y | y | y | y | 99.8 | 100 | -0.2 | 137.12 | 125.707 | 113.835 | 18 completed & 2 almost completed
16) Rainwater harvesting
16.1) rainwater harvesting (18 nos), Lakshmipur | y | y | y | y | y | 98 | 100 | -2 | 3.53 | 3.07 | 3.07 | all completed (rectification required)
17) Single pit latrines
Total single pit latrines (8500 nos) | 100 | 100 | 100 | 100 | 100 | 87.5635 | 100 | -12.4365 | 157.07 | 142.59 | 110.721
17.1) single pit latrines (8500 nos), Noakhali & Lakshmipur | y | y | y | y | y | 87.5635 | 100 | -12.4365 | 157.07 | 142.59 | 110.721 | cast:7500, installed: 7100
18) Software Training | NA | NA | NA | NA | Na | 6 | 100 | -94 | 31.15 | 6.552 | 3.366 | two sessions on public toilet user group training completed.
19) Additional works | [13 empty] | Tendered/Est amount (Additional) | RDPP-1 | Total |  |  | Average Progress
19.1) ponds with sf for 37 nos | y | y | y | y | y | 60 | 100 | -40 | 79.92 | - | - | work is in progress | PSF | 81.41 | 4.93 | 86.34 |  | 86 | 66.383 | %
19.2) rain water harvesting 42 nos | y | y | y | y | y | 70 | 100 | -30 | 10.16 | - | - | work is in progress | RWHS | 10.98 | 3.53 | 14.51 | say | 13.5 | 78.4 | %
19.3) test tube wells 10 nos in new chars | y | y | y | y | y | 70 | 100 | -30 | 7.15 | - | - | work is in progress | TTW | 7.15 | 4.96 | 12.11 |  | 12 | 83.3333 | %
[13 empty] | Deep Tub wells | 108.259 | 200.75 | 309.009 | say | 300 | 79.85

## Overview MoL
Table 4 - MoL | Design available (y/n) | Design concurred (y/n) | Estimate concurred (y/n) | Floating tender (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2010-06-30
Total MoL | 100 | 100 | 100 | 100 | 100 | 48.7771 | 85 | -36.2229 | 632.7279 | 141.91 | 60.04
18) Construction work in cluster villages
Total construction work (128 twin houses & 8 ponds GoB) | 100 | 100 | NA | 100 | 100 | 37.5 | 100 | -62.5 | 251.5874 | 0 | 0
18.1) construction of twin houses (128 nos), Lakshmipur & Noakhali | y | y | NA | y | y | 25 | 100 | -75 | 200.6944 | - | - | work started at Mufti Huzur, Dahakaiya Samj ponds & at 10 No.Adarshagram for 35 nos
18.2) construction of 6 ponds, Lakshmipur & Noakhali | y | y | NA | y | y | 100 | 100 | 0 | 35.503 | - | - | all completed
18.3) construction of 2 ponds, Lakshmipur & Noakhali | y | y | NA | y | y | 0 | 100 | -100 | 15.39 | - | - | w.o. issued
19) Settlement programme (RPA) | [5 empty] | 52.4049
19.1)Total : excavation of CV ponds (29 cv ponds) | 100 | 100 | 100 | 100 | 100 | 83.5489 | 100 | -16.4511 | 178.4005 | 123.18 | 50.04
19.1.1) Excavation of 25 cv ponds, Noakhali and Lakshmipur | y | y | y | y | y | 96.9167 | 100 | -3.0833 | 149.1705 | 123.18 | 50.04 | Out of 25, 21 completed & 4 are in progress
19.1.2) Excavation of 4 cv ponds, Noakhali and Lakshmipur | y | y | y | y | y | 0 | 100 | -100 | 29.23 | - | - | w.o. issued
19.2)Total house shifting, 774 families from out side the alignment of embankment and 256 directly affected to be shifted to twin houses. | - | - | - | - | - | 25 | 100 | -75 | 202.74 | 18.73 | 10 | 375 families shifted inside & 241 temporary shifted from the alignment of infrastructures.

## Maintnance
Table 5 - MAINTENANCE | Design available (y/n) | Design concurred (y/n) | Estimate concurred (y/n) | Floating tender (y/n) | Work order given (y/n) | Physical progress % | Planned progress % | Progress deviation % | Contract amount (Tk. Lac) | Reimbursement claimed (Tk. Lac) | Reimbursement recommended (Tk. Lac) | Remarks
Item of work | [6 empty] | 2010-06-30 |  |  | 86.4579 | 76.7168
Total LGED | 99.1018 | 99.1018 | 99.1018 | 99.1018 | 99.1018 | 99.1565 | 100 | -0.84355 | 2634.4024 | 2277.65 | 2021.03
7) Bridges | 100 | 100 | 100 | 100 | 100
7.1) bridges (3 no's), Noakhali | 0 | y | y | y | y | 100 | 100 | 0 | 100 | 196.09 | 119.32 | Work going on in all three
7.2) foot bridge (1 no), Noakhali | 0 | y | y | y | y | 100 | 0 | 100 | 100 | 9.3977 | - | w.o. issued
8) Busstand | 100 | 100 | 100 | 100 | 100
8.1) Busstand, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 56.7459 | 17.43 | 17.43 | earth filling 75% complete
9) Community ponds
Total community ponds (49 nos.) | 100 | 100 | 100 | 100 | 100 | 99.7959 | 100 | -0.20408 | 74.9549 | 67.07 | 67.07
9.1) 19 ponds, Lakshmipur (4 LCS) | y | y | y | y | y | 100 | 100 | 0 | 25.36 | 24.82 | 24.82 | work started for 18
9.2) 15 ponds, LGED, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 19.6449 | 15.27 | 15.27 | Work started for all 15
9.3) 15 ponds, LCS, Noakhali | y | y | y | y | y | 99.3333 | 100 | -0.66667 | 29.95 | 26.98 | 26.98 | Work started for all 15
10) Culverts
Total box culverts (28 nos.) | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 95.6897 | 100 | -4.3103 | 335.5503 | 308.68 | 308.68
Total pipe culverts (64 nos.) | 100 | 100 | 100 | 100 | 100 | 98.6842 | 100 | -1.3158 | 8.68 | 8.52 | 8.52
0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -100 | 0 | 0 | 0 | work started for both
10.1) box culverts (7 no's), Lakshmipur | y | y | y | y | y | 96.4286 | 100 | -3.5714 | 61.85 | 44.2 | 44.2 | W.O. issued
10.2) box culverts (21 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 228.73 | 227.97 | 227.97 | 5 yet to start work
10.3) pipe culverts (31 nos), Noakhali | y | y | y | y | y | 98.3871 | 100 | -1.6129 | 44.9703 | 36.51 | 36.51 | work started for 28 (21 completed), 2 yet to start, 1 tender held up.
10.4) pipe culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 8.68 | 8.52 | 8.52 | work started for all 7
10.5) pipe culverts (2 nos), Noakhali | y | y | y | y | y | 0 | 100 | -100 | - | - | - | number and locations yet to be decided
11) Cyclone shelters
Total cyclone shelters (20 nos.) | 100 | 100 | 100 | 100 | 100 | 99.2 | 100 | -0.8 | 1198.7251 | 978.06 | 970.06
11.1) 7 cyclone shelters, Lakshmipur | y | y | y | y | y | 97.7143 | 100 | -2.2857 | 425.7659 | 227.74 | 219.74 | work started for 5, W.O. canceled for 2. One w.o. and one estimate under process
11.2) 13 cyclone shelters, Noakhali | y | y | y | y | y | 100 | 100 | 0 | 732 | 731.7 | 731.7 | work started for all 13
11.3) Field raising near cyclone shelters (7 nos), Lakshmipur | y | y | y | y | y | 97 | 100 | -3 | 22.3101 | - | - | After major construction of cyclone shelter
11.4) Field raising near cyclone shelters (13 nos), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 18.6492 | 18.62 | 18.62 | work started for 13 & final for 12
12) Roads
Total rural roads (54.6 km) | 100 | 100 | 100 | 100 | 100 | 99.8818 | 100 | -0.11817 | 111.3321 | 109.31 | 109.31
Total paved roads (18.7 km) | 99.9572 | 99.9572 | 99.9572 | 99.9572 | 99.9572 | 100 | 100 | 0 | 740.984 | 585.21 | 413.36
12.1) paved (7 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 259.803 | 207.31 | 71.92 | work started in both groups
12.4) 13 rural roads (22.6 km), Lakshmipur | y | y | y | y | y | 100 | 100 | 0 | 78.16 | 75.03 | 38.57 | W.O. issued
12.2) paved (11.56 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 399.421 | 299.28 | 299.28 | work started on all 5 groups
12.3) paved (0.14 km), Noakhali | n | n | n | n | n | 0 | 100 | -100 | 3.6 | 3.59 | 3.59 | will be divided over the other roads
0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -100 | 0 | 0 | 0 | work started on 12 roads
12.5) 13 rural roads (32 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 111.3321 | 109.31 | 109.31 | 13 started, 12 made final
12.6) 8 earthen roads for cyclone shelter approach (2.7 km), Noakhali | y | y | y | y | y | 100 | 100 | 0 | 7.43 | 7.28 | 7.28 | 7 made final out of 8

## data status
|  | Design available | Design concurred | Estimate concurred | Floating tender | Work order given | physical progress | current planning
bwdb | sea dyke | 100 | 100 | 100 | 100 | 100 | 95.1527 | 100
| interior dyke | 100 | 100 | 100 | 100 | 100 | 97.0863 | 100
| guide dykes | 100 | 100 | 100 | 100 | 100 | 100 | 100
| re-excavations jarirdona | 100 | 100 | 100 | 100 | 100 | 100 | 100
| re-excavation bagardona | 100 | 100 | 100 | 100 | 100 | 100 | 100
| Jarirdona shortcut | 100 | 100 | 100 | 100 | 100 | 100 | 100
| Secondary drainage | 100 | 100 | 100 | 100 | 100 | 100 | 100
| Gabtali sluice | 100 | 100 | 100 | 100 | 100 | 100 | 100
| 2 sluices | 100 | 100 | 100 | 100 | 100 | 77.5 | 100
| closures | 100 | 100 | 100 | 100 | 100 | 100 | 100
lged | bridges | 100 | 100 | 100 | 100 | 100 | 100 | 100
| busstand | 100 | 100 | 100 | 100 | 100 | 100 | 100
| community ponds | 100 | 100 | 100 | 100 | 100 | 99.7959 | 100
| box culverts | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 92.8571 | 95.6897 | 100
| pipe culverts | 100 | 100 | 100 | 100 | 100 | 98.6842 | 100
| cyclone shelters | 100 | 100 | 100 | 100 | 100 | 99.2 | 100
| rural roads | 100 | 100 | 100 | 100 | 100 | 99.8818 | 100
| paved roads | 99.9572 | 99.9572 | 99.9572 | 99.9572 | 99.9572 | 100 | 100
dphe | deep tube wells | 100 | 100 | 100 | 100 | 100 | 79.85 | 100
| ponds with sand filter | 100 | 100 | 100 | 100 | 100 | 90 | 100
| public toilets | 100 | 100 | 100 | 100 | 100 | 99.8 | 100
| rainwater harvesting | 100 | 100 | 100 | 100 | 100 | 98 | 100
| single pit latrines | 100 | 100 | 100 | 100 | 100 | 87.5635 | 100
mol | twin houses | 100 | 100 | NA | 100 | 100 | 25 | 100
| community ponds | 100 | 100 | NA | 100 | 100 | 75 | 100
| settlement programme | 100 | 100 | 100 | 100 | 100 | 83.5489 | 100
|  |  |  | Planned Progress in percent for the month of |  |  | 2010-03-15 | 2010-04-01 | 2010-05-01 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2010-12-01
LGED | Additional. Box culvert 1 no | [5 empty] | 2010-03-15: 0; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
NOA/LAK | Add. pipe culvert 1 no | [5 empty] | 2010-03-15: 0; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
| Add. Earthen road | [5 empty] | 2010-03-15: 98; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
DPHE | Additional test tube wells 8 nos | [5 empty] | 2010-03-15: 0; 2010-04-01: 100; 2010-05-01: 100; 2010-06-01: 100
| Add. PSF 37 nos | [5 empty] | 2010-03-15: 0; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
| Add RWHS | [5 empty] | 2010-03-15: 0; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
| Software Training | [5 empty] | 2010-03-15: 20; 2010-04-01: 55; 2010-05-01: 85; 2010-06-01: 100
BWDB | Re-excavation of Banshkhali khal | [5 empty] | 2010-03-15: 45; 2010-04-01: 65; 2010-05-01: 85; 2010-06-01: 100
NOA/LAK | Secondary drainage khal | [5 empty] | 2010-03-15: 0; 2010-04-01: 30; 2010-05-01: 80; 2010-06-01: 100
NOA | Baggardona Monitoring | [5 empty] | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100
LAK | Protective work | [5 empty] | 0 10: 100
NOA | Closure-01 | [5 empty] | 0 10: 55; 30 20: 70; 80 30: 90; 100 40: 100
NOA | Closure-02 | [5 empty] | 0 10: 55; 30 20: 70; 80 30: 90; 100 40: 100

## hulp sheet
Nos
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10.1) box culverts (7 no's), Lakshmipur | y | y | y | y | y | 96.4286 | 5 | 5 | 5 | 5 | 5
10.2) box culverts (21 nos), Noakhali | y | y | y | y | y | 100 | 21 | 21 | 21 | 21 | 21
10.3) pipe culverts (31 nos), Noakhali | y | y | y | y | y | 98.3871 | 31 | 31 | 31 | 31 | 31
10.4) pipe culverts (7 no's), Lakshmipur | y | y | y | y | y | 100 | 7 | 7 | 7 | 7 | 7
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12.4) 13 rural roads (22.6 km), Lakshmipur | y | y | y | y | y | 100 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5
12.5) 13 rural roads (32 km), Noakhali | y | y | y | y | y | 100 | 32 | 32 | 32 | 32 | 32
12.6) 8 earthen roads for cyclone shelter approach (2.7 km), Noakhali | y | y | y | y | y | 100 | 2.7 | 2.7 | 2.7 | 2.7 | 2.7
12.1) paved (7 km), Lakshmipur | y | y | y | y | y | 100 | 7 | 7 | 7 | 7 | 7
12.2) paved (11.56 km), Noakhali | y | y | y | y | y | 100 | 10.57 | 10.57 | 10.57 | 10.57 | 10.57
12.3) paved (0.14 km), Noakhali | n | n | n | n | n | 0 | 0 | 0 | 0 | 0 | 0
9.1) 19 ponds, Lakshmipur (4 LCS) | y | y | y | y | y | 100 | 19 | 19 | 19 | 19 | 19
9.2) 15 ponds, LGED, Noakhali | y | y | y | y | y | 100 | 15 | 15 | 15 | 15 | 15
9.3) 15 ponds, LCS, Noakhali | y | y | y | y | y | 99.3333 | 15 | 15 | 15 | 15 | 15
11.1) 7 cyclone shelters, Lakshmipur | y | y | y | y | y | 97.7143 | 7 | 7 | 7 | 7 | 7
11.2) 13 cyclone shelters, Noakhali | y | y | y | y | y | 100 | 13 | 13 | 13 | 13 | 13
13.1) deep tube wells (400 nos), Lakshmipur & Noakhali | y | y | y | y | y | 99.075 | 400 | 400 | 400 | 400 | 400
13.3) deep tube wells (200 nos), Noakhali, Lakshmipur & new chars | y | y | y | y | y | 41.4 | 200 | 200 | 200 | 200 | 200
14.1) 10 ponds with sf, Lakshmipur | y | y | y | y | y | 90 | 10 | 10 | 10 | 10 | 10
16.1) rainwater harvesting (18 nos), Lakshmipur | y | y | y | y | y | 98 | 20 | 20 | 20 | 20 | 20
17.1) single pit latrines (8500 nos), Noakhali & Lakshmipur | y | y | y | y | y | 87.5635 | 6 | 6 | 6 | 6 | 6
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1) Re-excavation Jarirdona, 0km-2.625km (2.625 km), Lakshmipur | y | y | y | y | y | 100 | 2.625 | 2.625 | 2.625 | 2.625 | 2.625
3.2) Re-excavation Jarirdona, 2.625km-3.535km (0.91 km), Lakshmipur | y | y | y | y | y | 100 | 0.91 | 0.91 | 0.91 | 0.91 | 0.91
3.3) Re-excavation Baggardona, 7.035km-13.935km (6.9 km), Noakhali | y | y | y | y | y | 100 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9
3.4) Re-excavation Baggardona, 13.935km-17.035km (3.1 km), Lakshmipur | y | y | y | y | y | 100 | 3.1 | 3.1 | 3.1 | 3.1 | 3.1
1.1) Sea dyke, 0.63km-3.365km (2.5 km), Lakshmipur | y | y | y | y | y | 100 | 2.735 | 2.735 | 2.735 | 2.735 | 2.735
1.2) Sea dyke, 3.365km-5.085km (1.72 km), Lakshmipur | y | y | y | y | y | 100 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72
1.3) Sea dyke, 5.085km-8.585km (3.5 km), Noakhali | y | y | y | y | y | 100 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
1.4) Sea dyke, 8.585km-11.5km (2.915 km), Noakhali | y | y | y | y | y | 81.9245 | 2.915 | 2.915 | 2.915 | 2.915 | 2.915
1.5) Interior dyke, 11.5km-19.5km (8 km), Noakhali | y | y | y | y | y | 97.0863 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
4.1) Jarirdona shortcut, 3.535km-3.925km (0.39 km), Lakshmipur | y | y | y | y | y | 100 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39
4.2) Jarirdona shortcut, 3.925km-6.035km (2.11 km), Lakshmipur | y | y | y | y | y | 100 | 2.11 | 2.11 | 2.11 | 2.11 | 2.11
4.3) Jarirdona shortcut, 6.035km-7.035km (1 km), Noakhali | y | y | y | y | y | 100 | 1 | 1 | 1 | 1 | 1
4.4) drainage channel Gabtali khal (6.155 km), Lakshmipur | y | y | y | y | y | 100
4.5) improvement of secondary drainage (6 km), Lakshmipur | y | y | y | y | y | 100 | 6 | 6 | 6 | 6 | 6
4.6) improvement secondary drainage (15 km), Noakhali | y | y | y | y | y | 100 | 15 | 15 | 15 | 15 | 15
15.1) public toilets (20 nos), Lakshmipur & Noakhali (With water facilities) | y | y | y | y | y | 99.8 | 20 | 20 | 20 | 20 | 20
2.1) Guide dyke cum rural road, 7.035km-10.00km (2.965 km), Noakhali | y | y | y | y | y | 100 | 2.965 | 2.965 | 2.965 | 2.965 | 2.965
19.1.1) Excavation of 25 cv ponds, Noakhali and Lakshmipur | y | y | y | y | y | 96.9167 | 25 | 25 | 25 | 25 | 25
Excavation of 10 cv ponds (actually 4 needed), Noakhali & Lakshmipur | y | y | y | y | y | 0 | 4 | 4 | 4 | 4 | 4
Additional box culvert, 1 no, Lakshmipur | [6 empty] | 1 | no
Additional pipe culvert, 1 no, Noakhali | [6 empty] | 1 | no
Additional earthen road (6.17km), Noakhali | [6 empty] | 6.18 | km