## Sheet1
Itemwise FA Budget & Reimbursement Position under CDSP-III as on 30th June 2010
Sl. No. | Item | 2nd Revised Budget Allocation (BDT in lakh) | Expenditure incurred & claimed by IAs (BDT in lakh) | Recommended by TA Team (BDT in lakh)
Name of Agency: BWDB
A. | Baggardona Upstream area
(Civil Work)
1 | Re-excavation of Baggardona
| (Bhulua river) River (10 km.) | 648 | 626.034 | 626.034
2 | Re-excavation of Jarirdona khal(3.535 km) | 400 | 367.49 | 367.49
3 | Short cut Drainage cannel (Jarirdona 3.50 km) | 629 | 597.472 | 597.472
| Sub-Total of A. | 1677 | 1590.996 | 1590.996
B. | Boyer Char & Char Moradona area
1 | Drainage Sluice (DS-2, 7V-2.20x2.20m) | 570 | 487.54 | 487.54
2 | Closure-1 (D/S of steamer ghat) | 246.87 | 0 | 0
3 | Closure-2 (at CBD-I) | 113 | 0 | 0
4 | Embankment in Boyer Char (18.87 km) | 950 | 779.619 | 779.619
5 | Guide dyke cum rural road (2.96 km) | 81 | 80.77 | 80.77
6 | Short cut Drainage channel at Gabtoli (6.00 km) | 267 | 240.183 | 240.183
7 | Re-excavation of Banskhali Khal at D/S of sluice (2.10 km) | 110 | 0 | 0
8 | Improvement of Secondary drainage channel (38 km) | 68 | 30.6 | 30.6
9 | Drainage cum flushing sluices (Tanki & Chatla) | 230 | 59.696 | 51.696
| Sub-Total of B. | 2635.87 | 1678.408 | 1670.408
C. | Other cost
1 | Additional drainage study | 99.2 | 81.178 | 81.178
| Sub-Total of C. | 99.2 | 81.178 | 81.178
Total of BWDB |  | 4412.07 | 3350.582 | 3342.592
Name of Agency : LGED
Boyer Char & Char Moradona area
i) | Rural Infrastructure
| a) Road (Paved 18.75 km.) | 714 | 532.663 | 532.663
| b) Rural Road (Earthen 62 km.) | 230 | 184.34 | 184.34
| c) Bridge (3 nos.) | 200 | 197.266 | 197.266
| d) Foot bridge (1 no.) | 11 | 9.402 | 9.402
| e) Box culvert (29 nos.) | 320 | 277.686 | 277.686
| f) Pipe Culvert (40 nos.) | 55 | 45.03 | 45.03
ii) | Settlement Infrastructure
| a) Cyclone shelter (20 nos.) | 1240 | 1084.47 | 1084.47
| b) Community Pond (50 nos.) | 80 | 67.384 | 67.384
| c) Bus stand (1 no.) | 60 | 54.22 | 54.22
Total of LGED |  | 2910 | 2452.511 | 2452.511
Name of Agency : DPHE
A. | Boyer Char area
| a) Single pit latrine (8500 nos.) | 187 | 142.59 | 110.721
| b) Public Toilet in Market (20 nos.) | 150 | 125.707 | 113.835
| c) Deep Tubewell (600 nos.) | 300 | 181.157 | 160.463
d) Development of community pond with
| arrangement of PSF (47 nos.) | 105.75 | 4.786 | 2
| e) Rain Water Harvesting (60 nos.) | 13.5 | 3.07 | 3.07
| Sub-Total of A. | 756.25 | 457.31 | 390.089
B. | Other cost
| a) Training software activities (LS) | 31.15 | 6.552 | 3.37
| b) Test Tubewell (18 nos.) | 12.6 | 4.2 | 4.2
| Sub-Total of B. | 43.75 | 10.752 | 7.57
Total of DPHE |  | 800 | 468.062 | 397.659
Name of Agency : FD
A. | Plantation Programme
1 | Establishment of Mangrove plantation (500 ha) | 30.5 | 30.5 | 30.5
2 | Establishment of Foreshore Plantation (200 ha) | 236.4 | 26.08 | 26.08
3 | Establishment of strip Plantation
| a) Embankment Plantation (28.5 km.) | 14.4 | 12.03 | 12.03
| b) Feeder Road Plantation (120 km.) | 15.78 | 7.9 | 7.9
4 | Village afforestation (52 nos.) | 63.844 | 48.98 | 48.98
| Sub-Total of A. | 360.924 | 125.49 | 125.49
B. | Plantation Maintenance
| a) Mangrove plantation (500 ha) | 13 | 13 | 13
| b) Foreshore Plantation (200 ha) | 11.65 | 0 | 0
| c) Embankment Plantation (28.5 km) | 14.71 | 6.55 | 6.55
| d) Feeder Road Plantation (120 km) | 2.334 | 2.34 | 2.34
| Sub-Total of B. | 41.694 | 21.89 | 21.89
C. | Other cost
| a) Contingencies (LS) | 6.37 | 6.14 | 5.97
| b) Local Training & Logistic (1800 person) | 51.052 | 51.31 | 40.35
| c) Manpower (MR Basis) | 75.39 | 59.06 | 59.06
| Sub-Total of C. | 132.812 | 116.51 | 105.38
Total of FD |  | 535.43 | 263.89 | 252.76
Name of Agency : DAE
A. | Boyerchar area
1 | Demonstration (7 items) | 20.4 | 20.3 | 19.89
2 | Farmers Training (Local 288 nos.) | 17.28 | 17.28 | 17.28
3 | Farmer Motivation Tour (32 nos.) | 11.2 | 11.2 | 11.2
4 | Workshop/ seminar (Local 6 nos.) | 3.12 | 3.08 | 3.08
5 | On-farm testing of new technology (LS) | 3.4 | 1.3 | 1.3
6 | Procurement of support materials (LS) | 7 | 4.1 | 4.1
7 | Training of Trainers (9 nos.) | 2.4 | 2.08 | 2.08
8 | Printing Extension Materials (LS) | 1 | 1 | 1
9 | Contingency (LS) | 0.7 | 0.7 | 0.7
Total of DAE |  | 66.5 | 61.04 | 60.63
Name of Agency : MoL
A. | Other expenditure (Including K.L dist. & LRMS Program) | 60 | - - | - -
B. | Settlement Progamme
| a) Construction of twin houses | 33.26 | 0 | 0
| b) Rehabilitation of landless families (Ponds excavation) | 200 | 123.18 | 123.18
| c) Rehabilitation of landless families (shifting) | 202.74 | 18.73 | 18.73
Total of MoL |  | 496 | 141.91 | 141.91
Grand Total (BWDB+LGED+DPHE+FD+DAE+MoL) |  | 9220 | 6738.005 | 6648.062

## Sheet2
| E/R |  | C/S |  | Pond | BC
| 517890 |  | 989887 |  | 51673
| 295480 |  | 458178 |  | 65672
| 350363 |  | 834794 |  | 57529
| 325738 |  | 472787 |  | 57632
| 362460 |  | 1113663 |  | 41171
| 357714 |  | 1009784 |  | 37958
| 321021 |  | 435973 |  | 51159
| 297593 |  | 898742 |  | 65229
| 208055 | 208055 | 893204 |  | 63291
| 376711 |  | 898484 |  | 59742
| 3413025 | 208055 | 8005496 |  | 57647
71253
| 204362 |  | 1363279 | 254250 | 679956 | 538066
| 150195 |  | 951430 |  |  | 648257
| 51090 |  | 278416 |  |  | 1186323
| 37549 |  | 897226
| 443196 |  | 108993
1055103
1348184
1361099
1094377
559655
569923
713070
|  |  | 10300755 | 254250
Total | 3856221 | 208055 | 18306251 | 254250 | 679956 | 1186323