## Sheet1
Project |  |  | LRP | LRP |  |  |  |  | CDSP
SLUICE |  |  | Sluice BDII | Sluice BDI | Sluice 14 | Sluice 13 | Sluice 12 | Sluice 2 | Sluice M
|  |  | Baggar Dona II | BaggarDona I | (west) | (west) | (west) | Bashkhali Khal | Bashkhali Khal
gate openings |  | (mxm) | 3 @ 1.5x1.8 | 3 @ 1.5x1.8 | 1 @ 0.9*1.2 | 1 @ 1.5x1.5 | 2 @ 1.5x1.5 | 2 @ 1.5x1.8 | 8 @ 1.5x1.8
nearest khal/sea |  |  | Bagua Nadi | Bagua Nadi | Mara Dona K. | Mara Dona K. | Mara Dona K. | Sea | Sea
design: |  |  | BWDB/LRP | BWDB/LRP | BWDB/ ? | BWDB/ ? | BWDB/ ? |  | BWDB/ CDSP
completion: |  |  | 1987 | 1986 | 1983/84 | 1983/84 | 1983/84 | 1982/83 | 1996/98 *)
construction cost |  | (Tk) | . . . . . | . . . . . | . . . . . | . . . . . | . . . . . | . . . . . | 21000000
invert level |  | (+MSL) | 1.83+ | 1.22+ | ?? | ?? | ?? | ?? | 1.00+
catchment area |  | (ha) | . . . . . | . . . . . | . . . . . | . . . . . | . . . . . | . . . . . | . . . . .
u/s basin |  | (m) | 12.60 | 9.70 | 5 .00 to 6.00 | 5.00 | ?? | 16.00 | 21.00
d/s stilling basin |  | (m) | 12.60 | 17.30 | 5 to 6 | 10(right)/5(left) | ?? | 16.00 | 21.00
outflow channel |  | (m) | 250 | 500 | 1000 | n.a. | ?? | 4500 | 2500
CONDITION
concrete sluice |  |  | good | good | good **) | good | good | good | good
steel flap gates |  |  | 2 good, 1 bad | good | missing | missing | missing | badly rusted | to be installed
vertical lifting gates |  |  | good | good | none | none | none | none | to be installed
lifting device |  |  | good | good | none | none | none | none | to be installed
u/s basin |  |  | good ***) | good | good | good | good | good | good
d/s stilling basin |  |  | good | good | good | good | good | good | good
supply drain |  |  | good | good | fair | fair | fair | fair | good
outflow channel |  |  | fair | fair | fair | fair | fair | fair | fair
last re-excavation |  |  | 1996/97 | 1995/96 | ?? | 1994/95 | 1994/95 | 1993/94 | ??
Notes: | *) New sluice; nearly completed; gates and lifting devices not yet installed | [7 empty] | < cont'd >
**) sluice constructed in masonry
***) addit. about 20m protection with sandbags
RESULTS of INSPECTION of the CONDITION and FUNCTIONING of SLUICES | [8 empty] | TABLE A
(for locations see FIGURE 1)
< cont'd >
|  |  |  | CERP **) | CERP **) | CERP **) | CERP **) | CDSP
SLUICE |  |  | Sluice 8 *) | Sluice 12 | Sluice 16 | Sluice 3 | Sluice 17 | Sluice BT
|  |  | (east) | (east) | (east) | Gangchil Khal | (east) | Nabagram
gate openings |  | (mxm) | 6 @ 1.5x1.8 | 3 @ 0.9x1.2 | 3 @ 0.9x1.2 | 12@1.5x1.8 | 3 @ 0.9x1.2 | 2@1.5x1.8
nearest khal/sea |  |  | Lakhsmir Khal | Lakhsmir Khal | Noakhali Khal | Noakhali Khal | Noakhali Khal | Noakhali Khal
design: | [7 empty] | BWDB/ CDSP
completion: |  |  | 1982/83 | construction | construction | construction | construction | 1996/97
construction cost |  | (Tk) | . . . . . | 10000000 | 10000000 | . . . . . | 10000000 | 9000000
invert level |  | (+MSL) | ?? | 1.90+ | 2.65+ | 1.50+ | 2.50+ | 2.40+
catchment area |  | (ha) | . . . . . | . . . . . | . . . . . | . . . . . | . . . . . | . . . . .
u/s basin |  | (m) | 5.00 | 8.00 | 4.10 | 4.80 | 5.50
d/s stilling basin |  | (m) | 10.00 | 14.00 | 10.80 | 26.10 | 9.00
outflow channel |  | (m) | 20.00 | ?? | ?? | ?? | ??
CONDITION
concrete sluice |  |  | bad | n.a. | n.a. | n.a. | n.a. | good
steel flap gates |  |  | removed | n.a. | n.a. | n.a. | n.a. | good
vertical lifting gates |  |  | none | n.a. | n.a. | n.a. | n.a. | good
lifting device |  |  | none | n.a. | n.a. | n.a. | n.a. | good
u/s basin |  |  | fair | n.a. | n.a. | n.a. | n.a. | good
d/s stilling basin |  |  | fair | n.a. | n.a. | n.a. | n.a. | good
supply drain |  |  | silted up | n.a. | n.a. | n.a. | n.a. | good
outflow channel |  |  | silted up | n.a. | n.a. | n.a. | n.a. | good
last re-excavation |  |  | 1994/95 | n.a. | n.a. | n.a. | n.a. | 1996/97
Notes: | *) sluice and channels heavily silted up
**) construction of CERP-sluices just started
RESULTS of INSPECTION of the CONDITION and FUNCTIONING of SLUICES | [7 empty] | TABLE A
(for locations see FIGURE 1)