## Summary
SUMMARY SHEET OF AVERAGE YEARLY MAINTENANCE COST
Cost in Lac Taka
Sl No. | Name of System | Major Maintenance |  | Minor or Preventive Maintenance |  |  | Total
|  | BWDB | LGED | UP | WMC | Person who built it
1 | Char Baggardona I | 6.01 | 2.03 | 1.57 | 0.8 | 0.43 | 10.84
2 | Char Baggardona II | 8.45 | 3.82 | 0.88 | 0.32 | 1 | 14.47
3 | Char Bhatirtek: Nabagram | 3.28 | 1.12 | 0.46 | 0.07 | 0.31 | 5.24
4 | Char Bhatirtek: Kolmi | 1.79 | 0.52 | 0.1 | 0.05 | 0.23 | 2.69
5 | Char Bhatirtek: Gangchil | 5.3 | 1.12 | 0.64 | 0.12 | * | 7.18
6 | Char Majid | 13.22 | 4.16 | 0.57 | 0.32 | * | 18.27
TOTAL |  | 38.05 | 12.77 | 4.22 | 1.68 | 1.97 | 58.69

## CBDIest
YEAR_WISE MAINTENANCE REQUIREMENTS IN CHAR BAGGARDONA I
A: BWDB Infrastructure | [8 empty] | All cost in lac Taka
Type of Infrastructure | Infrastructure Name and and Quantity | Maintenance year |  |  |  |  | Avrage cost / year | Avrage unit cost/yr | Remarks
|  | 1st | 2nd | 3rd | 4th | 5th
Embankment:
| E-1: Sea Dyke ( 6.68 km) | 2 |  |  | 2 |  | 0.8 | 0.11976 | Breach closing and routin works:EMG
| E-2: Interior dyke (6.00 km) | 1 |  |  | 1 |  | 0.4 | 0.066667 | Breach closing and routin works:EMG
Sluice: Invert Level : + 1.08 m PWD
S-1 : Sluice - 1: 3 vent
| a) Civil works |  | 1 |  |  | 1 | 0.4 | 0.4 | Lumpsum
| b) Mechanical works (yearly regular) | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15
| c) Mechanical ; after checking in b) | 0.1 |  | 0.1 |  | 0.1 | 0.06 | 0.06 | Required only in one year for every 3-5 years. Optional
| d) Debris cleaning | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | During monsoon, 2 labours/week
Main Khals:
| D-1: Main Khal : 3.56 km | 3.5 |  | 0.15 |  | 0.15 | 0.76 | 0.21348 | Removal cross dams: R/E upper part
| D-2: Main Khal : 4.08 km | 6 |  | 0.15 |  | 0.15 | 1.26 | 0.315 | R/E required in the 1st year
| OFC-1: Outfall Channel (D/S of Sluice 1.07 km ) |  | 6 |  |  |  | 1.2 | 1.2 | R/E required
Secondary Khals:
0
| C-1:Khal : 4.03 km | 0.16 | 0.12 | 0.12 | 0.12 | 2 | 0.504 | 0.126 | Removal cross dams every year
| C-2:Khal : 6.40 km | 0.3 | 0.3 | 0.3 | 0.2 | 3.5 | 0.92 | 0.14375 | Removal cross dams every year
| C- 3 :Khal : 0.75 km |  |  |  |  | 0.4 | 0.08 | 0.10652
| C- 4 :Khal : 0.56 km |  |  |  |  | 0.28 | 0.056 | 0.1 | Users do not use it.
| C- 5 :Khal : 0.50 km |  | 0.25 |  |  |  | 0.05 | 0.1 | R/E required
Tertiary drains :
| TC-1 to TC-32 (32 nos= 96 km) | [7 empty] | To be undertaken by the users
Borrowpit:
| BK-1: Borrowpit : 0.75 km |  |  | 0.4 |  |  | 0.08 | 0.10667 | Removal cross dams and bank maintenance
| BK-2: Borrowpit : 5.0 km |  | 2.5 |  |  |  | 0.5 | 0.1 | Removal cross dams and bank maintenance
| BK-3: Borrowpit : 3.0 km | 1.5 |  |  |  |  | 0.3 | 0.1 | Removal cross dams and bank maintenance
Total BWDB Infrastructure |  | 14.725 | 10.335 | 1.385 | 3.485 | 7.745 | 7.535
B: LGED Infrastructure
Rural Roads:
| RR3-1 : (4.00 km) | 1.5 |  | 0.2 | 0.15 | 0.15 | 0.4 | 0.1 | To maintain 5.50 m RL: only top dressing
| RR2-1 : (3.00 km) | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.14 | 0.046667 | To maintain 5.00 m RL: Repaired by UP
| RR3-2 : (5 Km) |  | 3 |  | 0.15 | 0.15 | 0.66 | 0.132 | To maintain 5.00 m RL:
| RR3-3 : (2.50 km) | 2.55 |  | 0.2 | 0.15 | 0.15 | 0.61 | 0.244 | To maintain 5.25 m RL:
| RR2-2: (1.50 km) | [5 empty] | 0 | 0 | Under CBD II (under conversion to FRB)
| RR3-4: (2.00 km) |  | 1.5 |  | 0.1 | 0.1 | 0.34 | 0.17 | To maintain 5.25 m RL:
| RR3-5: (1.5 Km) |  | 1 |  | 0.15 | 0.1 | 0.25 | 0.16667 | To maintain 5.25 m RL:
Bridge :
| B-1 : Near C/Shelter 19 |  | 0.05 |  |  | 0.05 | 0.02 | 0.02 | Only the bridge approach road
Box Culverts :
| BC-1: Box Culvert | [7 empty] | maintenance is taken care in road maintenance part
BC-2: Box Culvert
BC-3: Box Culvert
BC-4: Box Culvert
Pipe culverts :
PC- 1 to PC-28: Pipe culverts
| Pipe culverts : 2 | 0.2 |  |  |  | 0.2 | 0.08 | 0.04 | Brick and earth work, repair head wall
| Pipe outlets : 26 | 2 |  |  |  | 2 | 0.8 | 0.030769 | Replace/repair pipes and earthwork
Total LGED Infrastructure |  | 6.45 | 5.75 | 0.5 | 0.8 | 3 | 3.3
Project Total = BWDB Total + LGED Total |  | 21.175 | 16.085 | 1.885 | 4.285 | 10.745 | 10.835
Gross Area (ha)= |  | 1740
O&M cost/ha (yearly average in Taka)= |  | 622.7011

## CBDIagre
MAINTENANCE PLAN : Responsibilities and cost sharing among the parties involved
Char Baggardona 1 | [13 empty] | All costs in lac Taka
Name of Infrastructure |  | Qty | Ownership | Type of maintenance | Maintenance cycle (Years) | Maintenance Responsibilities and Cost Sharing By | [6 empty] | Annual Average Maintenance Cost | Remarks
[6 empty] | BWDB | LGED | UP | Water Management Committee
[9 empty] | voluntary labours | Person who built /made it | Contribution | Own Resource
BWDB Infrastructure
Embankment |  | 13 km | BWDB | Resectioning :(Rehabilitation) | 5 | [7 empty] | 0
| * Sea dyke * Interior dyke |  |  | Preventive: Breach closing, repair of rain cuts, ruts, public cuts etc | 1 | 1 |  | 0.1 | 0.1 |  |  |  | 1.2 | can be undertaken by EMG or LCS type groups
Sluice |  | 1=(3-v) | BWDB
|  |  |  | Civil works | 2-3 | 0.4 | [6 empty] | 0.4
|  |  |  | Mechanical Regular | 1 | 0.15 | [6 empty] | 0.15
|  |  |  | Mechanical periodic | 2 | 0.06 | [6 empty] | 0.06
|  |  |  | Cleaning debris | 1 |  |  |  | 0.02 |  |  |  | 0.02 | 2 labours/week; monsoon
Main khals |  | 8.60 km | BWDB | Reexcavation: Rehabilitation | 5 | 3 | [6 empty] | 3
| D-1, D-2 and outfall channel |  |  | Preventive: removal cross dams, fishing nets | 1 |  |  |  |  | 0.22 |  |  | 0.22 | Remove or pay for the labours
Secondary khals |  | 12.50 km | BWDB | Reexcavation: Rehabilitation | 5 | 1.4 | [6 empty] | 1.4
| C-1,C-2,C-3, C-4, C-5 |  |  | Preventive: removal cross dams, fishing nets. | 1 |  |  |  |  | 0.21 |  |  | 0.21 | Remove or pay for the labours
Tertiary khals |  | 96 km | Users | Periodic | 7 | [7 empty] | 0 | To be undertaken by users
|  |  |  | Cleaning | 1 | [7 empty] | 0 | To be undertaken by users
Borrowpit |  | 8.75 km | BWDB | Resectioning and bank maintenance | 5 |  |  | 0.2 | 0.2 |  | 0.3 | 0.18 | 0.88 | If people want, voluntary labours, contribution from fisheries, and own resources can be utilized
LGED infrastructure
Rural road (earthen) |  | 20 km | LGED | earth work: slope/ shoulder repair | 1 |  | 1.4 | 1 |  |  |  |  | 2.4 | voluntary labours or own resources
Bridge |  | 1 | LGED | approach repair | 1 |  |  | 0.02 |  |  |  |  | 0.02
Box culverts |  | 4 | LGED | approach repair | 1 | [7 empty] | 0 | maintenance is included in road
Pipe culverts |  | 28 | LGED | earth work | 1 |  | 0.15 | 0.25 |  |  |  |  | 0.4 | voluntary labours or own resources
|  |  |  | Pipe replacement | 3 |  | 0.48 | [5 empty] | 0.48
TOTAL | [5 empty] | 6.01 | 2.03 | 1.57 | 0.32 | 0.43 | 0.3 | 0.18 | 10.84
We the undersigned agreed to implement the above maintenance plan in the next five years.
| XEN, BWDB |  |  | XEN, LGED |  | Chairman |  |  |  | Chairman |  |  |  | Manager, WMC
| Noakhali |  |  | Noakhali |  | Char Jubilee UP |  |  |  | Char Jabbar UP |  |  |  | Char Baggardona I

## CBD2est
YEAR-WISE MAINTENANCE REQUIREMENTS IN CHAR BAGGAR DONA II
A: BWDB Infrastructure | [8 empty] | All costs in Lac Taka
Type of | Infrastructure Name and | Maintenance years |  |  |  |  | Avrage cost/ year | Avrage unit cost/yr | Remarks
Infrastructure | Quantity | 1st | 2nd | 3rd | 4th | 5th
Embankment:
| E-2: Embankment (Interior Dyke: 4.0 km) | 1.5 |  |  |  | 1.5 | 0.6 | 0.15 | Crest and slope maintenance; EMG
| E-3: Marginal Dyke (7.0 km) |  | 2.5 |  |  | 1.5 | 0.8 | 0.11429 | Crest and slope maintenance; repair public cut: EMG
| E-3 : Closure dyke cum road (5.0 km) | [7 empty] | Under R&H
Sluice: 3-vent: Invert level : 1.82 m PWD
S-1 : Sluice 2 (3-vent)
| a) Civil works | 0.2 |  |  | 1 |  | 0.24 | 0.24 | Lumpsum: every 3-5 years
| b) Mechanical works (yearly regular) | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15
| c) Mechanical works (after checking in b) | 0.1 |  | 0.1 |  | 0.1 | 0.06 | 0.06 | Optional
| d) Debris cleaning | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | During monsoon, 2 labours/week
Main Khals:
| D-1: Bagardona Khal (14.60 km) | 3.2 | 0.2 | 0.2 | 0.2 | 15.2 | 3.8 | 0.26027 | Cross dams removals and R/s
| D-2 : Char Jabbar Khal (6.90 km) | [5 empty] | 0 | 0 | Outside the polder: maint. done in 1998
| R-1 : Bagua River | [5 empty] | 0 |  | Outside the polder
| OFC-1: outfall channel (0.30 km) | 3 |  |  |  | 3 | 1.2 | 4
Secondary Khals:
| C-7: Pankhar Khal ( 2.23 km) | 0.15 | 1.65 | 0.25 | 0.15 | 1 | 0.64 | 0.287 | R/E and Crossdams removal.
| C-4: Khal (3.06 km) | 0.1 | 0.1 | 0.1 | 0.1 | 1.5 | 0.38 | 0.12667 | Crossdams removal only
| C5 Khal (3.07 Km) | 0.1 | 0.1 | 0.1 | 0.1 | 1.5 | 0.38 | 0.12667 | Crossdams removal only
| C6 Khal (3.10 km) | 0.15 | 0.15 | 0.15 | 0.15 | 1.5 | 0.42 | 0.13548 | Crossdams removal only
| C-8 : Kanchan Khal (0.75 km) | 0.1 | 0.1 | 0.1 | 0.1 | 0.4 | 0.16 | 0.21333 | Crossdams removal only
| C-9 : Kishorir Khal (1.25 km) | [5 empty] | 0 | 0 | Abandoned(refilled)
| C-10 : Wapda Khal (1.50 km) |  |  |  |  | 0.75 | 0.15 | 0.1
| C-11 : Miar Khal (1.50 km) |  |  |  |  | 0.75 | 0.15 | 0.1
| C-12 : Nabin Khal (1.0 km) |  |  |  |  | 0.5 | 0.1 | 0.1
| C1 Khal (1.0 km) |  |  |  |  | 0.5 | 0.1 | 0.1
| C2 Khal (1.35 km) |  |  |  |  | 0.7 | 0.14 | 0.1037
| C3 Khal (1.50 km) | 0.2 |  |  |  | 0.75 | 0.19 | 0.12667 | Crossdams removal only
Tital BWDB Infrastructure |  | 8.97 | 4.97 | 1.17 | 1.97 | 31.32 | 9.68
B: LGED Infrastructure
Paved Roads :
FRB-1 : Atkapalia - Samitir Bazar (6 km)
| a) Seal coat on prime coat |  |  | 10 |  |  | 2 | 0.33333 | Every 4-5 years
| b) Earth work | 0.6 |  | 0.6 |  | 0.6 | 0.36 | 0.06 | On regular basis
Rural Roads:
| RR2-1:Samitir Bazar to Shafi Sareng Mosque (2.17 km) | 0.32 | 0.23 | 0.15 | 0.1 | 0.1 | 0.18 | 0.081818 | On regular basis
| RR2-2 : Jagadish House to west embankment Road ( 2.51 km ) | 0.4 | 0.26 | 0.26 | 0.15 | 0.1 | 0.234 | 0.0936 | On regular basis
| RR2-3: Latif house to west embankment road (3.70Km) | 0.57 | 0.38 | 0.32 | 0.2 | 0.15 | 0.324 | 0.087568 | On regular basis
| RR2-4: Pariskar Bazar to R&H road (1.906 km) | 0.3 | 0.2 | 0.15 | 0.1 | 0.1 | 0.17 | 0.085 | On regular basis
| RR3-1 : Nabin Mosque to Siddique house Road (0.88Km) | 0.14 | 0.1 | 0.1 | 0.1 | 0.05 | 0.098 | 0.098 | On regular basis
| RR2-5 : Kanchan Bazer to Shafi Sareng Mosque road (2.19 km) | 0.35 | 0.23 | 0.15 | 0.1 | 0.05 | 0.176 | 0.08 | On regular basis
| RR1-1 :Samitir Bazar to Samitir Bazar bridge road (1.10 km) | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.090909 | quite stable
| RR2-6 : Pariskar Bazar to Kanchan Bazar road (2.0 km) | 1.5 |  | 0.15 | 0.15 | 0.1 | 0.38 | 0.19 | R/S required
| RR2-7 : Atkapalia and Batu Mia road (1.0 Km ) | 0.15 | 0.1 | 0.1 | 0.05 | 0.05 | 0.09 | 0.09 | On regular basis
Bridge :
| B-1 (Samitir Bazar road) | 0.1 | 0.1 | 0.1 | 0.05 | 0.05 | 0.08 | 0.08 | For bridge approach
Box culverts :
| BC-1 :Box Culvert (Latif house to embankment road) | [7 empty] | Maintenance is considered in road
BC-2 :On FRB
BC-3 :On FRB
BC-4 :
BC-5 :
BC-6 :
BC-7 :
| BC-8 : | [7 empty] | Maintenance is considered in road
BC-9 :
BC-10:
Pipe culverts :
PC- 1 to PC-15: Pipe culverts
| a) Pipe culverts : 10 | 1 |  |  |  | 1 | 0.4 | 0.04 | 5 needs head walls repair
| b) Pipe outlets : 5 | 0.5 |  |  |  | 0.5 | 0.2 | 0.04 | Needs pipe replacement (50%)
Total LGED Infrstructure |  | 6.03 | 1.7 | 12.18 | 1.1 | 2.95 | 4.792
Project Total (BWDB + LGED) |  | 15 | 6.67 | 13.35 | 3.07 | 34.27 | 14.472
Gross Area (ha)= |  | 2083
O&M cost/ha (yearly average in Taka)= |  | 694.7672

## CBD2agre
MAINTENANCE PLAN : Responsibilities and cost sharing among the parties involved
Char Baggardona 2 | [13 empty] | All costs in lac Taka
Name of Infrastructure |  | Qty | Ownership | Type of maintenance | Maintenance cycle (Years) | Maintenance Responsibilities and Cost Sharing By | [6 empty] | Annual Average Maintenance Cost | Remarks
[6 empty] | BWDB | LGED | UP | Water Management Committee
[9 empty] | voluntary labours | Person who built /made it | Contribution | Own Resource
BWDB Infrastructure
Embankment |  | 11 km | BWDB | Resectioning :(Rehabilitation) | 5 | 1.2 | [6 empty] | 1.2 | can be undertaken by EMG or LCS type groups
| * Marginal dyke * Interior dyke |  |  | Preventive: Breach closing, repair of rain cuts, ruts, public cuts etc | 1 |  |  | 0.1 | 0.1 |  |  |  | 0.2 | can be undertaken by EMG or LCS type groups. A public cut has to be repaired by WMC
Sluice |  | 1=(3-v) | BWDB | Civil works | 3 | 0.24 | [6 empty] | 0.24
|  |  |  | Mechanical Regular | 1 | 0.15 | [6 empty] | 0.15
|  |  |  | Mechanical periodic | 2 | 0.06 | [6 empty] | 0.06
|  |  |  | Cleaning debris | 1 |  |  |  | 0.02 |  |  |  | 0.02 | 2 labours/week; monsoon
Main khals |  | 14.60 km | BWDB | Reexcavation: Rehabilitation | 5 | 4.8 | [6 empty] | 4.8
| D-1 and outfall channel |  |  | Preventive: removal cross dams, fishing nets | 1 |  |  |  |  | 0.2 |  |  | 0.2 | Remove or pay for the labours
Secondary khals |  | 22 km | BWDB | Reexcavation: Rehabilitation | 5 | 2 | [6 empty] | 2
| C-1 to C-12 |  |  | Preventive: removal cross dams, fishing nets. | 1 |  |  |  |  | 0.8 |  |  | 0.8 | Remove or pay for the labours
LGED infrastructure
Feeder Road-B |  | 7 km | LGED | a) Periodic: seal coat | 5 |  | 2 | [5 empty] | 2
|  |  |  | b) Earthwork: slope/shoulder repair |  |  | 0.36 | [5 empty] | 0.36
Rural road (earthen) |  | 17 km | LGED | earth work: slope/ shoulder repair | 1 |  | 1.16 | 0.5 | 0.1 |  |  |  | 1.76
Bridge |  | 1 | LGED | approach repair | 1 |  |  | 0.08 |  |  |  |  | 0.08
Box culverts |  | 10 | LGED | approach repair | 1 | [7 empty] | 0 | maintenance is included in road
Pipe culverts |  | 15 | LGED | earth work | 1 |  | 0.1 | 0.2 | 0.1 |  |  |  | 0.4
|  |  |  | Pipe replacement | 3 |  | 0.2 | [5 empty] | 0.2
TOTAL | [5 empty] | 8.45 | 3.82 | 0.88 | 0.32 | 1 | 0 | 0 | 14.47
We the undersigned agreed to implement the above maintenance plan in the next five years.
| XEN, BWDB |  |  | XEN, LGED |  | Chairman |  |  |  | Chairman |  |  |  | Manager, WMC
| Noakhali |  |  | Noakhali |  | Char Jabbar UP |  |  |  | Char Jubilee UP |  |  |  | Char Baggardona 2

## CBT1est
YEAR-WISE MAINTENANCE REQUIREMENTS IN CHAR BHATIR TEK: WM SYSTEM 1 (Nabagram)
A: BWDB Infrastructure | [8 empty] | All costs in lac Taka
Type of | Infrastructure Name and | Maintenance years |  |  |  |  | Avrage cost/ year | Avrage unit cost/yr | Remarks
Infrastructure | Quantity | 1st | 2nd | 3rd | 4th | 5th
Embankment:
| E-2:Interior Dyke: 0.80 km |  | 1 |  | 0.2 |  | 0.24 | 0.3 | resectioning needed, EMG may be deployed
| E-1: Sea Dyke: 5.00 km |  |  | 2 |  |  | 0.4 | 0.08 | By EMG
Sluice:
S-1 :Sluice 2: Nabagram CDSP Sluice: (3-vent): Invert Level=2.43 m PWD
| a) Civil works (regular and yearly) |  |  | 0.5 |  |  | 0.1 | 0.1
| b) Mechanical work (yearly) | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| c) Mechanical work (after checking in b) |  | 0.1 |  | 0.1 |  | 0.04 | 0.04 | optional
| d) Debris cleaning | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | monsoon, 1 labour/ week
Main Khals:
| D-1: Khal (6.050 km) |  | 6 |  |  |  | 1.2 | 0.2 | reexcavation needed due to faulty box culvert constructed on it.
| D-2: D/s of sluice (300 m) |  | 1 |  |  |  | 0.2 | 0.66667 | Desilt needed.
Secondary Khals:
0
| C1: Khal ( 1.00 km) | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.18 | 0.18 | removal of cross dams
| C3: Khal (3.00 Km) | 0.2 | 0.2 | 0.2 | 0.1 | 1.5 | 0.44 | 0.14667 | removal of cross dams
| C4: Khal (1.00 km) | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.18 | 0.18 | removal of cross dams, R/E upper part
| C5: Khal (1.50 km) | 1.5 | 0.1 | 0.1 | 0.1 | 0.75 | 0.51 | 0.34 | removal of cross dams and R/E
Total BWDB Infrastructure |  | 2.01 | 8.71 | 3.11 | 0.81 | 3.36 | 3.6
B: LGED Infrastructure
Rural Roads:
| RR2-1:Hashem Mia Road (1.75 km) | 1 | 0.2 | 0.2 | 0.1 | 0.1 | 0.32 | 0.18286 | R/S needed
| RR1-1 : Nabagram Bazar to Khewa Road ( 1.38 km ) | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.26 | 0.18571
| RR1-2: Nabagram Amin Bazar road (3.50Km) | 0.5 | 0.35 | 0.2 | 0.15 | 0.15 | 0.27 | 0.077143
| RR2-9: Halim Bazar to Shrimp Project road (2.10 km) | 1.5 | 0.2 | 0.2 | 0.15 | 0.15 | 0.44 | 0.20952 | R/s needed
| RR2-3 : (Part): Thanarhat nazir Khewa road (2.75 km) | 0.3 | 0.2 | 0.15 | 0.1 | 0.1 | 0.17 | 0.061818
Box culverts :
| BC-7 :Box Culvert over Hashem Mia Road (RR2-1) | [5 empty] | 0 |  | Demolished
| BC-3 :On RR1-2 | [5 empty] | 0 |  | maintenance is considered with road
Pipe culverts :
| a) Pipe culverts : 3 |  |  | 0.3 |  |  | 0.06 | 0.02 | new with head wall
| b) Pipe outlets : 3 |  | 0.3 |  |  | 0.3 | 0.12 | 0.04 | 50% pipe replacement
Total LGED Infrastructure |  | 3.6 | 1.55 | 1.35 | 0.7 | 1 | 1.64
System Total (Total BWDB + Total LGED) |  | 5.61 | 10.26 | 4.46 | 1.51 | 4.36 | 5.24
Gross Area (ha)= |  | 690
O&M cost/ha (yearly average in Taka)= |  | 759.4203

## CBT1agre
MAINTENANCE PLAN : Responsibilities and cost sharing among the parties involved
Char Bhatir Tek System-1 (Nabagram) | [13 empty] | All costs in lac Taka
Name of Infrastructure |  | Qty | Ownership | Type of maintenance | Maintenance cycle (Years) | Maintenance Responsibilities and Cost Sharing By | [6 empty] | Annual Average Maintenance Cost | Remarks
[6 empty] | BWDB | LGED | UP | Water Management Committee
[9 empty] | voluntary labours | Person who built /made it | Contribution | Own Resource
BWDB Infrastructure
Embankment |  | 6 km | BWDB | Resectioning :(Rehabilitation) | 5 | 0.24 | [6 empty] | 0.24 | can be undertaken by EMG or LCS type groups
| * Sea dyke * Interior dyke |  |  | Preventive: Breach closing, repair of rain cuts, ruts, public cuts etc | 1 | 0.4 | [6 empty] | 0.4 | can be undertaken by EMG or LCS type groups
Sluice |  | 1=(2-v) | BWDB
|  |  |  | Civil works | 3 | 0.1 | [6 empty] | 0.1
|  |  |  | Mechanical Regular | 1 | 0.1 | [6 empty] | 0.1
|  |  |  | Mechanical periodic | 2 | 0.04 | [6 empty] | 0.04
|  |  |  | Cleaning debris | 1 |  |  |  | 0.01 |  |  |  | 0.01 | 1 labours/week; monsoon
Main khals |  | 6.50 km | BWDB | Reexcavation: Rehabilitation | 5 | 1.4 | [6 empty] | 1.4
| D-1, D-2 |  |  | Preventive: removal cross dams, fishing nets | 1 | [7 empty] | 0
Secondary khals |  | 6.50 km | BWDB | Reexcavation: Rehabilitation | 5 | 1 | [6 empty] | 1
| C-1, C-3, C-4 and C-5 |  |  | Preventive: removal cross dams, fishing nets. | 1 |  |  |  |  | 0.31 |  |  | 0.31 | Remove or pay for the labours
LGED infrastructure
Rural road (earthen) |  | 12 km | LGED | earth work: slope/ shoulder repair | 1 |  | 1 | 0.46 |  |  |  |  | 1.46
Bridge |  | 0 | LGED | approach repair | 1
Box culverts |  | 2 | LGED | approach repair | 1 | [7 empty] | 0 | one demolished
Pipe culverts |  | 6 | LGED | earth work | 1 |  |  |  | 0.06 |  |  |  | 0.06
|  |  |  | Pipe replacement | 3 |  | 0.12 | [5 empty] | 0.12
TOTAL | [5 empty] | 3.28 | 1.12 | 0.46 | 0.07 | 0.31 | 0 | 0 | 5.24
We the undersigned agreed to implement the above maintenance plan in the next five years.
| XEN, BWDB |  |  | XEN, LGED |  |  |  | Chairman |  |  |  |  | Manager, WMC
| Noakhali |  |  | Noakhali |  |  |  | Sundalpur UP |  |  |  |  | Nabagram, CBT

## CBT2est
YEAR-WISE MAINTENANCE REQUIREMENTS IN CHAR BHATIR TEK: WM SYSTEM 2 (Kalmi)
A: BWDB Infrastructure | [8 empty] | All costs in lac Taka
Type of | Infrastructure Name and | Maintenance years |  |  |  |  | Avrage cost/ year | Avrage unit cost/yr | Remarks
Infrastructure | Quantity | 1st | 2nd | 3rd | 4th | 5th
Embankment:
| E-1:Embankment (Sea Dyke: 0.40 km) |  |  | 0.5 |  |  | 0.1 |  | Built by CERP. Maintenance by CERP.
Sluice:
S-2 : CERP Sluice: (4-vent): Invert level = +2.50 m PWD
| a) Civil works (regular and yearly) |  |  |  |  | 1 | 0.2 | 0.2 | no maintenance needed next 3-5 years. Built by CERP
| b) Mechanical work (regular and yearly) | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| c) Mechanical work (after checking in b) |  | 0.15 |  | 0.1 |  | 0.05 | 0.05
| d) Debris cleaning | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | Monsoon, 1 labour/week
Main Khals:
| D-4: Khal (2.10 km) | 0.5 |  |  |  | 1.2 | 0.34 | 0.1619 | u/s reexcavated partially, d/s not done by CERP.
Secondary Khals:
[6 empty] | 0.2 | 0.04 | 0.019048
| C2: Khal ( 1.20 km) | 0.1 | 0.1 | 0.1 | 0.1 | 0.6 | 0.2 | 0.16667 | cross dam removal
| C9: Khal (3.00 Km) | 2.5 | 0.15 | 0.15 | 0.1 | 1.5 | 0.88 | 0.29333 | R/E needed(50%), cross dam remova needed
| C12: Khal (1.10 km) | 0.1 | 0.05 | 0.05 | 0.05 | 0.5 | 0.15 | 0.13636 | cross dam removal
Total BWDB Infrastructure |  | 3.31 | 0.56 | 0.91 | 0.46 | 4.91 | 2.03
B: LGED Infrastructure
Rural Roads:
| RR2-2:Chiringa Bazar - Kalmi Road (3.17 km) | 0.6 | 0.3 | 0.15 | 0.1 | 0.1 | 0.25 | 0.078125 | Crest and slope maintenance
| RR2-3 : (part): Thanathat - Nazir Khewa Road ( 1.10 km ) | 0.15 | 0.1 | 0.1 | 0.1 | 0.1 | 0.11 | 0.1 | Crest and slope maintenance
| RR2-5: Manikgonj - Khewa road (2.40Km) | 0.3 | 0.25 | 0.15 | 0.1 | 0.1 | 0.18 | 0.075 | crest and slope maintenance
Box culverts :
| BC-1 :Box Culvert over D-4 | [5 empty] | 0 |  | Maintenance is taken care with road. Now maintenance not needed, newly built
| BC-2 : over C-2 | [5 empty] | 0
| BC-3 : over C-9 | [5 empty] | 0
| BC-4 : over C-2 | [5 empty] | 0
| BC-5 : over C-12 | [5 empty] | 0
Pipe culverts :
| a) Pipe culverts : 1 |  | 0.1 |  |  | 0.1 | 0.04 | 0.04 | new with head wall
| b) Pipe outlets : 2 |  | 0.2 |  |  | 0.2 | 0.08 | 0.04 | pipe replacement (50%)
Total LGED Infrastructure |  | 1.05 | 0.95 | 0.4 | 0.3 | 0.6 | 0.66
System Total = (BWDB Total + LGED Total) |  | 4.36 | 1.51 | 1.31 | 0.76 | 5.51 | 2.69
Gross Area (ha)= |  | 385
O&M cost/ha (yearly average in Taka)= |  | 698.7013

## CBT2agre
MAINTENANCE PLAN : Responsibilities and cost sharing among the parties involved
Char Bhatir Tek System-2 (Kalmi) | [13 empty] | All costs in lac Taka
Name of Infrastructure |  | Qty | Ownership | Type of maintenance | Maintenance cycle (Years) | Maintenance Responsibilities and Cost Sharing By | [6 empty] | Annual Average Maintenance Cost | Remarks
[6 empty] | BWDB | LGED | UP | Water Management Committee
[9 empty] | voluntary labours | Person who built /made it | Contribution | Own Resource
BWDB Infrastructure
Embankment |  | 0.50 km | BWDB | Resectioning :(Rehabilitation) | 5 | [7 empty] | 0
| * Sea dyke |  |  | Preventive: Breach closing, repair of rain cuts, ruts, public cuts etc | 1 | 0.1 | [6 empty] | 0.1 | can be undertaken by EMG or LCS type groups
Sluice |  | 1=(4-v) | BWDB
|  |  |  | Civil works | 3 | 0.2 | [6 empty] | 0.2
|  |  |  | Mechanical Regular | 1 | 0.1 | [6 empty] | 0.1
|  |  |  | Mechanical periodic | 2 | 0.05 | [6 empty] | 0.05
|  |  |  | Cleaning debris | 1 |  |  |  | 0.01 |  |  |  | 0.01 | 1 labours/week; monsoon
Main khals |  | 2.10 km | BWDB | Reexcavation: Rehabilitation | 5 | 0.34 | [6 empty] | 0.34
| D-4 |  |  | Preventive: removal cross dams, fishing nets | 1 | [7 empty] | 0 | Remove or pay for the labours
Secondary khals |  | 5.50 km | BWDB | Reexcavation: Rehabilitation | 5 | 1 | [6 empty] | 1
| C-2, C-9 and C-12 |  |  | Preventive: removal cross dams, fishing nets. | 1 |  |  |  |  | 0.23 |  |  | 0.23 | Remove or pay for the labours
LGED infrastructure
Rural road (earthen) |  | 7.0 km | LGED | earth work: slope/ shoulder repair | 1 |  | 0.4 | 0.1 | 0.04 |  |  |  | 0.54
Bridge |  | 0 | LGED | approach repair | 1
Box culverts |  | 5 | LGED | approach repair | 1 | [7 empty] | 0 | maintenance included with road
Pipe culverts |  | 3 | LGED | earth work | 1 |  | 0.04 | [5 empty] | 0.04
|  |  |  | Pipe replacement | 3 |  | 0.08 | [5 empty] | 0.08
TOTAL | [5 empty] | 1.79 | 0.52 | 0.1 | 0.05 | 0.23 | 0 | 0 | 2.69
We the undersigned agreed to implement the above maintenance plan in the next five years.
| XEN, BWDB |  |  | XEN, LGED |  |  | Chairman | [5 empty] | Manager, WMC
| Noakhali |  |  | Noakhali | [8 empty] | Kolmi, CBT

## CBT3est
YEAR-WISE MAINTENANCE REQUIREMENTS IN CHAR BHATIR TEK: WM SYSTEM 3 ( Gangchil)
A: BWDB Infrastructure | [8 empty] | All costs in lac Taka
Type of | Infrastructure Name and | Maintenance years |  |  |  |  | Avrage costperyear | Avrage unit cost/yr | Remarks
Infrastructure | Quantity | 1st | 2nd | 3rd | 4th | 5th
Embankment:
| E-1:Embankment (Sea Dyke: 4.0 km) |  | 1.8 |  | 1.8 |  | 0.72 | 0.18 | R/S done by CERP; EMG may be deployed for preventive maintenance
| E-3: Marginal Embankment (0.8 km) | 2.5 |  |  |  |  | 0.5 | 0.625 | Resectioning needed (now road)
| E-4: Road cum embankment (4.0 km) | [5 empty] | 0 | 0 | R&HD/ LGED
Sluice: | Invert Level : +1.50 m PWD
| S-3 : CERP Sluice (12-vent): outside the system : Under construction: Invert level : +1.50 m PWD | Under construction
| a) Civil works |  |  |  |  | 2 | 0.4 | 0.4 | The sluice is under construction and not ready for use.
| b) Mechanical work ( yearly) |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.32 | 0.32
| c) Mechanical work ( after checking in b) |  | 0.4 |  |  | 0.4 | 0.16 | 0.16
| d) Debris cleaning | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02
Main Khals:
| D-2: Khal (4.00 km) |  |  |  |  | 4 | 0.8 | 0.2 | Reexcavated in 1998
| D-3: Khal (3.27 km) | 1 |  |  |  | 3 | 0.8 | 0.24242 | Reexcavated in 1998, upper part need excavation
Secondary Khals:
0
| C6: Khal ( 2.50 km) | 2.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.58 | 0.232 | Reexcavated in 1998, upper part needs excavation
| C11: Khal (1.50 Km) | 3 |  |  |  |  | 0.6 | 0.4 | Reexcavation needed
| C7: Khal (1.00 km) |  | 1 |  |  |  | 0.2 | 0.2 | Reexcavation needed
| C8: Khal (1.50 km) |  | 1.5 |  |  |  | 0.3 | 0.2 | Reexcavation needed
Total BWDB Infrastructure |  | 9.02 | 5.22 | 0.52 | 2.32 | 9.92 | 5.4
B: LGED
Bridge :
| B-1: Over D-2 and E-4 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | repair of bridge approach
| B-2: Over D-3 and E-3 |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.04 | 0.04 | repair of bridge approach
Rural Roads:
| RR2-3 : (part): Thanarhat - Nazir Khewa Road ( 1.10 km ) | 0.15 | 0.1 | 0.1 | 0.1 | 0.1 | 0.11 | 0.1 | Crest and slope maintenance
| RR2-4 : Manikgonj - Asa Road (1.70 km) | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.058824 | Crest and slope maintenance
| RR2-6: Amanatgonj - embankment (4.33 km) | 2 | 0.4 | 0.2 | 0.1 | 0.1 | 0.56 | 0.12933 | Crest and slope maintenance
| RR2-7: Gangchil Bazar - Kalmi (1.10 km) | 0.15 | 0.1 | 0.1 | 0.1 | 0.1 | 0.11 | 0.1 | Crest and slope maintenance
| RR2-10: Asa-Gangchil to embankment road (2.30 km) | 0.3 | 0.2 | 0.2 | 0.1 | 0.1 | 0.18 | 0.078261 | Crest and slope maintenance
| RR2-8: Gangchil Mosque road (0.70 km) | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.14286 | Crest and slope maintenance
| RR2-11: Kalmi - Gangchil road (1.60 km): existing | 1 | 0.2 | 0.1 | 0.1 | 0.1 | 0.3 | 0.1875 | Crest and slope maintenance
Box culverts :
| BC-2 :Box Culvert over RR2-6 | [5 empty] | 0 |  | maintenance is considered in road
| BC-6 :Box Culvert over RR2-6 | [5 empty] | 0
| BC-4 :Box Culvert over D-3 | [5 empty] | 0
| BC-5 :Box Culvert over RR2-6 | [5 empty] | 0
Pipe culverts :
| a) Pipe culverts : 3 |  | 0.3 |  |  | 0.3 | 0.12 | 0.04 | new with head wall
| b) Pipe outlets : 3 | 0.3 |  |  | 0.3 |  | 0.12 | 0.04 | pipe replacement (50%)
Total LGED Infrastructure |  | 4.1 | 1.6 | 1 | 1.1 | 1.1 | 1.78
System Total = BWDB Total + LGED Total |  | 13.12 | 6.82 | 1.52 | 3.42 | 11.02 | 7.18
Gross Area (ha)= |  | 710
O&M cost/ha (yearly average in Taka)= |  | 1011.2676

## CBT3agre
MAINTENANCE PLAN : Responsibilities and cost sharing among the parties involved
Char Bhatir Tek System-3 (Gangchil) | [13 empty] | All costs in lac Taka
Name of Infrastructure |  | Qty | Ownership | Type of maintenance | Maintenance cycle (Years) | Maintenance Responsibilities and Cost Sharing By | [6 empty] | Annual Average Maintenance Cost | Remarks
[6 empty] | BWDB | LGED | UP | Water Management Committee
[9 empty] | voluntary labours | Person who built /made it | Contribution | Own Resource
BWDB Infrastructure
Embankment |  | 5.0 km | BWDB | Resectioning :(Rehabilitation) | 5 | 0.5 | [6 empty] | 0.5 | By EMG/LCS
| * Sea dyke * Marginal dyke |  |  | Preventive: Breach closing, repair of rain cuts, ruts, public cuts etc | 1 | 0.72 | [6 empty] | 0.72 | can be undertaken by EMG or LCS type groups
Sluice |  | 1= (12-v) | BWDB
|  |  |  | Civil works | 3 | 0.4 | [6 empty] | 0.4 | Sluice is under construction
|  |  |  | Mechanical Regular | 1 | 0.32 | [6 empty] | 0.32
|  |  |  | Mechanical periodic | 2 | 0.16 | [6 empty] | 0.16
|  |  |  | Cleaning debris | 1 |  |  |  | 0.02 |  |  |  | 0.02 | 4 labours/week; monsoon
Main khals |  | 7.50 km | BWDB | Reexcavation: Rehabilitation | 5 | 1.6 | [6 empty] | 1.6
| D-2 and D-3 |  |  | Preventive: removal cross dams, fishing nets | 1 | [7 empty] | 0
Secondary khals |  | 5.50 km | BWDB | Reexcavation: Rehabilitation | 5 | 1.6 | [6 empty] | 1.6
| C-6, C-7, C-8 and C-11 |  |  | Preventive: removal cross dams, fishing nets. | 1 |  |  |  | 0.08 |  |  |  | 0.08
LGED infrastructure
Rural road (earthen) |  | 12.0 km | LGED | earth work: slope/ shoulder repair | 1 |  | 1 | 0.46 |  |  |  |  | 1.46
Bridge |  | 2 | LGED | approach repair | 1 |  |  | 0.08 |  |  |  |  | 0.08
Box culverts |  | 4 | LGED | approach repair | 1 | [7 empty] | 0 | maintenance included with road
Pipe culverts |  | 6 | LGED | earth work | 1 |  |  | 0.1 | 0.02 |  |  |  | 0.12
|  |  |  | Pipe replacement | 3 |  | 0.12 | [5 empty] | 0.12
TOTAL | [5 empty] | 5.3 | 1.12 | 0.64 | 0.12 | 0 | 0 | 0 | 7.18
We the undersigned agreed to implement the above maintenance plan in the next five years.
| XEN, BWDB |  |  |  | XEN, LGED |  |  |  | Chairman |  |  |  | Manager, WMC
| Noakhali |  |  |  | Noakhali

## CMest
YEAR-WISE MAINTENANCE REQUIREMENTS IN CHAR MAJID
A: BWDB Infrastructure | [8 empty] | All costs in lac Taka
Type of | Infrastructure Name and | Maintenance years |  |  |  |  | Avrage cost per year | Avrage unit cost /yr | Remarks
Infrastructure | Quantity | 1st | 2nd | 3rd | 4th | 5th
Embankment:
| E-3: Embankment cum pavement road in North Western boundary (2.8km + 4.8 km= 7.6 km) | [7 empty] | RHD to take care
| E-3: Embankment cum pavement road (2.50 km pavement) | [7 empty] | maintenance. is considered in FRB
| E-1: Sea dyke (2.50 km non-pavement) |  | 2 |  |  | 2 | 0.8 | 0.32 | Routin maintenance; EMG
| E-2 : Interior dyke (3.0 km) | 3 |  |  |  | 1.5 | 0.9 | 0.3 | crest and slope maintenance; EMG
Sluice:
| S-1 : Sluice (old, CEP : 3-vent) | 1 |  |  |  |  | 0.2 | 0.2 | renovation and cleaning u/s and d/s channel
S-2 : Sluice (outfall of Banskhali khal, 8-vent: Invert level 1.06 m PWD)
| a) Civil work |  | 0.5 |  |  | 1.5 | 0.4 | 0.4 | Optional: maintenance may not require for next 4-5 years
| b) Mechanical work (yearly) |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.32 | 0.32
| c) Mechanical work (after checking in b) |  | 0.4 |  | 0.4 |  | 0.16 | 0.16
| d) Debris cleaning | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | Monsoon; 2 labours/week
Main Khals:
| D-1 : Banskhali Khal ( 5.50 km) | [7 empty] | including d/s portion
| a) Sluice u/s portion (3.00 km) | 6 |  |  |  |  | 1.2 | 0.4
| b) Sluice d/s portion (3.00 km) | 10 |  | 10 |  | 10 | 6 | 2 | To build Cross bundh at the oufall and make a small drain
| D-2 : Gupter Khal ( 5.60 km) |  |  |  |  | 6 | 1.2 | 0.21429
| D-3: (along the southern part: 2.75 km) |  |  | 3 |  |  | 0.6 | 0.21818 | Southern Borrowpit
Secondary Khals:
[7 empty] | 0 | 0
| C-1 : Boatkhali Khal-1 ( 2.70 km) |  |  |  |  | 1.3 | 0.26 | 0.096296 | removal of cross dams
| C-2 : Boatkhali Khal-2 ( 2.30 km) |  |  |  |  | 1.2 | 0.24 | 0.10435
| C-3 : Boatkhali Khal-3 ( 2.40 km) |  | 0.4 |  |  | 1.2 | 0.32 | 0.13333
| C-6 : Zubair Khal-1 ( 1.50 km) |  |  |  |  | 0.75 | 0.15 | 0.1
| C-7 : Zubair Khal-2 ( 0.60 km) |  |  |  |  | 0.3 | 0.06 | 0.1
| C-4 : Nister Khal ( 2.60 km) |  |  |  |  | 0.3 | 0.06 | 0.023077
| C-5 : Samitir Khal ( 2.50 km) |  |  |  |  | 1.25 | 0.25 | 0.1
| C-8: Drain in WMA 5&6 ( 1.00 km) |  |  |  |  | 0.5 | 0.1 | 0.1
Borrowpit:
TOTAL BWDB Infrastructure |  | 20.04 | 3.74 | 13.44 | 0.84 | 28.24 | 13.26
B: LGED Infrastructure
Paved Roads :
FRB-1A :North embankment to Zubairhat (2.40 Km)
| a) Seal coat over prime coat and earthwork |  | 4.8 | 0.2 | 0.2 | 0.2 | 1.08 | 0.45 | every 3-5 years
FRB-1B : North embankment (4.80 Km)
| a) Seal coat over prime coat and earthwork |  |  |  |  | 4 | 0.8 | 0.16667 | every 3-5 years
FRB-1C :Southern part: Bhuiyarhat to sluice (3.00 Km)
| a) Seal coat over prime coat and earthwork |  | 6 |  |  | 0.2 | 1.24 | 0.41333 | every 3-5 years
Rural Roads:
| RR2-1: Boat Khali road (2.41 km) | 0.25 | 0.2 | 0.2 | 0.1 | 0.1 | 0.17 | 0.068
| RR2-2 : Rabi shop to site office: 3.45 km | 0.35 | 0.25 | 0.25 | 0.1 | 0.1 | 0.21 | 0.06
| RR2-3: Boiragi bari road (3.00Km) | 0.3 | 0.25 | 0.25 | 0.1 | 0.1 | 0.2 | 0.066667
| RR2-4: Karim Bazar to South embankment road ( 4.00 km) | 0.4 | 0.3 | 0.15 | 0.1 | 0.1 | 0.21 | 0.0525
| RR1-1 : Renur Bazar to Ershad Colony-Bhuiarhat road ( 7.00 Km) | 0.7 | 0.5 | 0.35 | 0.2 | 0.1 | 0.37 | 0.052857
| RR2-5 : Renur Bazar to east embankment (0.50 km) | 0.1 | 0.05 | 0.05 | 0.05 | 0.05 | 0.06 | 0.12
| RR2-6: Killa to colony road (0.70 km) | 0.2 | 0.1 | 0.1 | 0.05 | 0.05 | 0.1 | 0.14286
Bridge :
| B-1: (at Gupter khal) | 0.08 | 0.07 | 0.05 | 0.05 | 0.05 | 0.06 | 0.06 | only bridge approach
| B-2: (at Banskhali khal) | 0.07 | 0.08 | 0.05 | 0.05 | 0.05 | 0.06 | 0.06 | only bridge approach
Box culverts :
| BC-1 : | [5 empty] | 0 |  | maintenance is taken care in the road maintenance
| BC-2 :On FRB | [5 empty] | 0
| BC-3 :On FRB | [5 empty] | 0
| BC-4 : | [5 empty] | 0
| BC-5 : | [5 empty] | 0 |  | maintenance is taken care in the road maintenance
| BC-6 : | [5 empty] | 0
| BC-7 : | [5 empty] | 0
| BC-8 : | [5 empty] | 0
| BC-9 : | [5 empty] | 0
| BC-10: | [5 empty] | 0
Foot Bridge
| FB-1 : (at Renur Bazar) |  |  | 0.05 | 0.05 | 0.05 | 0.03 | 0.03 | only bridge approach
| FB-2 : (at Karim Bazar road) |  |  | 0.05 | 0.05 | 0.05 | 0.03 | 0.03 | only bridge approach
| FB-3 : ( at Zubair Bazar road) |  |  | 0.05 | 0.05 | 0.05 | 0.03 | 0.03 | only bridge approach
Pipe culverts :
PC- 1 to PC-13:
| a) pipe culverts = 8 |  |  |  | 0.8 |  | 0.16 | 0.02 | New with head wall
| b) pipe outlets = 5 |  | 0.5 |  |  | 0.5 | 0.2 | 0.04 | 50% pipes to be replaced
TOTAL LGED Infrastructure |  | 2.45 | 13.1 | 5.8 | 1.95 | 5.75 | 5.01
PROJECT TOTAL = BWDB TOTAL + LGED TOTAL |  | 22.49 | 16.84 | 19.24 | 2.79 | 33.99 | 18.27
Gross Area (ha)= |  | 1281
O&M cost/ha (yearly average in Taka)= |  | 1426.2295

## CMagre
MAINTENANCE PLAN : Responsibilities and cost sharing among the parties involved
Char Majid | [13 empty] | All costs in lac Taka
Name of Infrastructure |  | Qty | Ownership | Type of maintenance | Maintenance cycle (Years) | Maintenance Responsibilities and Cost Sharing By | [6 empty] | Annual Average Maintenance Cost | Remarks
[6 empty] | BWDB | LGED | UP | Water Management Committee
[9 empty] | voluntary labours | Person who built /made it | Contribution | Own Resource
BWDB Infrastructure
Embankment |  | 5.50 km | BWDB | Resectioning :(Rehabilitation) | 5 | 1.7 | [6 empty] | 1.7 | can be undertaken by EMG or LCS type groups
| * Sea dyke * Interior dyke |  |  | Preventive: Breach closing, repair of rain cuts, ruts, public cuts etc | 1 | [7 empty] | 0
Sluice |  | 1=(8-v) | BWDB
|  |  |  | Civil works | 3 | 0.4 | [6 empty] | 0.4 | Including rehabilitation of old (remove gates)
|  |  |  | Mechanical Regular | 1 | 0.32 | [6 empty] | 0.32
|  |  |  | Mechanical periodic | 2 | 0.16 | [6 empty] | 0.16
|  |  |  | Cleaning debris | 1 |  |  |  | 0.04 |  |  |  | 0.04 | 2 labours/week; monsoon
Sluice (old, CEP) |  | 2-v | BWDB | renovation |  | 0.2 | [6 empty] | 0.2
Main khals |  | 11 km | BWDB | Reexcavation: Rehabilitation | 5 | 9 | [6 empty] | 9
| D-1 (Banskhali U/s and D/s), D-2 and D-3 |  |  | Preventive: removal cross dams, fishing nets | 1 | [7 empty] | 0
Secondary khals |  | 15 km | BWDB | Reexcavation: Rehabilitation | 5 | 1.44 | [6 empty] | 1.44
| C-1 to C-8 |  |  | Preventive: removal cross dams, fishing nets. | 1 | [7 empty] | 0 | Remove or pay for the labours
LGED infrastructure
Feeder Road-B |  | 10 km | LGED | a) Periodic: seal coat | 5 |  | 2.96 | [5 empty] | 2.96
|  |  |  | b) Earthwork: slope/shoulder repair |  |  |  |  | 0.16 |  |  |  | 0.16
Rural road (earthen) |  | 21 km | LGED | earth work: slope/ shoulder repair | 1 |  | 1 | 0.32 |  |  |  |  | 1.32
Bridge |  | 2 | LGED | approach repair | 1 |  |  | 0.06 | 0.06 |  |  |  | 0.12
Foot Bridge |  | 3 | LGED | approach repair | 1 |  |  | 0.09 |  |  |  |  | 0.09
Box culverts |  | 10 | LGED | approach repair | 1 | [7 empty] | 0 | maintenance is included in road
Pipe culverts |  | 13 | LGED | earth work | 1 |  |  | 0.1 | 0.06 |  |  |  | 0.16
|  |  |  | Pipe replacement | 3 |  | 0.2 | [5 empty] | 0.2
TOTAL | [5 empty] | 13.22 | 4.16 | 0.57 | 0.32 | 0 | 0 | 0 | 18.27
We the undersigned agreed to implement the above maintenance plan in the next five years.
| XEN, BWDB |  |  | XEN, LGED |  |  | Chairman |  |  |  |  | Manager, WMC
| Noakhali |  |  | Noakhali |  |  | Char Bata UP |  |  |  |  | Char Majid